## Summary
S/N | Project Description | Owner | Success Factor | Expected Completion | Stakeholders | Progress | Status | Cost Savings | Labor savings | Space savings | Status | Comments
1 | Automation of Keypoint tubing bending process | Guan Yee | Innovation | Q2 2021 | WPPL | 0% | 100% | N.A | N.A | N.A | Not started | To be discussed | 2020 Project Status | Status
2 | eOESR project | Siddharth | Innovation | Q4 2020 | WPPL, MILFORD, WILMSLOW | 0% | 100% | N.A | N.A | N.A | KIV to Q3 |  | Total Projects | 16
3 | Root Cause Analysis/Field Mfg investigation for BioAccord LC stacks | Chan Yee Hwa | Quality | Q4 2020 | WPPL, MILFORD | 50% | 50% | N.A | N.A | N.A | Excel on findings to be shared |  | Completed | 3
4 | ePR system | Siddharth | Innovation | Q4 2020 | WPPL | 25% | 75% | N.A | N.A | N.A | Working with Tim Norton |  | Open | 10
5 | Upgrade of PC/testers in 2020 - Pump Tray testers Q1/Sample Managers Q3/alliance Q4 | Huazhen | Growth | Q4 2020 | WPPL, MILFORD, WILMSLOW | 25% | 75% | N.A | N.A | N.A | Alliance Pump Tray completed in Q1 2020 |  | KIV | 3
6 | ICT transfer (All PCBAs Altera) | Edwin | Growth | Q4 2020 | WPPL, MILFORD, | 25% | 75% | N.A | N.A | N.A
7 | Packaging Improvement - Detectors Q1/BSM&QSM Q2 | Guan Yee | Growth | Q2 2020 | WPPL, MILFORD | 50% | 50% | N.A | N.A | N.A | Detector completed (update savings)
8 | IDP Projects | Yee Hwa/ Guan Yee | People | Q1 2020 | WPPL | 100% | 0% | N.A | N.A | N.A |  | Employee interaction (AWWA)
9 | FTN Labour Redistribution/ Lean | Desmond | Growth | Q1 2020 | WPPL | 100% | 0% | N.A | N.A | N.A | Completed (please update $ savings)
10 | DSOP | Edwin | Quality | Q1 2020 | WPPL | 50% | 50% | N.A | N.A | N.A | DSOP with Cioplenu
11 | UDI labelling | Eugene | Growth | Q4 2020 | WPPL | 0% | 100% | N.A | N.A | N.A
12 | Tooling Renewal - SG ability to support tooling | Guan Yee | Quality | Q2 2020 | WPPL | 25% | 75% | N.A | N.A | N.A | Access rights granted. Need training
13 | E-Returns (instrument) | Siddharth | Quality | Q2 2021 | WPPL | 0% | 100% | N.A | N.A | N.A | KIV to Q4
14 | Development of Nitrogen (N2) for Project Mantis | Yee Hwa | Growth | Q4 2020 | WPPL | 25% | 75% | N.A | N.A | N.A
15 | Calibration migration to Micro Precision | Huazhen | Innovation | Q1 2020 | WPPL | 100% | 0% | N.A | N.A | N.A
16 | APAC Repair Center | Siddharth | Innovation | Q4 2020 | WPPL | 25% | 75% | N.A | N.A | N.A
|  |  | Quality |  |  |  | 0%
|  |  | Customer Experience |  |  |  | 25%
|  |  | Innovation |  |  |  | 50%
|  |  | Growth |  |  |  | 75%
|  |  | People |  |  |  | 100%