## Manufacturing Setup
Product Transfer - Waters QDa Instrument Level | [44 empty] | Document Number : ENG-011 Rev 0
[6 empty] | Aug 2017 |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan/2018 |  |  |  | Feb |  |  |  | Mar
ID | Task Name | Ownership | Duration (Week) |  | Closed | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19
1 | Manufacturing Setup | [44 empty] | Remarks
1.1 | Identify Requirements of Space, Utilities, Environment, Cleanroom, ESD, Network, Flooring, Gasing, AirCon, Ventilation, Security, etc | GES | 4 | Plan | Closed | bar: Aug 2017 W33 to Sep W36
Actual | bar: Aug 2017 W33 to Sep W36
1.2 | Identify Software For Manufacturing (Printing, Testing, Data Collection, Traceability, etc) | Waters & GES | 4 | Plan | Closed | bar: Aug 2017 W33 to Aug 2017 W35
Actual | bar: Aug 2017 W33 to Aug 2017 W35
1.3 | Develop Equipment List, Include Consignment | Waters & GES |  | Plan | Closed | bar: Aug 2017 W35
Actual | bar: Aug 2017 W35
1.4 | Finalize Floor Layout Design & Material Flow Path | GES | 2 | Plan | Closed | bar: Aug 2017 W35 to Sep W36
Actual | bar: Aug 2017 W35 to Sep W36
1.5 | Quotation & Cost Computation | GES |  | Plan | Closed | bar: Aug 2017 W35
Actual | bar: Aug 2017 W35
1.6 | Obtain Capex Approval For Setup Cost | GES |  | Plan | Closed | bar: Sep W36
Actual | bar: Sep W36
1.7 | Submit Purchase Request To Place Order To Vendor | GES |  | Plan | Closed | bar: Sep W37
Actual | bar: Sep W37
1.8 | Define Equipment Installation Plan Schedule | GES |  | Plan | Closed | bar: Sep W36
Actual | bar: Sep W36
1.9.1 | Order & Shipment Of New Equipment/Tool For Line Setup (Nitrogen LT 6 weeks) | GES | 8 | Plan | Closed | bar: Sep W37 to Nov W44
Actual | bar: Sep W37 to Nov W46
1.9.2 | Shipment of Consigned Equipment - Assembly Jig | Waters | 2 | Plan | [41 empty] | 2 jig Received but cannot use | bar: Oct W43 to Nov W44; Dec W50 to Mar W19
Actual
1.9.3 | Shipment Of Consigned Equipment - Tester | Waters | 2 | Plan | Closed | [40 empty] | For the 4 testesr - Ready | bar: Oct W43 to Nov W44
Actual | bar: Oct W43
1.10.1 | Shifting Column Manager Production Line To Vacate Area For QDa Line Setup | GES |  | Plan | Closed | bar: Oct W40
Actual | bar: Oct W40
1.10.2 | Verification Of Column Manager Production Line In New Site | Waters & GES |  | Plan | Closed | bar: Oct W41 to Oct W43
Actual | bar: Oct W41 to Oct W43
1.11.1 | Shifting Detector Optic Bench Station Within Cleanroom To Vacate Area For QDa Line Setup | GES |  | Plan | Closed | bar: Oct W41
Actual | bar: Oct W41
1.11.2 | Verification Of Detector Optic Bench Station In New Site Within Cleanroom | Waters & GES |  | Plan | Closed | bar: Oct W42
Actual | bar: Oct W42
1.12 | Execute Manufacturing Process Setup | GES | 4 | Plan | bar: Oct W43 to Mar W19
Actual
1.12.1 | Electrical Installation | GES |  | Plan | Closed | [40 empty] | Installation change to week 45 due to relocation of nitrogen generator. | bar: Oct W43 to Nov W45
Actual | bar: Nov W45
1.12.2 | Network Point installation | GES |  | Plan | Closed | bar: Nov W45
Actual | bar: Nov W44
1.12.3 | Air/Exhaust Piping Installation | GES |  | Plan | Closed | bar: Nov W44 to Nov W46
Actual | bar: Nov W46
1.12.4 | Nitrogen Generator Installation | GES |  | Plan | Closed | bar: Nov W45 to Nov W46
Actual | bar: Nov W46
1.12.5 | Setup Raw Material & WIP Area | GES |  | Plan | Closed | [40 empty] | Need to close by next week | bar: Oct W43; Dec W51; Feb W4 to Mar W18
Actual | bar: Mar W11
1.12.6 | Setup Work Stations In White Room | GES |  | Plan | Closed | bar: Oct W43; Dec W51
Actual | bar: Dec W49
1.12.7 | Setup Final Test Station In White Room | GES |  | Plan | Closed | bar: Oct W43; Nov W46
Actual | bar: Nov W46
1.12.8 | Setup Work Stations In Clean Room | GES |  | Plan | Closed | bar: Nov W44 to Nov W46
Actual | bar: Nov W46
1.12.9 | Setup Test Station In Clean Room | GES |  | Plan | bar: Nov W45
Actual
1.12.10 | Setup Label Printing Station | GES |  | Plan | Closed | [40 empty] | Need to confirm the label printing format and type | bar: Oct W43; Dec W51 to Mar W19
Actual | bar: Mar W11
1.12.11 | Allocate Manufacturing Fixtures & Tools To Assigned Stations | GES |  | Plan | [41 empty] | Go-NO Go Guide issue (colin) Leak check adapter for PCB 633 (Sufern / John). | bar: Nov W44; Dec W50; Feb W4 to Mar W19
Actual
1.12.12 | Test Equipment Installation | Waters & GES |  | Plan | Closed | [40 empty] | 4 Test Bays installed | bar: Nov W46 to Nov W47
Actual | bar: Nov W46 to Nov W47
1.12.13 | Production Database Setup | GES |  | Plan | Closed | bar: Oct W43; Dec W51; Feb W4 to Mar W19
Actual | bar: Mar W11
1.12.14 | PC Server Setup | Waters |  | Plan | Closed | bar: Oct W40; Nov W44; Nov W47
Actual | bar: Nov W47
1.13 | Qualification Of Facility Setup | Waters & GES |  | Plan | Closed | bar: Nov W47
Actual | bar: Nov W47
1.14 | Qualification Of Test Equipment | Waters & GES | 2 | Plan | Closed | bar: Nov W47 to Dec W48
Actual | bar: Nov W47
Plan
Complete
add standard tool list with statues

## Jig and Fixture
Tools and fixture
S/NO | Tools / Fixture | Received | Status | ASP | Leadtime | Remarks
1 | Assembly Fixture: WPN AN52370 | Received on 8th Jan. | Closed | 45602
2 | Soldering Fixture: WPN AN52385 | Received on 8th Jan. | Closed | 45607
3 | Modified Socket or 11mm spanner | Received | Closed | 45615
4 | Go/ No Go gauge – (46.50mm to 46.55mm) – Tooling Ref: MP004980. | Received (2 per) | Closed
5 | Segmented Quad Alignment fixture – Tooling Ref: AN52404. | Received (2 per) | Closed
6 | Source Enclosure Fit Gauge - Tooling Ref: AN52401. | Sufern | Closed
7 | Go and No Go Ring Gauges (46.30mm – 46.40mm) | Received (2 per) | Closed
8 | Go/No Go Plate Gauge (40.00mm – 40.10mm) AN52387 | Received (2 per) | Open |  |  | Go/No Go Plate Gauge (40.00mm – 40.10mm) not performing per requirement. Need to rework or fabricate new one. Assign to Collin Marshall (Waters). Need to the gauge by end May.
9 | Segmented Quad Insertion Tool - Tooling Ref: AN52366. | Received (2 per) (AN80028) | Closed
10 | WX 4354 Dowel Inspection tool (Step 5) | Not Required | Closed
11 | Analyser Mount | Received (2 per) (WWT307) | Closed
12 | Alignment Fixture | Received (2 per) (52331) | Closed
13 | GEDORE Torque Wrench (1Nm with 7mm Spanner) | Received on 29 Mar | Closed |  | 2018-03-30
14 | Wiha Insulated Open End Wrench (1000V) 6mm | Received on 29 Mar | Closed |  | 2018-03-30
15 | Qda PMT ring Spacer tool (Step11) | Not Required | Closed
16 | Slip Gauge: YPG 082474 /082475/082476 | Received on 8th Jan. | Closed | 45661
17 | Ring Gauge: WPN MP004999 | Received on 8th Jan. | Closed
18 | Plug Gauge: WPN MP004980 | Received | Closed
19 | Coda Pin Insertion Tool: WPN AN52368 | Received on 8th Jan. | Closed
20 | Diff Aperture Checker: WPN AN52371 | Received on 8th Jan. | Closed
21 | Assembly Fixture: WPN AN52363 | Received on 8th Jan. | Closed
22 | Centre rod (step 17) | Received | Closed
23 | NO Go (Short rod) (5.28-5.38) | Received 8th Jan 18 | Closed
24 | Pin Gauge: Calibrated pin Gauge (1.49-1.51) | Closed - Sufern | Closed | 46483 |  | Not Required
25 | Diff Aperture Plate Checker: WPN AN52371 | Received on 8th Jan. | Closed
26 | Pin Gauge: Calibrated Pin Gauge (0.99- 1.01) | Closed - Sufern | Closed | 46484 |  | Not Required
27 | Diff Aperture Plate Checker: WPN AN52371 | Received on 8th Jan. | Closed
28 | 6366402 GC Septum | Closed Sufern | Closed | 48425 |  | Given 2 pcs
29 | 1x4mm push fit blank | Closed | Closed |  |  | Given 2 pcs
30 | 2x6mm straight tube-tube adapter & blanks | Closed | Closed |  |  | Given 2 pcs
31 | Deburring tools | Received on 6 Mar | Closed | 48899
32 | Pat And Flash Test Box | Closed | Closed
33 | Leak Test Connector | Closed | Closed
34 | Ultrasonic Bath | Received on 6 Mar | Closed
35 | Leak Check Helium Regulator need to be smaller scale. |  | Open |  |  | Need to Purchase a new smaller scale regulator for helium tank. Request from Wexford. Sidd is working on it.
36 | WWT280 QDa Pumping Block Removal Tool |  | Open |  |  | Request from Mandy (WPPL) to fabricate the tools.
37 | Leak check adaptor unable to fit with PCBA 210000633 to perform TSP No. 44914 (Source Interface Leak Check Procedure). |  | Open | 44914
38 | Crocodile Clip for PAT and Flash Tester |  | Open |  |  | For Safety reason, need to get a crocodile clip to secure on the instrument instead of technician holding the probe. Sidd is working on it.

## ASP Update
Sub Assembly Number | Description | Waters Document Number | Rev | Status | Remarks
289011007 | QDA DETECTOR ASSEMBLY II | 48899 | 04 | Received on ECO9218607 | ASP received at rev 04, pending on Wexford update
279002720 | MAINS PSU ASSEMBLY | NA | NA | Submitted to WPPL
289011030 | API GAS INLET VALVE II | NA | NA | Submitted to WPPL
289010953 | QDA ANALYSER MARK 2 | 45615 | 10 | Redlined
289008109 | PUMPING BLOCK ASSY | 45603 | 01 | Submitted to WPPL
289008737 | ASSY, SEGMENTED QUAD | 45661 | 01 | Submitted to WPPL
289010114 | ION BLOCK ASSY MKII | NA | NA | Submitted to WPPL
289008179 | ASSY, TURBO VENT VALVE | NA | NA | Submitted to WPPL
289008857 | ASSY, INTERNAL BACKING LINE | NA | NA | Submitted to WPPL
289010596 | QDA GAS HANDLING ASSEMBLY II | NA | NA | Submitted to WPPL
289007879 | RF COIL BOX | NA | NA | Submitted to WPPL
289011010 | INVISIBLE CALIBRATION ASSEMBLY | NA | NA | Submitted to WPPL
289008649 | ESI ENCLOSURE ASSY | NA | NA | Submitted to WPPL
| QDa Packing | NA | NA | In Progress of Redline