## Flex
[5 empty] | Shipped |  | OK |  | Potential delay, need to monitor |  |  |  | Delay, need immediate action
Updated On: | 2018-04-20 16:27 |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  |  | DO NOT CHANGE
Instrument |  | Q2 Forecast |  | WW14 | WW15 | WW16 | WW17 | WW18 | WW19 | WW20 | WW21 | WW22 | WW23 | WW24 | WW25 | WW26
PN | Short Desc | Prod Plan | QTD Del'd | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | Type of Issue | Status
186269505 | Alliance X | 335 | 51 | 27 | 24 | 24 | 24 | 22 | 24 | 24 | 26 | 22 | 32 | 32 | 24 | 30 | Material | Open
186269506 | Alliance X | 930 | 144 | 76 | 68+11 | 79 | 78 | 62 | 78 | 78 | 76 | 62 | 70 | 70 | 60 | 62 | Quality | Close
186001515 | Pump | 25 | 9 | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 3 | 0 | 4 | 0 | 0 | 0 | Tester
186001525 | Pump | 35 | 12 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 3 | 3 | 2 | 0 | 0 | 0 | Manufacturing
186001825 | Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tooling
WAT207000 | 515 Pump | 70 | 18 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
186015001 | BSM | 80 | 26 | 10 | 8 | 8 | 8 | 6 | 8 | 8 | 8 | 4 | 8 | 4 | 0 | 0
186015018 | QSM | 250 | 138 | 50 | 50 | 38+12 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186015080 | ACQUITY UPLC H-Class QSM PLUS | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 44 | 44 | 36 | 0
186002487 | 2489 Detector | 100 | 18 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 6 | 6 | 12 | 10 | 12
186248900 | Detector X | 740 | 188 | 64 | 60 | 64 | 60 | 48 | 60 | 60 | 60 | 48 | 60 | 60 | 48 | 48
186015031 | 5031 Detector | 270 | 72 | 24 | 24 | 24 | 24 | 16 | 24 | 24 | 24 | 16 | 22 | 16 | 16 | 16
186015032 | 5032 Detector | 270 | 66 | 22 | 22 | 22 | 22 | 16 | 24 | 24 | 24 | 18 | 24 | 28 | 16 | 8
186015033 | 5033 Detector | 210 | 48 | 16 | 16 | 16 | 16 | 18 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
186015034 | 5034 Detector | 23 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | 0 | 0 | 5
186002998 | 2998 Detector | 75 | 0 | 6 | 6 | 6 | 6 | 4 | 6 | 6 | 6 | 4 | 6 | 6 | 6 | 7
186299800 | Detector X | 560 | 84 | 40 | 40 | 4+36 | 40 | 32 | 40 | 48 | 48 | 48 | 48 | 48 | 48 | 40
186017002 | Arc 2489 Detector | 140 | 36 | 12 | 12 | 12 | 16 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 4 | 0
186017003 | Arc 2998 Detector | 165 | 10 | 10+4 | 12 | 12 | 14 | 8 | 12 | 12 | 16 | 12 | 16 | 16 | 9 | 12
186017012 | Arc Bio 2489 UV/Vis Detector | 10 | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186017013 | Arc Bio 2998 PDA Detector | 10 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Part No | Part Description |  |  | Supplier | Instrument Affected | WPPL Team (Lead) | Milford Contact | Type of Issue | Brief Description of Issue | [5 empty] | Target Recovery Date | Status
| Linearity test software |  |  | 2018-04-02: Flex; 2018-04-09: 186015033 186015034 186017003; 2018-04-16: Desmond; 2018-04-30: Tester; 2018-05-07: 19 Jan 18 update: ECO released to Flex on 17-Jan-2018 05 Jan 18 update: Impacted by linearity test software. Desmond is working with Milford to see if there is possibility of TMD to resume production.; 2018-06-18: Monitoring; 2018-06-25: Close
405002568 | OPTICS BENCH, MACHINING, 2998 |  |  | 2018-04-02: JEP; 2018-04-09: 186299800 186002998 186015034 186017003 186017013; 2018-04-16: Bethany; 2018-04-30: Material; 2018-05-07: 20 Apr 18 update : Based on current Qty received 127pcs at Flex, can full fill production requirement till week 17. DC allocation :- 186299800 - 50 units on week 17 (Top priority customer order + forecast) 186015034 - 2 units by week 17 186002998 - 6 units by week 17 186017003 - 16 units by week 18 13 Apr 18 update : Dimension corelation issue btw Flex and JEP after alignment Flex will use JEP data for 2 dimension.Total 39pcs can be released, 18pcs at Flex pending data, 44pcs to be delivered by JEP on Monday(16-Apr). Balance 24pcs on Tuesday(17-Apr). DC alloation :- 186299800 - 50 units on week 16 (Top priority customer order + forecast) 186015034 - 3 units by week 17 186002998 - 6 units by week 17 186017003 - 16 units by week 17 06 Apr 18 update : Total 55pcs rejected due to dimension out (dowel pin hole). JEP to deliver 20pcs on 06-Apr. ship impact: Immediate (33units) and 11-Apr, 66units DC alloation :- 186299800 - 40 units by next week (Top priority customer order + forecast) 186015034 - 3 units by week 17 186002998 - 6 units by week 17 186017003 - 16 units by week 17 29 Mar 18 update : Quality issue (Porosity) needs to be sorted out with Waters and Flex. 56 received, next shipment impact on 11Apr (55units). Alternately, ETLA has been approved and green light was given to Flex to issue PO to ETLA to drive material. 23 Mar 18 update : Continue to monitor. Next shipment impact on 4-Apr (47units) 16 Mar 18 update : Continue to monitor. Next shipment impact on 28-Mar: 1unit. 09 Mar 18 update: Continue to monitor. Next shipment impact on 28-Mar: 19units. 02 Mar 18 update : Continue to monitor. Next shipment impact on 28-Mar: 49units 25 Feb 18 update: Continue to monitor. Next shipment impact on 21-Mar. 14 Feb 18 update: 30pcs deliverd on 08 Feb. Continue to monitor. Next shipment impact on 28 Feb 14 units. 09 Feb 18 update : Weekly shipment from JEP. Continue monitoring. Next shipment impact on 28-Feb: 14units 02 Feb 18 update : Weekly shipment from JEP. Continue monitoring. Next shipment impact on 28-Feb (43units) 26-Jan-18 update : Next shipment impact 28-Feb-2018 19 Jan 18 update : 22units delivered on 18-Jan. Next impact will be on 14-Feb (56units). Flex is continue following up with supplier 12 Jan 18 update: 97pcs received on 04-Jan. 07-Feb: 11units. Flex is continue following up with supplier 05 Jan 18 update: Flex to continue to follow up with JEP. 29 Dec 17 update: 53pcs delivered on 22 Dec. Next potential impact 48units 17 Jan. 22 Dec 17 update: 24pcs delivered on 22 Dec. Next potential impact 10 Jan - 22units. With above Q4 shipment is covered. 15 Dec 17 update: 20pcs delivered on 14 Dec. 19pcs received 15 Dec. 20pcs to be delivered on 18 Dec. With above Q4 shipment is covered. 08 Dec 17 update: 25pcs delivered on 07 Dec. Potential shipment impact on 27-Dec: 39 units. Flex to continue to follow up with JEP. 01 Dec 17 update: 49 pcs delivered on 30/11. Revised shipment impact will be 19 units on 27/12. With consideration of the upside, potential shipment impact 64pcs for this quarter. Continue to follow up with JEP. 24 Nov 17 update: Rejection at JEP due to porosity issue. Potential shipment impact on 13 Dec, 36pcs. For the other 2 parts from JEP (405003295 & 405006788), sufficient qty to meet this quarter shipment and next shipment impact is on 10-Jan-18. Flex to continue follow up. 03 Nov 17 update: Flex to continue to follow up weekly delivery with JEP. 20 Oct 17 update: JEP committed to deliver 65 units weekly. Flex to continue to follow up weekly delivery with JEP. 13 Oct 17 update: 10/12: 57pcs delivered on 12-Oct 10/10: 60pcs delivered on 5-Oct 06 Oct 17 update: Potential shipment impact 71units, 01 Nov. 29 Sep 17 update: Shipment impact 25-Oct: 42units. Flex to continue to monitor weekly delivery. 22 Sep 17 update: Delivery is scheduled for 22/09. Moving forward JEP will deliver 65pcs every week on Thursday and gradually increase the qty if required. 15 Sep 17 update: 24pcs delivered on 14-Sep-17 late afternoon 48pcs scheduled to be delivered today late afternoon With this, new shipment impact is 18-Oct-17 for 46units Flex working with supplier for further schedule. 08 Sep 17 update : - 6pcs reject out of 76pcs from 5-Sep Delivery - the revised impact is 4-Oct-45 units. - JEP has not provided any further ship plan yet. Flex will keep WPPL updated about the status for this part. 31 Aug 17 update : Based on accepted parts, impacting WWK38, 17 units. According to Flex, a new guideline been set for acceptance of the parts with porosity. All the rejects can be used: 36pcs returned from JEP have been received 36pcs at JEP FG - delivered 31 Aug 2pcs delivery TBA STX has shipped raw casting (306pcs) as well to JEP with ETA as 31-Aug-17. Current Lead Time confirmed by JEP is 2Wks turn-around from casting received date. Flex will continue to work with JEP for arranging delivery from new castings as early as possible. In addition to the above qty, ACP has another 48pcs as on yesterday. 25 Aug17 update: High reject at incoming due to cosmetics and poor finishing. Impacting: 1. 120pcs RTV back to JEP and sorted. 2. 42pcs with good condition received. 3. 34pcs ETA on 25 Aug. As per Flex, JEP will continue do sorting and update result daily. Next shipment impact 13 Sep, 34 units. 18 Aug 17 update: Reject of defect Optic bench. Flex return all for sorting. Delivery commitment cover until end August. To monitor closely. 76pcs: 22 Aug 78pcs: 29 Aug; 2018-06-18: ASAP; 2018-06-25: Open
WAT045248 | HPMV Sub Assy Testing |  |  | Flex | 186269505 186269506 WAT045438 | Desmond | Mike Higgins Fred Sarrifi | Manufacturing | 19 Jan 18 update: TMD 010368 has been closed with the effect of ECO9217360 released to Flex on 12.01.2018. 17 Nov 17 update: TMD expire on 01 Feb 2018. Desmond to follow up on ECO for closure prior to TMD expired targeted Jan. 18 Aug 17 update: To follow up on ECO closure, Jan 2018. 04 Aug 17 update: TMD010368 has been issued to allow Flex only perform 100% testing on WAT045248 sub assembly built into spare WAT045438. All sub assembly built into instrument will be tested 100% at final test, instead of sub-assembly level. This would free up the capacity constraint to support instrument build. To follow up with Flex on recovery plan for Spares. 28 July 2017 update : Due to obsolete of SOP WAT077886O Sampling Inspection / Testing, Flex is required to perform 100% testing per TSP735000287, instead of sampling check at 1 out of 8 units for sub assemblies that are built into instruments. This has increased the cycle time and impact the line capacity to fulfill both instruments and spares demand. ECO need to be raised to update ASP for WAT045248 to call for 100% testing per TSP735000287 for all spares only. | [5 empty] | Monitoring | Close
NA | Firmware issue |  |  | 2018-04-02: NA; 2018-04-09: 186015032 186015033; 2018-04-16: Edwin Koh; 2018-04-30: Tester; 2018-05-07: 14 Feb 18 update: 68pcs received on 12-Feb. Another 108pcs to be shipped on 16-Feb. Next shipment impact 28 Feb 72 units. Recovery in progress. 02 Feb 18 update : Recovery in progress. Please refer to recovery tab 26 Jan 18 update : TMD010453 being issued to rework all 186015032 and 186015033 built with On-Semi PDA chips. 5 units affected at ADC has returned to Flex on 26-Jan. Flex has implemented ECO9218579, resume production line with the configuration of Hamamatsu PDA chips and v1.69 firmware 19 Jan 18 update : Flex to put both 186015032 & 186015033 build with old PDA chips on hold, while waiting for Waters final decision if to reload the v1.65 old formware. Waters will provide TMD to Flex should the decision is for Flex to reload with v1.65 old frmware.; 2018-06-18: Monitoring; 2018-06-25: Close
425000540 | MASK, PDA |  |  | Tech-Etch | 186299800 186002998 186015033 186015034 186017003 | Bethany | John Gannon | Material | 02 Feb 18 update : Potential impact on 21-Feb(250pcs): 33units. Supplier confirmed to ship on 2-Feb with ETA 7-Feb to Flex. Salt spray test report will be available by end of this week. 26 Jan 18 update : 150pcs received at Flex and pending for the Salt spray test report. 19 Jan 18 update : Previous lot was rejected due to plating issue and parts were all scrapped and produce the new lot.. Supplier will be shipping the material on 19-Jan-2018 and follow by Salt spray test report. | [5 empty] | ASAP | Close
405003295 405006788 | OPTICS BENCH, MACHINING,2998LG OPTICS BENCH,MACHINING |  |  | 2018-04-02: JEP; 2018-04-09: 186015032 186015033; 2018-04-16: Eugene; 2018-04-30: Quality; 2018-05-07: 02 Feb 18 update : Material has been UAI but no acceptance criteria defined. Continue monitoring. No impact to production. 26-Jan-18 update : Part is being on-hold at Flex QA due to having minor porosity. They are neither having light passing through nor near any screw holes where there is no acceptance criteria established. Pending WPPL QA to review and advise; 2018-06-18: Monitoring; 2018-06-25: Close
WAT270524 279001810 | GPV ASSEMBLY ASSY, GPV, DUAL CHANNEL, QSM |  |  | PARKER HANNIFIN | 186269505 186269506 186015018 | Bethany | John Gannon | Material | 20 Apr 18 update : Part# 279001810 - 100 ETA 23/Apr. 150 pc ETD on 20/Apr and 125 pc ETD on 21/Apr(Qty to be confirmed). Part# WAT270524 - 97pcs received. Parker is working this weekend and they will have a ship plan update for next week on 23/Apr 06 Apr 18 update : Parker production is in recovery mode and expected recover to be the second half of April. Parker is arranging weekly shipment. Under monitoring. Next shipment impact on 25-Apr 29 Mar 18 update : Shipment impact on 11-Apr (7units). 100pcs shipping on 30-Mar-2018. 23 mar 18 update : No impact to Q1'2018 shipment. Continue to monitor.Next Shipment impact on 11-Apr (101units) 16 Mar 18 update : Close to for Q1'2018 shipment. Continue to monitor. Next shipment impact on 4-Apr: 53units 09 Mar 18 update: Continue to monitor. Next shipment impact on 28-Mar: 78units. 02 Mar 18 update : Parker allocation plan : 80pcs ETD 3/02, 108pcs ETD 3/06, 106pcs ETD 3/09, 56pcs ETD 3/12. 25 Feb 18 update: Continue to monitor. Next shipment impact on 7-Mar, but Parker is making weekly shipment on Friday to catch up. 09 Feb 18 update : Potential impact on week 09 shipment for Alliance. Parker is having capacity constraint, they are working to catch up the backlog and arrange shipment according to Flex minimum require Qty. 02 Feb 18 update : Potential impact on week 08 shipment for QSM & Alliance. Parker is having component supply difficulties and hence running into backlogs. Supplier is due to ship next lot on 2/2 for both Part#. Flex is closely monitoring. 92pcs shipped for Part# 279001810 on 31-Jan | [5 empty] | ASAP | Close
NA | Wavelength verification failure |  |  | NA | 186002998 186299800 186017003 186015033 186015034 | Desmond | Eric Turner | Tester | 29 Mar 18 update : Backlog clear 16 Mar 18 update : To continue monitor the shipment. 09 Mar 18 update: Received agreement from Milford team to step down the testing - revert to normal 1x final test with additional power recycling step. To closely monitor production recovery. To complete shipment on last day of Q1 - 29-Mar-18. 02 Mar 18 update : Flex is still struggling to clear backlog. Current direction to Flex is to test final units 2 times to ensure there are no intermittent failure issue. refer to recovery tab. 25 Feb 18 update: Flex is still struggling to clear backlog. Current direction to Flex is to test final units 2 times to ensure there are no intermittent failure issue. To date, the backlog quantity affected are 186299800 102 units, 186017003 43 units, 186015033 29 units, 186002998 12 units and 186015034 3 units. 18 Feb 18 update: Suspected the wavelength verification failure is due to grating PN 402000198 supplied by Horiba. Flex is currently liaising with Horiba to get more testing data details on the recent lots from Horiba. Will need to verify if this is the root cause or due to any other issue. 09 Feb 18 update : Eric got a unit to fail while on hyperterm and got the details to send to the firmware engineer for analysis. Continue run and ship PDA/ELAMBDA units as we are not seeing the wavelength verification failure for new build instrument of PDA and eLAMBDA instruments. Flex will still perform additional test (recycle power and ensure initialization ok) for PDA/ ELAMBDA. Continue evaluation for 2998X, control run 2998x model with limited qty(4x) using 477 charge amp board from different lot code (200118) to see results. | [5 empty] | ASAP | Close
210000444 | ASSY, PCB ALLIANCE H/C |  |  | 2018-04-02: Flex Senai; 2018-04-09: 186269506; 2018-04-16: Edwin Shaynee; 2018-04-30: Quality; 2018-05-07: 13 Apr 18 update : No Impact to production. Shaynee to follow up with Failure analysis report. 06 Apr 18 update : Production continue and so far no impact to production. Pending for Failure analysis from Flex senai. report target to be receivde on end of 06-Apr. 29 Mar 18 update : Flex has started loading 444 PCBA by using IC date code 1736 on 24-Mar. Everything was OK until 26 Mar evening, whereby production reported 3u fail and on 27 Mar production reported another 1u fail. Flex is doing additional H/C testing to continue production. Flex to provide the failure analysis report. 23 Mar 18 update : 1723 date code additional testing no re-curring of the error code observed previously. Flex to continue the rest of the 1723 date code. When date code 1726 arrive Friday 23 Mar, Flex to switch to use date code 1726. Flex KP to work with Flex Senai on the root cause analysis. Flex KP production to continue monitoring of date code 1726. 16 Mar 18 update : Eugene & Edwin agreed using old DC 1723 to continue production, those with pass result is shippable and rejected need to be on hold. Result will be available on Monday. Flex is continue pulling in new DC for Avago MPN from manufacturer and open market. 09 Mar 18: During the weekly FPY review, it is observed that there is a surge in failure of 3 units of 210000444 in week of 02-Mar-18, and the failure analysis for previous months has not been forthcoming. Flex to purge current PCBA lot back to Senai and pull in fresh lot (new datecode) to resume production and access the performance of the new datecode PCBA.; 2018-06-18: Monitoring; 2018-06-25: Close
NA | NA |  |  | NA | 186269505 186269506 | Yee Hwa | Mike Cotter Joshua Burnett | Manufacturing | 20 Apr 18 update : Flex have committed to output 20/day per recovery plan. Will be able to meet quarter number. 13 Apr 18 update : 70% test yield, Milford is working on Abnormal Peak issue which contribute to 18% of the yield loss. | [5 empty] | ASAP | Open
279003850 | ASSY, SOLENOID VALVE, 3-WAY |  |  | 2018-04-02: Bio-Chem; 2018-04-09: 186269505 186269506; 2018-04-16: Bethany; 2018-04-30: Material; 2018-05-07: 20 Apr 18 update : 200pcs intransit (ETA 23-Apr), Next ship date on 27-Apr; 2018-06-18: ASAP; 2018-06-25: Open
WAT026574 | SCR 8-32 SHOULDER |  |  | 2018-04-02: M&J; 2018-04-09: 186001515 186001525 WAT207000; 2018-04-16: Bethany; 2018-04-30: Material; 2018-05-07: 20 Apr 18 update : Localized from Ronco to asia supplier M&J. Due to short LT, M&J is pending for Marcorubber part for risk build & FA. Marcorubber committed to ship 5/4 with expediting fees paid, ETA 5/7 at M&J, and ETD M&J 5/9. Pre-alert, supplier’s expediting for improvement. Checking with Milford if able to support.; 2018-06-18: ASAP; 2018-06-25: Open
279002660 | ASSY, PRE-AMP WITH CABLE 2489 |  |  | 2018-04-02: Flex Senai; 2018-04-09: 186015031 186248900 186017002; 2018-04-16: Hua Zhen; 2018-04-30: Tester; 2018-05-07: 20 Apr 18 update : Flex Senai will rent a unit to use for production, the rental unit will ETA Senai on 24-Apr (for noise and reference test).; 2018-06-18: ASAP; 2018-06-25: Open
Note on B7: sgblim: New Seal pack implementation
Note on B8: sgblim: New Seal pack implementation
Note on H14: sgblim: Parker
Note on G21: sgblim: JEP
Note on F22: sgblim: JEP
Note on H23: sgblim: JEP
Note on F25: sgblim: JEP
Note on F27: sgblim: JEP

## Venture
[5 empty] | Shipped |  | OK |  | Potential delay, need to monitor |  |  |  | Delay, need immediate action
Updated On: | 2018-04-20 16:27 |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  |  | DO NOT CHANGE
Instrument |  | Q2 Forecast |  | WW14 | WW15 | WW16 | WW17 | WW18 | WW19 | WW20 | WW21 | WW22 | WW23 | WW24 | WW25 | WW26
PN | Short Desc | Prod Plan | QTD Del'd | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | Type of Issue | Status
186001500 | 1500 CH | 35 | 9 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | Material | Open
186002441 | TCM | 70 | 24 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 0 | 0 | 0 | 0 | Quality | Close
186002449 | PCM | 25 | 8 | 4 | 0 | 4 | 0 | 0 | 4 | 4 | 4 | 5 | 0 | 0 | 0 | 0 | Tester
186001791 | Alliance CH/C | 12 | 4 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Manufacturing
186001863 | Alliance CH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tooling
186179100 | Alliance X CH/C | 670 | 168 | 56 | 56 | 56 | 60 | 40 | 56 | 56 | 60 | 40 | 60 | 58 | 40 | 32
186186301 | Alliance X CH | 580 | 144 | 48 | 48 | 48 | 44 | 44 | 48 | 48 | 44 | 44 | 44 | 44 | 40 | 36
186015007 | CM - Right | 18 | 9 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186015008 | CH/C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186015009 | CM - Left | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186015010 | HTCH | 40 | 12 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 0 | 4 | 4 | 0 | 4
186015011 | 30cm CH/C | 160 | 36 | 12 | 12 | 12 | 12 | 12 | 12 | 16 | 12 | 12 | 12 | 12 | 12 | 12
186015042 | CH-A | 560 | 140 | 48 | 48 | 44 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
186015043 | CM-A | 350 | 96 | 32 | 32 | 32 | 32 | 24 | 30 | 24 | 24 | 24 | 24 | 24 | 24 | 24
186015045 | HTCH-30A | 75 | 24 | 8 | 8 | 8 | 8 | 5 | 8 | 8 | 8 | 4 | 10 | 0 | 0 | 0
186015049 | CM-Aux | 100 | 24 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4
186015038 | UPC2 CM-A | 10 | 4 | 4 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0
186015039 | UPC2 CM-Aux | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186015017 | FTN | 180 | 74 | 50 | 49+1 | 0 | 50 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186015046 | I-Class FTN | 180 | 20 | 10 | 10 | 9+1 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186015029 | FLR Detector | 140 | 28 | 14 | 12 | 2+10 | 12 | 6 | 12 | 12 | 12 | 6 | 12 | 12 | 12 | 6
186002475 | 2475 Detector | 22 | 0 | 2 | 6 | 0 | 6 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
186247500 | 2475 Detector | 135 | 40 | 12 | 12 | 6+6 | 12 | 10 | 12 | 12 | 10 | 12 | 10 | 10 | 6 | 0
186015000 | I-BSM | 70 | 40 | 14 | 14 | 12+2 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186017000 | ACQUITY Arc QSM-R | 290 | 60 | 30 | 30 | 29+1 | 30 | 24 | 21 | 21 | 21 | 16 | 20 | 21 | 16 | 10
186017006 | Arc 2475 Detector | 31 | 1 | 1+4 | 0 | 6 | 0 | 6 | 0 | 0 | 6 | 5 | 6 | 6 | 0 | 0
186017008 | Arc 30cm CH | 90 | 12 | 4 | 4 | 4 | 4 | 4 | 8 | 8 | 8 | 12 | 8 | 10 | 8 | 8
186017009 | Arc 30cm CH/C | 175 | 48 | 16 | 16 | 16 | 16 | 12 | 16 | 16 | 12 | 8 | 12 | 12 | 12 | 11
186017014 | Arc Bio 30cm CH | 10 | 10 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186017015 | Arc Bio 30cm CH/C | 12 | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186015082 | ACQUITY UPLC I-Class BSM PLUS | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 23 | 23 | 22 | 24 | 23 | 22 | 20
186015085 | ACQUITY UPLC H-Class FTN-H PLUS | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 47 | 44 | 37 | 46 | 44 | 37 | 37
186015088 | ACQUITY UPLC I-Class FTN-I PLUS | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 18 | 19 | 13 | 17 | 19 | 13 | 11
Part No | Part Description |  |  | Supplier | Instrument Affected | WPPL Team (Lead) | Milford Contact | Type of Issue | Brief Description of Issue | [5 empty] | Target Recovery Date | Status
290001119 290001193 | BOX, SHIPPING, ACQUITY COLUMN HEATER BOX, SHIPPING, ACQUITY UPLC CH-A |  |  | 2018-04-02: J&J; 2018-04-09: 186015010 186015042; 2018-04-16: Yin Ying; 2018-04-30: Material; 2018-05-07: 30-Sep-2016 update : On-going review with venture. 23-Sep-2016 update : Compilation in progress, will review with venture team for submission. 26-Aug-2016 update : Evaluation report compilation in progress 08-July-2016 update : Built of 2 units to be shipped to TUV and Venture to witness for the test. 01-July-2016 update : Built of 2 units to be carried out on 1st week of July for drop test. 17-Jun-2016 update : Built of 2 units will be carried out by end of Q2 for drop test. 27-May-2016 update : TUV(Test Lab) can perform test protocol per Waters spec, pending Quote from TUV. Material allocated 2 sets for drop testing. 13-May-2016 update : In progress of drafting test protocol for Milford to review before proceed with the test. 15-Apr-2016 update : Eugene has reviewed the carton Box based on supplier drawing with no concern on the dimentional. Yin Ying to follow up with Venture for the 2 Units built, drop test & reliabulity test before can submit ECR. 08-Apr-2016 update : Carton box inspected and approved by VEnture, will liase with Eugene for dimensional buy off. Venture is preparing material to build 2 sets of instrument for drop test. 24-Mar-2016 update : Sample received on 22-Mar, Venture is inspecting the dimension. 11-Mar-2016 update : FA submission on 22/Mar. 26-Feb-2016 update : FA submission by mid March 15-Jan-2016 update : To activate Venture to work with supplier on FA sample using DW material.; 2018-06-18: Q4; 2018-06-25: Open
289010609 | ASSY, MIXER, 4.6MM X 100MM, 200um |  |  | Waters | 186017000 | Yin Ying | Dave Robinson | Material | 05-Feb-2016 update : 10pcs received by Venture on 1st Feb 2016.(Monday) Fedex# 509096121145. 13pcs ETD 04-Feb - Fedex# 509096142165 ETA(10-Feb-2016) 28-Jan-2016 update : Last gating part# 289010609, 10pcs estimated to dock Venture on 1st Feb 2016.(Monday) Fedex# 509096121145. 22-Jan-2016 update : Last gating part for 186017000 after the first 17 units build. | [5 empty] | ASAP | Close
725000459 | ASSY, PCB, DEGASSER, QSPI MULTI-PERS |  |  | 2018-04-02: IDEX; 2018-04-09: 186015000; 2018-04-16: Eugene; 2018-04-30: Quality; 2018-05-07: 19-Feb-2016 update : Missing label on U7 component, CoC needed to prove that the board has the firmware version of V1.05. CoC obtain on 17-Feb-2016. Production resume. 05-Feb-2016 update : 725000459-R(IDEX) QOH high rejected due to Fail Functional: Vacuum Pump Failure & 50pcs new lot missing label, replacement TBA. Eugene to update the finding.; 2018-06-18: ASAP; 2018-06-25: Close
289007089 | ASSY,CH-30A DOOR |  |  | 2018-04-02: FUYU; 2018-04-09: 186015045; 2018-04-16: Eugene; 2018-04-30: Quality; 2018-05-07: 13-May-2016 update : No Impact to production. CH-30A Dowel Pin Missing/Falling Off - Column door loose issue. - Short term solutions - Venture & Fuyu had established the inspection method to inspect the part before release to production. After implementation of the short term solution, they actually caught 48pcs and reject 48pcs out of 230 material and the fall out rate is 20.8% (48/230) - Long term solution - Per Jared feedback, his opinion is this is not design issue and so long as supplier process ensure parts made correctly per requirements. - WPPL has rejected FUYU proposed supplier - TCR(Distributor). HTM is able to honor the same price as per existing $ 13.90 for MOQ = 100pcs. Will link up FUYU & HTM to proceed for FA sample. 06-May-2016 update : No Impact to production. CH-30A Dowel Pin Missing/Falling Off - Column door loose issue. - Short term solutions - Venture & Fuyu had established the inspection method to inspect the part before release to production. After implementation of the short term solution, they actually caught 48pcs and reject 48pcs out of 230 material and the fall out rate is 20.8% (48/230) - Long term solution - Per Jared feedback, his opinion is this is not design issue and so long as supplier process ensure parts made correctly per requirements. - WPPL has rejected FUYU proposed supplier - TCR. Alternately, requesting quotation from HTM/ACHB. 29-Apr-2016 update : No Impact to production. CH-30A Dowel Pin Missing/Falling Off - Column door loose issue. - Short term solutions - Venture & Fuyu had established the inspection method to inspect the part before release to production. After implementation of the short term solution, they actually caught 48pcs and reject 48pcs out of 230 material and the fall out rate is 20.8% (48/230) - Long term solution - Per Jared feedback, his opinion is this is not design issue and so long as supplier process ensure parts made correctly per requirements. - After reviewing FUYU proposed supplier - TCR company profile and found TCR is just a distributor. Alternately, requesting quotation from HTM. 22-Apr-2015 update : No Impact to production. CH-30A Dowel Pin Missing/Falling Off - Column door loose issue. - Short term solutions - Venture & Fuyu had established the inspection method to inspect the part before release to production. After implementation of the short term solution, they actually caught 48pcs and reject 48pcs out of 230 material and the fall out rate is 20.8% (48/230) - Long term solution - Per Jared feedback, his opinion is this is not design issue and so long as supplier process ensure parts made correctly per requirements. FUYU proposed new supplier - TCR for Part# 405011878. FUYU will share the quotation & estimated FA submission date once available. 15-Apr-2016 update : No Impact to production. CH-30A Dowel Pin Missing/Falling Off - Column door loose issue. - Short term solutions - Venture & Fuyu had established the inspection method to inspect the part before release to production. After implementation of the short term solution, they actually caught 48pcs and reject 48pcs out of 230 material and the fall out rate is 20.8% (48/230) - Long term solution - Per Jared feedback, his opinion is this is not design issue and so long as supplier process ensure parts made correctly per requirements. FUYU has feedback to WPPL on 23-Mar-2016 that the supplier has declared they will not be producing the part for FUYU anymore. Yin Ying to work with FUYU on alternate sourcing and FA submission for Part# 405011878 Hinge support. 08-Apr-2016 update : No Impact to production. CH-30A Dowel Pin Missing/Falling Off - Column door loose issue. - Short term solutions - Venture & Fuyu had established the inspection method to inspect the part before release to production. - Long term solution - Per Jared feedback, his opinion is this is not design issue and so long as supplier process ensure parts made correctly per requirements. 26-Feb-2016 update : CH-30A Dowel Pin Missing/Falling Off - Column door loose issue. - Short term solutions - Venture & Fuyu had established the inspection method to inspect the part before release to production. - Long term solution - QA to feedback to Randy and Mike Cook and pending for their response. 19-Feb-2016 update : CH-30A Dowel Pin Missing/Falling Off - Column door loose issue. - Short term solutions - Venture & Fuyu had established the inspection method to inspect the part before release to production. - Long term solution - QA to advice and update.; 2018-06-18: Monitoring; 2018-06-25: Close
405011878 | HINGE SUPPORT,CH-30A |  |  | 2018-04-02: FUYU; 2018-04-09: 186015045; 2018-04-16: Bethany Eugene; 2018-04-30: Material Quality; 2018-05-07: 30-sep-2016 update : Venture updated that both fitting test and durability test are passed. 23-Sep-2016 update : 3pcs sample of 289007089 received by Venture passed the part level verification. Venture will perform fitting test and durability test ( 200 time door open and close). Venture will update with the result. 16-Sep-2016 update : FUYU will arrange 3pcs sample of 289007089 to Venture to buy off. 09-Sep-2016 update : Fuyu has conduct assembly test at FG level by using HTM FA sample. result looks good. FUYU to submit FA report to Venture for approval. 12-Aug-2016 update : HTM FA sample will only be ready for submission on end of August. Fuyu will schedule to have FG level for review by 5th Sept’16 . 05-Aug-2016 update : Fuyu has came back that paint peel off issue is due to metal part didnt go through primer process prior to paint process. 22-July-2016 update : Paint peel off - Fuyu has received the AL plate sample with surface treatment(chromate conversion) from HTM and will perform paint test by next week. 08-July-2016 update : 1st FA submission by HTM was rejected by FUYU. 1) Paint peel off --> Need FUYU to check with previous supplier on the chemical conversion for coating whether per Waters spec 735001516. 2) Getting FUYU to release 20pcs risk run order to HTM to see the process capability. And need HTM to perform cross section(3pcs) & painting & form fit function test(5pcs). 01-July-2016 update :1st FA submission by HTM was rejected by FUYU and found 2 findings 1) Paint peel off 2) Hold depth concern, HTM to submit dimension for FUYU to verify. FUYU to advise on the 2nd FA submission from HTM. 17-Jun-2016 update : No Impact to production. FA from HTM received by FUYU meeting spec. FUYU will install at final assy 289007089. Will update the result in return 20-May-2016 update : No Impact to production. Has linked up both HTM & FUYU for FA sample submission. HTM FA sample submission on 15-Jun 13-May-2016 update : No Impact to production. - WPPL has rejected FUYU proposed supplier - TCR(Distributor). HTM is able to honor the same price as per existing $ 13.90 for MOQ = 100pcs. Will link up FUYU & HTM to proceed for FA sample. 06-May-2016 update : No Impact to production. - WPPL has rejected FUYU proposed supplier - TCR. Alternately, requesting quotation from HTM/ACHB. 29-Apr-2016 update : No Impact to production. - After reviewing FUYU proposed supplier - TCR company profile and found TCR is just a distributor. Alternately, requesting quotation from HTM. 22-Apr-2015 update : No Impact to production. FUYU proposed new supplier - TCR for Part# 405011878. FUYU will share the quotation & estimated FA submission date once available. 15-Apr-2016 update : No Impact to production. FUYU has feedback to WPPL on 23-Mar-2016 that the supplier has declared they will not be producing the part for FUYU anymore. Yin Ying to work with FUYU on alternate sourcing and FA submission for Part# 405011878 Hinge support.; 2018-06-18: Monitoring; 2018-06-25: Close
405003366 | SUPPORT PLATE THICKENED VHP HEAD |  |  | 2018-04-02: Yangbum; 2018-04-09: 186015000; 2018-04-16: Wan-Jing; 2018-04-30: Quality; 2018-05-07: 04-Mar-2016 update: Recleaning as per schedule at Richport –no further shipment delay reported. Richport delivered 850pcs - this met Venture’s immediate requirement. No issues to highlight. 26-Feb-2016 update : Part# 405003366 every package at Yangbum has the small puncture which violates critical clean packaging. All affected parts at Yangbum will be reclean and repackage by Richport. Currently recleaning is in progress at Richport. Richport will prioritise partial delivery of min. 100pcs by 02 Mar for Venture’s requirement.; 2018-06-18: Monitoring; 2018-06-25: Close
210000852 (210000282 Old PCBA) 210000891 (210000361 Old PCBA) | ASSY, PCB, ETHERNET SWITCH |  |  | Venture | 186015007 186015008 186015009 186015010 186015017 186015046 700003191 | Edwin | Gene Tancrell | Material | 06-May-2016 update : ECO 9205805 has been released to Venture. F/up with leading SN. 29-Apr-2016 update: Impact sheet submitted from WPPL. Pending Milford Impact Sheet to complete the ECR flow before out for approval. At the same time, Milford has routed TMD010100 for extension. Need to be "active" before 2-May-16 expiry date. 22-Apr-2016 update : ECR 9205805 has released to Venture to process for impact sheet submission. 15-Apr-2016 update : Follow up ECR 9205805 to be released. (Status : Assigned) Per last update from Gene - Testing in RDEL is still not complete and need their report before she can complete the ECR. 01-Apr-2016 update : Follow up ECR 9205805 to be released. (Status : Assigned) 24-Mar-2016 update : TMD received. Venture has started to re-programme the PCBA with new firmware 361000622 Rev B. Production and shipment recovery in progress. 18-Mar-2016 update : To allow production to resume while pending validation, the proposal is to use un-validated firmware for production under TMD but all existing inventory must be reworked. 11-Mar-2016 update : Approval was given to ship 186015010 by using 210000852 PCBA. 186015007 & 186015009 & spare 700003191 continue to be on hold until there is a re-design on firmware. Recovery schedule TBA. 04-Mar-2016 update : New Ethernet Card 210000852 cannot communicate with Test Station. Pending Milford to advice next step. 26-Feb-2016 update : New Ethernet Card 210000852 cannot communicate with Test Station (TE82987-1). Venture to provide update. Failure Symptom: Unit under Testing not able to obtain IP address from test station. | [5 empty] | Monitoring | Close
210000891 (210000361 Old PCBA) | ASSY, PCB, ETHERNET SWITCH |  |  | 2018-04-02: Venture; 2018-04-09: 186015017 186015046; 2018-04-16: Edwin; 2018-04-30: Material; 2018-05-07: 11-Mar-2016 update : Approval from Waters on 10/Mar to proceed shipment. 04-Mar-2016 update : Waters Milford requested to on hold shipment FTN while they are confirming if the PCBA is OK due to using Ethernet switch; 2018-06-18: ASAP; 2018-06-25: Close
415000656 | HOUSING,HEATER |  |  | 2018-04-02: Oneida; 2018-04-09: 186015010 186015029; 2018-04-16: Bethany; 2018-04-30: Material; 2018-05-07: 18-Mar-2016 update : Shipment resume. issue closed. 11-Mar-2016 update : Paint issue is due to Oneida using new batch of SW powder and need Waters to buy off. Approval has been obtained and production is resumed, and committed date is on ETD 14/Mar. Venture is expediting with Oneida for better delivery date. No response from Oneida as of Friday. 04-Mar-2016 update : Potential delay due to Paint Issue. Pending supplier to provide more information on this paint issue.; 2018-06-18: ASAP; 2018-06-25: Close
441000983 | ASSY, HEATER TROUGH, HTCH-A |  |  | Thermal Circuit | 186015042 N2971032 700005247 | Eugene Bethany | Tom Demerle Dave Reed | Quality Material | 10-Jun-2016 update : Defect Desc : Radius out of spec resulting difficulty to move during testing. 40pcs - ETA : 10-Jun. 24 - ETA : 13-Jun. Q2 shipment recovered. 03-Jun-2016 update : Defect Desc : Radius out of spec resulting difficulty to move during testing. 133pcs - ETA 06/06. 100pcs for next week shipment. Shipment recovered by week 23. 27-May-2016 update : Defect Desc : Radius out of spec resulting difficulty to move during testing. 25pcs ETA 05/27, 50pcs ETA 05/30, 25pcs - 05/27(TBC). Delivery from Thermal Circuit should have 100pcs per week and Shipment able to recover by week 23. 20-May-2016 update : Defect Desc : Radius out of spec resulting difficulty to move during testing.Expected to have at least 80pcs shipping from Thermal Circuit. However, still pending confirmation & tracking# from Thermal Circuit. GES to continue follow up for subsequent delivery date & Qty. 13-May-2016 update : Defect Desc : Radius out of spec resulting difficulty to move during testing. 25pcs ETD 05/12, 50pcs ETD 05/13. Subsequent delivery date & Qty to be confirmed by Thermal Circuit. 06-May-2016 update : Defect Desc : Radius out of spec resulting difficulty to move during testing. 50pcs received on 29-Apr & accepted. 87pcs received. 25pcs DHL# 9282602641 ETA : 09/May. Subsequent delivery: 110u 5/9, 30u 5/20, 140u 5/27, 200u 6/2, 200u 6/10, 175u 6/21. 29-Apr-2016 update : Defect Desc : Radius out of spec resulting difficulty to move during testing. 50pcs received on 29-Apr & accepted. Subsequent delivery: 10u 5/2, 110u 5/9, 30u 5/20, 140u 5/27, 200u 6/2, 200u 6/10, 175u 6/21. 22-Apr-2016 update : Defect Desc : Radius out of spec resulting difficulty to move during testing. Current recovery date from Thermal Circuit (ETA GES) as below : 60 pcs 5/2 ,110 pcs 5/9 (we are anticipating delivery of these Thursday 4/21) 30 pcs 5/20, 140 pcs 5/27, 200 pcs 6/2, 200 pcs 6/10, 175 pcs 6/21, 125 pcs 7/20 15-Apr-2016 update : Defect Desc : Radius out of spec resulting difficulty to move during testing. Material : 50 pcs (2 boxes) ETD US 4/22. Venture is still expediting with Thermal Circuit for next delivery date & Qty. Per last update from Dave Reed. Tom Demerle Waters SQE manager is reviewing reworked metal troughs from Technimetal. There should be a disposition made today if they can be used. If troughs can be used they have to be anodized at another supplier before Thermal circuits can start assembly, probably next week. Quality : As confirmed by Thermal Circuit all inventory need to be scrapped. 08-Apr-2016 update : Defect Desc : Radius out of spec resulting difficulty to move during testing. Material : 50 pcs (2 boxes) ETD US 4/22. Venture is expediting with Thermal Circuit for next delivery date & Qty. Quality : As confirmed by Thermal Circuit all inventory need to be scrapped. 01-Apr-2016 update : Defect Desc : Radius out of spec resulting difficulty to move during testing. Material : All the inventory(FG+WIP) currently at Thermal Circuit are encountert the same failure. Next incoming will be in May with fresh build. Continue following up with Venture on the recovery plan. Current recovery schedule :- 160pcs - 05-May-2016 110pcs - 12-May-2016 169pcs - 19-May-2016 150pcs - 26-May-2016 150pcs - 02-Jun-2016 Quality : 100% rejected due to Physical part not meeting spec. | [5 empty] | Monitoring | Close
289010016 | ASSY, FLOW CELL, 2475 W/BULKHEAD |  |  | 2018-04-02: Waters; 2018-04-09: 186017006; 2018-04-16: Bethany; 2018-04-30: Quality; 2018-05-07: 27-May-2016 update : High fall out during production. 10pcsreceived, however 10pcs rejected due to cosmetic defect - poor finishing found. 20-May-2016 update : High fall out during production Machine shop shipped 10pcs ETA 23/05. Fedex# 509096446456 13-May-2016 update : High fall out during production Machine shop received the compnent , however it is put on quality hold. Machine shop is figuring out the issue and update GES. Follow up with Machine shop for update 06-May-2016 update : High fall out during production Machine shop will only receive material on 11-May(initial on 04-May) and arrange shipment to GES on the following week (Wk20). Continue expedite. 29-Apr-2016 update: High fall out during production. Waters Milford do not have any WIP quantity that can ship immediately. Will continue to expedite.; 2018-06-18: ASAP; 2018-06-25: Close
400007161 | ASSY CHASSIS 2475 FLR W/INTERLOCKING |  |  | 2018-04-02: Baiteng; 2018-04-09: 186247500; 2018-04-16: Bethany; 2018-04-30: Quality; 2018-05-07: 06-May-2016 update : Quality reject due to corrosion. 23pcs received. Next incoming 55 pcs estimated eta by 25/ May (GES to advice on the inspection result). 29-Apr-2016 update: Quality reject due to corrosion. All chassis available in Venture has been sorted - only 32u out of 100u are good to be used. Venture buyer is expediting next lot from Baiteng (original ETA date 6-Jun-16).; 2018-06-18: 2016-05-04; 2018-06-25: Close
WAT081102 | BUSHING CAM |  |  | 2018-04-02: LM TARBELL INC; 2018-04-09: 186015029 186247500 N2971015; 2018-04-16: Eugene Bethany; 2018-04-30: Quality Material; 2018-05-07: 13-May-2016 update : 100pcs receive and passed IQA inspection. Next incoming 75pcs ETD US 11/05. 06-May-2016 update : Quality issued (encountered fitting issued) Material : Current ETA 100u 1/Jun & 200u 21/Jun & 150u 27/Jun. Venture is expediting from supplier.; 2018-06-18: ASAP; 2018-06-25: Close
441001040 | ASSY, CABLE, DB25M-F, RIGHT ANGLE, 4 FT |  |  | 2018-04-02: L-COM; 2018-04-09: 186015042 186015045; 2018-04-16: Bethany; 2018-04-30: Material; 2018-05-07: 20-May-2016 update : 78pcs + 100pcs ETA GES on 20-May-2016. 100pcs ETA 27/May. GES to continue follow up for subsequent delivery with L-Com till the shortage gap is closed. 13-May-2016 update : Supplier shipment delinquent due to supplier switching to new warehouse facility, Buyer is working closely with vendor located in US. Checking with Milford to spare some Qty.; 2018-06-18: ASAP; 2018-06-25: Close
289010629 | ASSY, CHASSIS, PUMP |  |  | 2018-04-02: Baiteng; 2018-04-09: 186017000; 2018-04-16: Eugene; 2018-04-30: Quality; 2018-05-07: 27-May-2016 update : Defect : BRACKET TUBE RETAINER, BASE found with wrong orientation with Rev A Chasis. Quality : ADC 44 units ship as it. Material : Rev A - 7 chasis. Scrapped. ECO# 9206054 released on 24-May to have Rev B implement immediately. Rev B : In-house - 40pcs, 60pcs - ETA 06/06(Via Sea). 20pcs stock at Baiteng. 20-May-2016 update : Defect : BRACKET TUBE RETAINER, BASE found with wrong orientation with Rev A Chasis. Quality : ADC 44 units need to be reworked? TBA WPPL is expediting to release ECO for updated ASP to be effective immediately to allow GES to use Rev B. Material : Rev A - 7 chasis. Venture is exploring rework possibility. Rev B : In-house - 13pcs, 7pcs - ETA 05/20, 80pcs - ETA 06/03(Via Sea) ECO# 9206054; 2018-06-18: ASAP; 2018-06-25: Close
289005264 | ASSY, SAMPLE TRAY, 2 DRAWER, MAGNETIC |  |  | JPI | 186015017 186015046 N2971031 | Eugene | Tom Demerle Paul Pavone | Quality | 17-Jun-2016 update : Defect : Hole diameter over size TMD010161 has released to Venture to use up the non-conforming part of 300pcs at GES Venture. JPI has replaced the Pin and its hould be able to control the dimension in the future. ECO# 9205530 was released to correct the orientation of the engraving. (Eff : 03-Aug) 10-Jun-2016 update : Defect : Hole diameter over size Based on update from JPI dated 08-Jun, the pins have been repaired and JPI is working to put the tool back together. JPI is able to resume production to build for remaining inventory needs. 03-Jun-2016 update : Defect : Hole diameter over size - Current stock at GES is being on-hold and pending for TMD from Waters to UAI. Will impact wk 25 shipment if TMD is not able to release to GES within this 2 weeks. - Quality : Patrick Devlin is drafting TMD - ECO# 9205530 was released to correct the orientation of the engraving. (Eff : 03-Aug) | [5 empty] | ASAP | Close
415001736 | EXTENSION THERMISTOR A.S. NON-LINEAR |  |  | 2018-04-02: FUYU; 2018-04-09: 186015017 186015046 N2971031; 2018-04-16: Eugene; 2018-04-30: Quality; 2018-05-07: 17-Jun-2016 update : Parts reworked at GES and GES acknowledged accepted. 10-Jun-2016 update : Defect : the profile of a surface is jagged. Fu Yu will be running new production lot on 10-Jun, and will send out the first delivery next Monday. Current inventory at GES all purged out.; 2018-06-18: ASAP; 2018-06-25: Close
441001042 | ASSY, PCB W/CABLE, THETA ENCODER |  |  | 2018-04-02: Atronix; 2018-04-09: 186015017 186015046; 2018-04-16: Edwin; 2018-04-30: Material; 2018-05-07: 30-Sep-2016 update : - Q3 FTN & I-FTN production is being recovered. Fresh build and rework activity are completed. 23-Sep-2016 update : Venture current output for fresh build is around 18 units per day. Continue to monitor to ensure shipment on track. 16-Sep-2016 update : Venture current output for fresh build is around 18 units per day. Need to closely monitor to make sure the schedule don't slip. 02-Sep-2016 update: Material supply is ahead of production requirement by around 2 weeks. Need minimum 150 pieces to close Q3 (including balance 130 rework units). Venture current output for fresh build is around 18 units per day. Need to closely monitor to make sure the schedule don't slip. 26-Aug-2016 update : Another 159 pieces of 441001042 shipped, with ETA 29-Aug-16. This is sufficient to cover production need until 11-Sep-16. Current test output is having backlog of around 50 units. Venture will need to catch up production and testing during weekend for recovery. 19-Aug-2016 update : Cable supply is catching up and usually one week ahead of the production need. Venture is having slight backlog on test output, will continue to monitor if Venture can recover by 22-Aug-16 12-Aug-2016 update : Another new lot of 162pcs ETA 15/Aug. YTD 5017 received 129u, 5046 46u, PKI N2971031 13u return from GES. To continue monitor. 05-Aug-2016 update : Total 189pcs 441001042 received. Production recovery in progress. To-date 50u 5017 & 14u 5046 delivered. Next lot of 441001042 ETD 05-Aug. 29-July-2016 update : First shipment of 69 pieces 441001042 ETA Venture latest on 1-Aug-16 morning. Followed by another 120 pieces ETD Atronix NH on 29-Jul-16. Venture will start stripping down of instruments on 29-Jul-16, to get ready for rework once received 441001042. 126 units of ADC stock is scheduled to return to Venture on 29-Jul-16. Total Q3 quantity will be 1080 units (504 for rework + 576 fresh build). 22-July-2016 update : Defect : Part# 441001042 was observed to exhibit corrosion. - It is determined that all affected units must be reworked in Venture. Rework Procedure is being developed, and will raise TMD once rework procedure is finalized. Targeted to receive TMD by 26-Jul-16. New lot of 441001042 with Parylene coating ETD Atronix on 29-Jul-16. Quantity TBA. - Demand / Supply Planning group need to finalize allocation to build before Venture receive the new lot, to make sure that we are building / reworking units based on priority. 15-July-2016 update : Defect : Part# 441001042 was observed to exhibit corrosion. FTN & I-FTN production stop build and stop ship due to 441001042(ATRONIX), does not contain appropriate Parylene coating that leads to pcb corrosion. It was discovered that the supplier, Atronix, had changed manufacturing sites from Bellrica, MA to Mexico, changed the coating supplier and the coating type, in which Waters was not informed of these changes.; 2018-06-18: ASAP; 2018-06-25: Close
289003687 | ASSY DOOR DETECTOR FLR |  |  | 2018-04-02: Oneida; 2018-04-09: 186015029; 2018-04-16: Bethany; 2018-04-30: Material; 2018-05-07: 02-Sep-2016 update : Non-conformance parts accepted and released to support production. Closed. 26-Aug-2016 update : Understand that Gloss Specification is never a pass/fail criteria for CM and gloss spec is for color batch approval only. Eugene will advise advise on the final disposition for the non-conformance parts. 65 pcs non-conformance - Oneida 19pcs non-conformance - Waters Milford 19-Aug-2016 update : Defect description: Child part (400001778) Dark Blue Gloss Out of spec. out of 70pcs, 51pcs accepted and 19pcs rejected. Next shipment from Oneida ETA on 12.09.2016 Qty 80u(ETD 06-sep), Venture is working with Oneida for few days improvement and partial Qty to close Q3 shortage. 12-Aug-2016 update : Defect description: Child part (400001778) Dark Blue Gloss Out of spec. 70pcs from Milford ETA 15/Aug. Next shipment from Oneida ETA on 13.09.2016 Qty 80u. 05-Aug-2016 update : Defect description: Child part (400001778) Dark Blue Gloss Out of spec, Spec (5 to 9). Actual 4.1 to 4.4. Next shipment from Oneida ETA on 13.09.2016 Qty 80u. Milford has excess qty 70pcs to support.; 2018-06-18: Monitoring; 2018-06-25: Close
279002708 (New HC 279003580) | ASSY, ENGINE, H/C, SAMPLE MANAGER ASSY, ENGINE, H/C, INTERMEDIATE, CPSM |  |  | 2018-04-02: Laird Tech; 2018-04-09: 186015017 186015046 N2971031; 2018-04-16: Bethany; 2018-04-30: Material; 2018-05-07: 30-Sep-2016 update : ECO 9208661 with effective 09-Jan-2017, shall review again on the effectivity date and if rework is required after Q4 production plan is released. - ECO 9208252 with immediate effectivity date to support field service rework. 23-Sep-2016 update : Impact sheet submitted for both ECR 9208252 & ECR 9208661 and new heater cooler (279003580) estimated to be phase-in in Jan 2017. in order to sustain entire Q4 demand, QOH 422 + QOO 500pcs to be remained at old HC 279002708. There is no rework Qty and cost involve. Shall review again the demand and declare Qty subject to change. 09-Sep-2016 update : ECR 9208252 & ECR 9208661 to rework heater cooler to fix fan restart issues. - To rework 279002708 to 279003580 (ECR 9208661) - CMTi managed to expedite the cable Assy with ETA 05-Oct-2016 - Laird Tech to use their own local source for Fan Assy - Laird Tech to advise how soon they can produce new heater cooler 279003580. - Raw material to be returned to Laird Tech China for reworking. Qty and schedule TBA. 26-Aug-2016 update : ECR 8208252 & ECR 9208661 to rework heater cooler to fix fan restart issues. - To rework 279002708 to 279003580 (ECR 9208661) - LT 14weeks for 2 new parts - Part# 441001827 (cable assy) & 279003348(Fan assy) both under expediting. - Getting Laird Tech to advise how soon they can produce new heater cooler 279003580. - Raw material to be returned to Laird Tech China for reworking. Qty and schedule TBA.; 2018-06-18: ASAP; 2018-06-25: Close
279002056 | POWER SUPPLY CM-A |  |  | 2018-04-02: SL Power; 2018-04-09: 186015043 186015049; 2018-04-16: Eugene Bethany; 2018-04-30: Quality Material; 2018-05-07: 16-Sep-2016 update : Excess Hole on the PSU Chassis 279002056. TMD 010220 approved and released to Venture. Production resume. ECR9210514 will be submitted to revise the Waters 279002056 drawing to show the location of the added hole. 09-Sep-2016 update : Excess Hole on the PSU Chassis 279002056. - As confirmed by Rob Zanardelli, after the investigation by the engineering team, this extra hole poses very low risk and is acceptable by Waters. - TMD to be generated by Rob Zanardelli to use up the non-conformance part. - There will be an upcoming ECR initiate to show the location of the newly added extra hole. - the reason for SL Power to have this extra hole was only for SL Power final test station to improve the accuracy of the final voltage setting.; 2018-06-18: Monitoring; 2018-06-25: Close
410001746 | SPRING, COMP, .360 X 0.50L X .047 |  |  | 2018-04-02: Lee Spring; 2018-04-09: 186015017 186015046; 2018-04-16: Eugene Bethany; 2018-04-30: Quality Material; 2018-05-07: 16-Sep-2016 update : Fitting problem due to dimension out Replacement of 741pcs received and inspection done. Part are within spec. Production resume. 09-Sep-2016 update : Fitting problem due to dimension out - after sorting, out of 842pcs stock, only 203pcs is sgood part and 741pcs rejected from store & production. Venture is working with supplier for replacement.; 2018-06-18: ASAP; 2018-06-25: Close
NA | NA |  |  | 2018-04-02: NA; 2018-04-09: 186015017; 2018-04-16: Desmond Wesley; 2018-04-30: Tester; 2018-05-07: 21-Oct-2016 update : i) Tester preventive maintenance (PM) is completed on 17-Oct. ii) Communication error due to tester-BSM's CPU2000 w/etthernet pcba board. It was replaced (18-Oct) and TE83064-15 is running normally after monitoring. 14-Oct-2016 update : 1 Tester stack communication error. 2 tester preventive maintenance (PM) in progress. Desmond/Wesley are following up on this with Venture (Hong Cheng).; 2018-06-18: ASAP; 2018-06-25: Close
430002472 | ASSY, TUBE, HEAD TO XDUCER, MP35N |  |  | 2018-04-02: Waters; 2018-04-09: 186015000; 2018-04-16: Bethany; 2018-04-30: Material; 2018-05-07: 28-Oct-2016 update : All QOH + incoming 150pcs can be used. Production resume as usual. 21-Oct-2016 update : Fail Function(Dynamic leakage) due to Ferrule uneven Surface. Venture QOH 121pcs need to go through test and Venturewill update with the test result. Following up next delivery schedule with Joanne Levine and also the root cause causing uneven surface for this Tube assy as she mentioned production is putting On-hold right now. 14-Oct-2016 update : Fail Function due to uneven Surface. Milford has stock and checking with JL to arrange shipment immediately.; 2018-06-18: ASAP; 2018-06-25: Close
289010016 | ASSY, FLOW CELL, 2475 W/BULKHEAD |  |  | 2018-04-02: Waters; 2018-04-09: 186017006; 2018-04-16: Bethany; 2018-04-30: Material; 2018-05-07: 21-Oct-2016 update : 4pcs received and will perform test on the Flow cell. venture to update with the test result. Shipment should be on schedule if testing not fail. 14-Oct-2016 update : Flow cell test failed. Best ETD committed by JL is on 02-Nov-2016. Expediting with JL for better delivery date.; 2018-06-18: ASAP; 2018-06-25: Close
405005441 | Stator Valve |  |  | Waters | 186015017 186015046 | Eugene | Monica | Quality | 4-Nov-16 update: Total 44 pieces 405005441 from date code of 21-Sep will be rejected to Milford. 28-Oct-2016 update: Waters Milford has alerted that there is a potential quality seal failure issue within the 2 lots that were shipped in Sept (125 pieces shipped 21-Sep & 50 pieces shipped 27-Sep). However, the failure can be detected at sub-assy and final test, thus Venture may continue to ship out instruments as soon as the units pass final test. At the same time, Venture has also highlighted that they encounter higher failure at both sub assy and final test (failing pressure decay test) comparing to historical trend, and the rejected parts pointed down to 405005441 with MFG date code of 21-Sep. Venture will continue to monitor output and will purge out bad parts from date code of 21-Sep. So far, there is no report of line down situation resulting from this part. | [5 empty] | NA | Close
| Datum Base Sub Assy - Washer assembled with wrong orientation |  |  | Waters | 186015017 186015046 N2971031 | Eugene | Randy | Quality | 4-Nov-16 update. It is highlighted by Milford on 28-Oct-16 that they encountered units with washer assembled with wrong orientation. Venture validate their in-house units and observed the same issue. Venture reworked all in-house units (both sub-assembly and instrument), before resume shipment to ADC. | [5 empty] | ASAP | Close
441000296 | ASSY, CABLE, INTERNAL RS-232 |  |  | 2018-04-02: Atronix; 2018-04-09: 186015000; 2018-04-16: Bethany; 2018-04-30: Material; 2018-05-07: 27-Nov-2016 update : Issue resolved. 18-Nov-2016 update : Supplier delinquent shipment from ETA 18/Nov to ETD 05/Dec.; 2018-06-18: ASAP; 2018-06-25: Close
289006521 | PLATE WITH SHAFT, THETA DRIVE |  |  | 2018-04-02: Machine shop; 2018-04-09: 186015017 186015046 N2971031 700009452; 2018-04-16: Bethany Eugene; 2018-04-30: Material Quality; 2018-05-07: 02-Dec-2016 update : Part# 289006521 - 360pcs - 509097027857/868/879 ETA : 12-Dec-2016. 27-Nov-2016 update : Venture has received 100 pieces on 24-Nov-16. Sorted 60 pieces, only 1 piece reject. Another 89 pieces ETA 28-Nov-16. To monitor on yield. 18-Nov-2016 update : No impact to production as of this week. Venture feedback Fitting issue for 289006521 and they had measured both this part and its mating part and so far both are within specs. Pending Venture to advise the root cause of why the shaft cannot go thru the bearing of its mating part. Eugene has requested for 20 measurement results for both mate parts. Pending Venture to provide.; 2018-06-18: ASAP; 2018-06-25: Close
405005441 | STATOR, VALVE, SYRINGE, HPLC FITTING |  |  | 2018-04-02: Machine shop; 2018-04-09: 186015017 186015046 N2971031; 2018-04-16: Bethany; 2018-04-30: Material; 2018-05-07: 09-Dec-2016 update : Machine shop shipped 185pcs with ETA 09-Dec-2016. 24pcs - 13-Dec-2016 170pcs - 20-Dec-2016 100pcs - 29-Dec-2016 02-Dec-2016 update : Machine shop shipped 78pcs on 02-Dec-2016. Fedex# 509097009300 to ETA 05-Dec-2016. To continue follow up for subsequent shipment. 27-Nov-2016 update : Waters Milford has delayed the shipment to Venture, mentioning that they are having materials issue without giving further details. Need to check with Milford on recovery date. Immediate impact on shipment due 30-Nov-16.; 2018-06-18: ASAP; 2018-06-25: Close
205001632 289010016 | ASSY, FLOW CELL HOLDER REFRESH, 10PK |  |  | 2018-04-02: Machine shop; 2018-04-09: 186247500 186017006; 2018-04-16: Desmond Wesley; 2018-04-30: Quality; 2018-05-07: 23-Dec-2016 update : with new golden flow cell received, current yield is above 90%. Production resume. 15-Dec-2016 update : First pass 50%, Venture is still manage to mix and match to complete the build. To Continue monitor. 09-Dec-2016 update : Current flowcell FPY is at 48.74%. Based on current flowcell inventory is sufficient to support for Q4 production.; 2018-06-18: ASAP; 2018-06-25: Close
NA | NA |  |  | 2018-04-02: NA; 2018-04-09: 186015045; 2018-04-16: Wesley Desmond; 2018-04-23: NA; 2018-04-30: Tester; 2018-05-07: 10-Feb-2017 update : no issue to meet increased of 15units per quarter. 6-Feb-17 update: Production Meeting discussion - attach rate probably at 387 units per year. Operations team to work with Venture to simulate at a realistic volume (additional 50 units per quarter against current demand). 20-Jan-2017 update : Wesley and Desmond to advise on the Production and Tester capacity for Insturment 186015045 if were to support at 300 units per quarter.; 2018-06-25: Close
NA | NA |  |  | NA | NA | Wesley | NA | Tester | 24-Feb-2017 update : Root cause is inconclusive and Milford tasked Venture to update master database by performing dummy print for database synchronization. Please close this. 3-Feb-17 update : Missing running SN is due to migrating of server. Still under investigation on who cause this issue, and actual root cause. 20-Jan-2017 update : Missing running serial number for I-BSM & Arc QSM. Please advise | [5 empty] | NA | Close
210000345 | ASSY, PCB, QSM PUMP ROHS |  |  | CEI | 186017000 | Yin Ying | Judy Tusino | Material | 24-Feb-2017 update : 25 PCBA support from Flex has been received. Based on currently delivery from CEI. No impact to production. 48pcs 28/2, 36pcs 14/3, 156pcs 25/4 17-Feb-2017 update : 48pcs ETA 28-Feb, 36pcs 14-Mar, 156pcs ETA 25-Apr 8unit impacting on 20-Feb production. There is a shortage of connector# 323000584. CEI is continue expedite and will update the delivery date 3-Feb-17 update: Perform allocation between Milford and Venture. Total short 121 pcs for Q1 2017 (36 pcs ETD 7-Feb-17, 48 pcs ETD 28-Feb-17, 48 pcs ETD 14-Mar-17). To continue expedite. | [5 empty] | 2017-02-21 | Close
441001080 | ASSY HEATER TROUGH HTCH-30 |  |  | 2018-04-02: Thermal Circuit; 2018-04-09: 186015045; 2018-04-16: Bethany; 2018-04-30: Material; 2018-05-07: 03-Mar-2017 update : Thermal Circuit total shipped 97pcs with ETA 02-Mar. No impact to Q1 production. 24-Feb-2017 update : Thermal Circuit will be shipping 20pcs on 1 March. TC will provide another update on 24-Feb (US time). 17-Feb-2017 update : Demand increased for 5045 modal from Q4'16(70u) to Q1'17 95u. Current delivery schedule from TC : 100pcs ETA 29/Mar, 100pcs ETA 02/May. Understand TC does not have any material issue to support. the major concern is TC needs longer LT to manufacture the material (4 weeks). Continue expedite with TC for better delivery date.; 2018-06-18: ASAP; 2018-06-25: Close
405009623 405014527 | BUSHING FLANGE .302 I.D. CLAMP BEARING NUT |  |  | 2018-04-02: ACHB; 2018-04-09: 186015017 186015046 N2971031 700005225; 2018-04-16: Eugene; 2018-04-30: Quality; 2018-05-07: 03-Mar-2017 update : TMD010296 issued to allow to use the exisiting non-conformance part. Upon approval of this TMD production can begin building and shipping product with the above mentioned material non-conformance.; 2018-06-18: ASAP; 2018-06-25: Close
289010698 | ASSY BARBED SEAL WASH HOUSING VELOX |  |  | 2018-04-02: ACHB; 2018-04-09: 186017000; 2018-04-16: Yin Ying; 2018-04-30: Material; 2018-05-07: 10-Mar-2017 update : After further investigation, ACHB child part is only required for Type II passivation per Waters spec and assembly part will send to Richport for critical clean process prior to release shipment to CM. Based on the COC document submitted by ACHB, their local supplier is paasivate per Waters spec, Type II and found no issue to release the existing material to continue production. 03-Mar-2017 update: Shipment affected from week 11 onwards. ACHB did not passivate per Waters spec. WPPL is clarifying if ACHB local passivation supplier able to comply to Waters spec. TBA; 2018-06-18: ASAP; 2018-06-25: Close
415002903 279003532 | BEZEL, DETECTOR, 2475, ALTUS A-10 ASSY, DETECTOR, FLR., HPLC, ALTUS, A-10 |  |  | Fu Yu Venture | N2971015 | Yin Ying | Nic Swajza Matt Franklin | Material | 07-Apr-2017 update : TMD010303 (expiry date:20-Jun-2017) already released to Venture to resume production. Will follow up to release ECR 9214017. 31-Mar-2017 update : Venture has highlighted that they received new revision of 415002903, but the drawing has not been updated yet, and BOM/ASP of 279003532 is not updated to reflect the additional materials. Checked with Nic on the progress for ECR9214017, and there is a delay in completing the ECO on time. Matt has routed TMD010303 for review, and has given Matt a due date on 31-Mar-17 for TMD issuance, in order to resume production on time for 5-Apr-17 shipment. | [5 empty] | Monitoring | Close
279001958 | ASSY HEATER ELEMENT |  |  | 2018-04-02: THERMAL CIRCUITS INC; 2018-04-09: 186015017 186015046; 2018-04-30: Quality; 2018-05-07: 02 June 2017 update : Venture receive 250pcs, this part is no longer critical. 26-May-2017 update :Thermal circuit have quality issue. This part might affect FTN shipments from 21/Jun onwards. Quality arose and Thermal Circuit still have some corrective actions to be taken off.; 2018-06-18: Monitoring; 2018-06-25: Close
289006107 | ASSY COVER HEATER COLUMN DUAL CM (JPI) |  |  | MRPC (JPI) | 186015038 186015043 186015049 700005439 | Edwin/ Erwin | Paul Ebai | Quality | 26-May-2017 update : Scrap the parts under WPPL to close this case since this material was exposure prior to re-texturing the tool 19- May- 2017 update : The 124 pcs in question has been reviewed by Eugene and Erwin from Waters QA previously and found to be unacceptable. Do not think it any value to revisit this disposition. If Paul and MRPC like to look into it, can arrange for those to be sent back. On financial side, I would recommend a decision to scrap the parts under WPPL to close this case so that we can focus on acceptance moving forward. 28-Apr-2017 update : Need to establish cosmetic criteria for molded parts, MRPC propose to base on SPI guidelines. Edwin to follow up with MRPC for details while Erwin to follow up with Milford SQE on acceptance criteria. 21-Apr-2017 update: no impact to production. Next shipment from MRPC, 160pcs will ETD 28-Apr & ETA GES 05-May. Summary of Discussions and Action Items, please refer to attached file for details 13-Apr-2017 update: Edwin will be in Milford (week of 10-14 Apr 2017) for discussion with Jason Dion and Paul Ebai on this part. One sample has been sent over to Milford by GES for Edwin to discuss with Milford. Action owner: Edwin Delivery status from MRPC:- Venture continue follow up MRPC for subsequent delivery. 40pcs ETA 13-Apr 120pcs ETA 17-Apr 07-Apr-2017 update : Edwin will be in Milford (week of 10-14 Apr 2017) for discussion with Jason Dion and Paul Ebai on this part. One sample has been sent over to Milford by GES for Edwin to discuss with Milford. Action owner: Edwin Delivery status from MRPC:- 80pcs ETA 10-Apr 40pcs ETA 13-Apr 120pcs ETA 17-Apr 31-Mar-2017 update : After Milford team visit to MRPC, this is the summary of the review: 594 molded parts after the tool was re-textured will be disposition of "Use As Is". 80 pc of 594 pc shipped to Venture and the balance of 514 pc are acceptable as is. MRPC will perform a thermal study on the tool during the next production run to determine the temperature profile on the cavity surface near all ejector pins reach the required temperatures recommended for the material requirements. If the thermal study is acceptable, then MRPC is suggesting that Waters consider a very light vapor hone finish to slightly lower the gloss of the part that may minimize the ghosting/shadowing effect in viewing the part in the vertical position. 24-Mar-2017 update : No Impact to Q1 shipment. Parts reviewed by Paul on 22 March and on the same day, MRPC shipped initial partial shipment with slight ghosting. 40pcs passed (out of 80pcs) and released to production. Remaining 40pcs Venture require Eugene to verify whether it can be used. Eugene follow up with Paul on the closure of the SCAR. Venture Quality to monitor the subsequent lot 2-3, Venture purchasing to follow up with MRPC for subsequent delivery date and Qty. 17-Mar-2017 update : MRPC is still on track per original schedule. 17th Mar will send the part to Paul Ebai to review and will run partial on 22-Mar-2017. Eugene will sort the 163pcs "rejected" parts from Venture to confirm the "rejected" parts can or cannot be used and will updatet the result on 22-Mar-2017. 10-Mar-2017 update : WPPL/Venture has done sorting for Venture inventory. 24pcs accepted out of 199pcs. Instructed Venture to prioritize for 5049 instrument. Continue expedite with MRPC for progress and expedite shipment with good material. 1. Cavity Block is sent out to the tool maker for re-texturing- Monday, March 6. 2. Cavity Block will return to MRPC NE- Friday, March 10 3. Cavity Block inspection and assembly into tool. This includes cleaning, adding vents for Gas, adjusting KO pins , March 16 4. Start to run parts- March 16 5. Start assembling of parts- March 20 6. Start making partial shipments- March 22 03-Mar-2017 update : Immediate impact to production. QOH at Venture (200pcs) all found with white silver marking on the cover plate. No visibility for the recovery plan as of now and how soon the porduction can be recovered. Quality issue due to cosmetic reject - blush mark. This has been highlighted by Waters in December 2016. Currently supplier has hold back the inventory for shipment as all parts are found in bad condition including inventory at Venture. MRPC is working internally on process improvement on tooling/fixture to ensure no white silver marking on the cover plate. | [5 empty] | Monitoring | Close
400002078 | R COVER FLD ACQUITY |  |  | 2018-04-02: Trend; 2018-04-09: 186015029; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Quality; 2018-05-07: 30 June 2017 update: 22pcs ETA 30/Jun & 12pcs ETA 7/Jul. No impact to July production, continue to follow up with Venture for subsequent delivery for entire Q2. 23 June 2017 update : Impacting shipment on 5/Jul. ETD & Qty pending Prod advise. cosmetic Issue (Jigging Point/Dent). Pending subsequent delivery confirmation; 2018-06-18: Monitoring; 2018-06-25: Close
210000460 | ASSY PCB TCM REV C |  |  | 2018-04-02: Venture; 2018-04-09: 186002441; 2018-04-30: Tester; 2018-05-07: 16 June 2017 update : Tester is down which will affect the TCM model. Will be short of 2 units for 28 June shipment. Waitng for Waters to send in the part needed to fix the tester.; 2018-06-25: Close
400003882 | COVER INTEGRAL PCB HTCH-A |  |  | 2018-04-02: Trend; 2018-04-09: 186015042; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Quality; 2018-05-07: 30 June 2017 update : 60pcs ETA 5/Jul. No impact to July production, continue to follow up with Venture for subsequent delivery for entire Q2. 23 June 2017 update : Cosmetic issue (Dented). Impacting shipment on 19/Jul. Next delivery date to be confirmed by Trend. 16 June 2017 update : TREND has done the sorting for all invty (W1400003882-COVER INTEGRAL PCB HTCH-A)\ on 15 June and turned out all rejected. Thus, shipment for Column Heater (W1186015042-R) on 21/Jun will be affected. There’s another lot that is due for delivery to GES on 16/Jun, but TREND will still need to check and re-screen to see if the lot has the same condition.; 2018-06-18: Monitoring; 2018-06-25: Close
289003547 | ASSY FILTER IN-LINE SS FRIT |  |  | 2018-04-02: Waters; 2018-04-09: 186015000; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 18 Aug 17 update: 15u ETD 06-Sep, 1u ETD TBA; WATERS Milford stop shipment & rescreen their parts to ensure part is meeting part's specifications. WATERS Milford target to ship out by 18/Aug. Venture to follow up with Joanne Levine.; 2018-06-18: Monitoring; 2018-06-25: Close
279001951 | XDUCER PRESSURE FLEX CABLE 20K PSI |  |  | 2018-04-02: DJ Instruments; 2018-04-09: 186015000; 2018-04-16: Wan Jing; 2018-04-30: Quality; 2018-05-07: 11 Aug 17 update: No impact to production. Defect: Difference Plating covered. TMD010372 received on 11Aug 2017 TMD expiry date: 08 Feb 2018. Affected PN: 279002494, 279001380 (Milford), 279001951 (Venture) & 27900881 (Flex).; 2018-06-18: Monitoring; 2018-06-25: Close
279002268 | POWER SUPPLY 270 WATT INC INRUSH LIMIT |  |  | 2018-04-02: SL Power; 2018-04-09: 186017000; 2018-04-16: Wan Jing; 2018-04-30: Quality; 2018-05-07: 18 Aug 17 update: Sorting done, 4 rejected out of 100pcs. No impact to open orders. 11 Aug 17 update: Impact Arc QSM 23 Aug 3u & onward shipment to WPPL. There are 103pcs pending at incoming (IQ10 location) which has 3pcs rejected with same issue & balance. 100pcs pending for sorting, sorting activity will not begin until decision is made between Venture and supplier. Defect:- Cosmetic Issues, scratches on PSU Flange.; 2018-06-18: ASAP; 2018-06-25: Close
NA | Firmware upgrade |  |  | 2018-04-02: Flex; 2018-04-09: 186015029 186015043 186017000; 2018-04-30: Tester; 2018-05-07: 11 Aug 17 update: New Firmware approved and shipment released. 04 Aug 17 update: Firmware upgrade issue. Venture is allowed to build and test the instruments affected, but not allow to ship until given green light by Waters upon IQ activity is completed and approved.; 2018-06-18: ASAP; 2018-06-25: Close
405005879 | HOUSING, EM OPTICS BENCH, MACHINING |  |  | 2018-04-02: B&E; 2018-04-09: 186015029; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 11 Aug 17 update: B&E managed to improve to ship 24pcs ETD on 15 Aug 17. Venture to continue to closely monitor shipment from B&E 04 Aug 17 update : Replacement 3u Target ETD 8'Aug and will on hold. Original 3u put on hold for shipment is using alternate vendor (China Synergy) raw cast material. Can only release the instruments for shipment upon FA approval of the new vendor material. (new firmware to be immediately implemented to use thus potential impact affecting the shipment on 8 Aug 2017 and onwards); 2018-06-18: ASAP; 2018-06-25: Close
405003380 | ACQUITY UPLC SAMPLE MANAGER FTN |  |  | 2018-04-02: DESIGNATRONICS; 2018-04-09: 186015017; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 31 Aug 17 update : 28 units ETD 13/Sep 7 units ETD 15/Sep Delayed shipment due to shortage of raw material. Vendor will ship on 6/Sep and ETA GES on 11/Sep from USA.; 2018-06-18: Monitoring; 2018-06-25: Close
NA | Firmware |  |  | 2018-04-02: Venture; 2018-04-09: 186001500; 2018-04-16: Desmond; 2018-04-30: Tester; 2018-05-07: 24 Nov 17 update: Tester down due to firmware problem. Pending Milford's reply, Desmond to follow up.; 2018-06-18: Monitoring; 2018-06-25: Close
279000495 | ACQUITY UPLC I-CLASS BSM |  |  | 2018-04-02: XP Power; 2018-04-09: 186015000; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 29 Dec 17 update: 10 Jan shipment slip to 17 Jan; 2018-06-18: Monitoring; 2018-06-25: Open
400000938 | BRACKET ENGINE MOUNTING |  |  | 2018-04-02: MCE; 2018-04-09: 186179100; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 12 Jan 18 update : Managed to improve the delivery from 06 Feb to 23 Jan. No impact to production 05 Jan 18 update: Materials ETA 06 Feb. To continue to expedite.; 2018-06-18: Monitoring; 2018-06-25: Close
289001511 | ASSY MINIRAIL |  |  | NSK | 186015017 186015046 700005201 | Bethany | John Gannon | Material | 09 Feb 18 update : NSK has shipped 300pcs. 02 Feb 18 update : Demand increased. Shipment delay due to NSK capacity constraint unable to further pull-in any order. NSK further push out to ship on 05-Feb. Potentil impact last week of Feb shipment. Venture continue expedite with supplier. 26-Jan-18 update: NSK committed to drop ship from Japan on 31-Jan-2018. Venture is closely follow up with NSK. 19 Jan 18 update : Demand increased. Shipment delay due to capacity constraint unable to further pull-in any order. Venture is closely following up with NSK for delivery to ensure no delinquent. 05 Jan 18 update: Delay due to NSK delinquent delivery. Venture to continue to follow up. | [5 empty] | Monitoring | Close
4 instruments 3 spares | Final test station |  |  | 2018-04-02: NA; 2018-04-09: 186015029 186002475 186247500 186017006 700002035 700003707 700009344; 2018-04-16: Edwin Desmond; 2018-04-30: Tester; 2018-05-07: 25 Feb 18 update : Issue at final test resolved. However, the FLR detectors family output is still affected due to other issue at optic bench energy level. 09 Feb 18 update : Backlog shipment clear, partial shipment backlog for week 06. recovery in progress. 02 Feb 18 update : Backlog shipment clear, partial shipment backlog for week 05. recovery in progress. 19 Jan 18 update : Edwin put on hold previously due to inconsistent results from the testers, right now only testing using 1 tester and additional steps and data collection required from Venture. So the test cycle will be longer, output will be less, they are still working on resolving the tester issue. 05 Jan 18 update: Tester intermittent functional test fail. Both Final test station under Evaluation tests, to find out the root cause of the issue. 29 Dec 17 update: Ongoing investigation. 22 Dec 17 update: Potential impact from 27 Dec shipment onwards. Ongoing investigation.; 2018-06-18: ASAP; 2018-06-25: Close
210000422 | ASSY PCB VISTA PUMP ROHS |  |  | 2018-04-02: CEI; 2018-04-09: 186015000; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 15 Dec 17 update : 96pcs received, 32pcs ETA 15 Dec and 72pcs ETA 19 Dec. Sufficient material to close for Q4 shipment. 08 Dec 17 update: Upside BSM 186015000, short of 76 pcs to close the quarter. Current commited delivery date 22 Dec 17. CEI will have final confirmation whether able to deliver to Venture on 15 Dec 17 (Friday).; 2018-06-18: Monitoring; 2018-06-25: Close
NA | Server down |  |  | 2018-04-02: Venture; 2018-04-09: 186015000 186015043 186015029 186247500 186015011 186179100 186017009 186017014 186017015 186186301 186015010 186015042 186015017 186015046; 2018-05-07: 08 Dec 17 update: Venture server down. Work around solution was given to Venture to continue to print the instrument S/N label and certificate of functional performance. Production and shipment resume on 08 Dec.; 2018-06-18: Monitoring; 2018-06-25: Close
405010357 | PULLEY TIMING .08 P X 42 G FAIRLOC |  |  | DESIGNATRONICS | 186015017 186015046 | Bethany/ Jie Hui | John Gannon | Material | 01 Dec 17 update: Shipment received, incoming inspection. 24 Nov 17 update: Supplier delinquent shipment, initial plan to ship on 22 Nov. Venture to continue expedite. 17 Nov 17 update: Shipment delayed ETA to 20 Nov, 4 units of FTN slip from 22 Nov to 24 Nov. Venture to expedite. | [5 empty] | Monitoring | Close
400002298 | ACQUITY UPLC CH-A |  |  | 2018-04-02: Baiteng; 2018-04-09: 186015042 186015010 186015007; 2018-04-16: Wan Jing; 2018-04-30: Quality; 2018-05-07: 10 Nov 17 update: GES rejected the new lot received (464pcs) due to different color. 1st lot received from Baiteng is different from FA sample Actual lot rec'd: dark surface Affected shipment: 06/Dec onwards; 2018-06-18: Monitoring; 2018-06-25: Close
441000983 | ACQUITY UPLC CH-A |  |  | Thermal Circuit | 186015042 | Bethany/ Jie Hui | Dave Reed | Material | 29 Dec 17 update: 50pcs ETA on 02 Jan 1/02 25 pieces, 1/04 50 pieces, 1/08 25 pieces,1/09 25 pieces, 1/10 50 pieces, 1/11 25 pieces, 1/15 25 pieces, 1/15 50 pieces 15 Dec 17 update : 16/Dec-50pcs; 18/Dec-88pcs; 28/Dec-100pcs; 5/Jan-200pcs. Sufficient material to close for Q4 shipment. 08 Dec 17 update: 441000983 - 25pcs ETA 09-Dec 25pcs -ETD 08-Dec -- Venture to follow up tracking# Next delivery and Qty TBA 01 Dec 17 update: Current update from Thermal Circuuit is ETD 08 Dec, qty TBA. Woking with Thermal Circuit with partial quantity to be ship on 05 Dec. 24 Nov 17 update: Thermal Circuits plans to ship on or before 08 Dec quantity to be confirm. Will update more details next week. 17 Nov 17 update: Second source for a raw material had just qualified. Venture is working closely with supplier for recovery. 10 Nov 17 update: Vendor and Waters are currently qualifying a second source for a raw material. Alternate source they are qualifiying is Tucker Engineering. Primary supplier did not deliver as scheduled. There will be part shipping on 15 Nov, quantity to be confirmed on Monday. | [5 empty] | Monitoring | Close
210000389 | ACQUITY UPLC Column Mgr-Right Inlet |  |  | 2018-04-02: CEI; 2018-04-09: 186015007; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 17 Nov 17 update: CEI able to improve ETA on 08 Dec, 20 pcs. Kevin agreed to push out 7 units to week 50 10 Nov 17 update: Loaded PO to MILFORD 5pcs only & ETD 10/Nov. CEI still short of 1 RES 344000504 to complete the build. Currenlty CEI is buying from distributor and under expediting mode.; 2018-06-18: Monitoring; 2018-06-25: Close
401000607 425001201 | ASSY TCM II ACQUITY UPLC Column Heater HT |  |  | 2018-04-02: Foamtec; 2018-04-09: 186002441 186015010; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 10 Nov 17 update: Venture is using FA sample to be built in instrument by using current open PO. Due to incomplete documents and caused FA cannot be buy off on time and failed the delivery. Kevin will mark OTD failed to Venture for this shipment.; 2018-06-18: Monitoring; 2018-06-25: Close
405010357 | ACQUITY UPLC SAMPLE MANAGER FTN |  |  | 2018-04-02: DESIGNATRONICS; 2018-04-09: 186015017; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 10 Nov 17 update: Delayed ETA to 20/Nov.; 2018-06-18: Monitoring; 2018-06-25: Close
410002737 | PULLEY GT2 TIMING BELT 16 GR |  |  | 2018-04-02: DESIGNATRONICS; 2018-04-09: 186015017; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: vendor will ship on 17/Nov. Only 4U of FTN will bedelayed from 22/Nov to 24/Nov. 03 Nov 17 update: Wrong part received. New lot will ETA on 6/Nov. Venture will ship more if output more.; 2018-06-18: Monitoring; 2018-06-25: Close
210000969 | ASSY PCB ACTIVE HTCH-A WITH FAN |  |  | 2018-04-02: Venture PCBA; 2018-04-09: 186015042 186015045; 2018-04-30: Tester; 2018-05-07: 27 Oct 17 update: The uprev PCBA is encountering high reject in functiona testing. GES & WATERS are working on to update the testing software. Already have some qty tested but still on hold to do a re-test.; 2018-06-18: Monitoring; 2018-06-25: Close
360000138 | HEATER COIL |  |  | 2018-04-02: BACKER HOTWATT, INC; 2018-04-09: 186186301; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 27 Oct 17 Update: 12U ETD 22/Nov 24U ETD 4/Dec Push out to ETA 30/Nov due to raw material shortage. Venture to expedite.; 2018-06-18: Monitoring; 2018-06-25: Close
289006107 | ASSY COVER HEATER COLUMN DUAL CM (JPI) |  |  | 2018-04-02: MRPC; 2018-04-09: 186015039 186015043 186015049; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Quality; 2018-05-07: 03 Nov update: Cosmetic issue - texturing and ghosting encounter on the cover. Pending WPPL Milford QA 27 Oct 17 update: Tooling issue & will need FA with WATERS approval, TBA. Venture will continue to expedite for Dec'17 shortages.; 2018-06-18: Monitoring; 2018-06-25: Close
441001095 | ACQUITY AUXILIARY COLUMN MANAGER |  |  | 2018-04-02: ATRONIX; 2018-04-09: 186015039; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: Shipment improved 20 Oct 17 update: ETA delay from 19/Oct to 10/Nov due to short of connector WAT020122. Venture is expedting with Atronix for recovery.; 2018-06-18: Monitoring; 2018-06-25: Close
Various Parts | NA |  |  | IDEX | Various instrument | Bethany/ Jie Hui | Mark Looney | Material | 13 Oct 17 update: Due to recent wild fire that is going on at California, Sonoma Valley, Idex Rohnert Park facility employees has been partially affected. Mark Looney will provide latest update on Monday or Tuesday. | [5 empty] | Monitoring | Close
210000852 279003610 | ASSY, PCB, ETHERNET SWITCH ASSY, ETHERNET CARD |  |  | 2018-04-02: Venture; 2018-04-09: 186015007 186015008 186015009 186015010 186015017 186015046 700003191; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Quality; 2018-05-07: 20 Oct 17 update: Defect lead oxidised (AVX tant cap #0356680) Next AVX incoming 2K ETA 22 Oct, 7100 ETA 05 Nov. With current on hand quanity for 279003610 FTN shipment, UPLC CLASSIC shipment should not be affected. Venture to provide recovery plan. 13 Oct update: All current stocks were affected by lead oxidised (AVX tant cap #0356680) Potential impact Nov shipment instrument & Spare. UPLC CLASSIC (Impact WW45 shipment onwards) UPLC H & I (Impact WW46 shipment onwards) Venture is working on the recovery plan. Milford does not have stock to support.; 2018-06-18: Monitoring; 2018-06-25: Close
405010358 | PULLEY TIMING .08 P X 14 G FAIRLOC |  |  | DESIGNATRONICS | 186015017 | Bethany/ Jie Hui | John Gannon | Material | 27 Oct 17 update: 12U ETD 30/Oct; 10U ETD 1/Nov 20 Oct 17 update: Part is currently under Anodize process and once back it’s set screw and ship. The parts will be back from plating 10/23. Supplier current commited to ship on 27/10 under consolidation shipment, lot size 670 pcs. Venture had instructed supplier to ship via air on 24/10. 13 oct 17 update: FTN shipment on 25/Oct will be affected due to supplier push out delivery schedule (ETD 26/09 to 23/10). Designatronics had been escalated internally. John Gannon is helping to follow up with Designatronics daily for recovery plan. | [5 empty] | Monitoring | Close
289007089 | ACQUITY UPLC CH-30A |  |  | 2018-04-02: FU Yu; 2018-04-09: 186015045; 2018-04-16: Yin Ying; 2018-04-30: Material; 2018-05-07: 13 Oct 17 update: ETA 13/Oct (First time receive, need WPPL to approve incoming checklist). 06 Oct 17 update: ETA 13/Oct 29 Sep 17 update: ETA TBA, reference part 405011878 FA approved. Samples received at GES on 28/sep. FUYU needs 3weeks to turn around.; 2018-06-18: Monitoring; 2018-06-25: Close
279001951 | XDUCER PRESSURE FLEX CABLE 20K PSI |  |  | 2018-04-02: DJ Instruments; 2018-04-09: 186015000 186015017 186015046 186017000; 2018-04-16: Bethany/ Wan Jing; 2018-04-30: Quality; 2018-05-07: 06 Oct 17 update: The lab results have emerged that parts are Tin/Cobalt plated which is not per Waters print. Randy Ryder has updated the team to continue to build and hold material until an updated TMD (TMD010372) has been approved. 29 Sep 17 update: Potential quality defect comes from concern that our plating supplier may have switched plating materials from Chrome to Tin/Cobalt without approval on the latest batch of FR3 housings. Potential shipment impact is on 01-Nov and onwards. 4000 ETD 10/19/2017, estimated dock date 23 october.; 2018-06-18: Monitoring; 2018-06-25: Close
415001696 400002298 | HOUSING HTCH-A MODIFIED MULTI-TOOL COLLET & COMP. SCREW HPFT |  |  | 2018-04-02: Fuyu; 2018-04-09: 186015042; 2018-04-16: Yin Ying; 2018-04-30: Material; 2018-05-07: 22 Sep 17 update: ECO received but having issue to implement, impacting last 15u shipment for Q3. Raised TMD 010396 to allow Venture to continue production. 15 Sep 17 update: 415001696(FUYU)QOH 472pcs & 410002920 ETA 22/Sep must use in set but 410002920 pending ECO9215089 & need perform FA upon receive. Impact 15 units.; 2018-06-18: Monitoring; 2018-06-25: Open
402000130 | DIFF. GRATING 1000 G/MM |  |  | 2018-04-02: OPTOMETRICS; 2018-04-09: 186015029; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 22 Sep 17 update: 70pcs approved to use on 18/Sep. 6u Shipped 21/Sep , 6u ETD 25/Sep; 2018-06-18: Monitoring; 2018-06-25: Open
410003180 | WASTE VALVE INLINE 1/4-28 THREADS |  |  | 2018-04-02: IDEX; 2018-04-09: 186015017 186015046; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 22 Sep 17 update: IDEX experienced a late delivery on one component (Teflon Balls) that is normally a 2-week lead-time to continue to expedite with IDEX.; 2018-06-18: Monitoring; 2018-06-25: Open
279002649 | ASSY EMISSION HOME SENSOR |  |  | 2018-04-02: ATRONIX; 2018-04-09: 186247500; 2018-04-16: Yin Ying; 2018-04-30: Material; 2018-05-07: 22 Sep 17 update: 6u ETD 29/Sep. 100% Wire Wrong Orientation. Replacement 45pcs will shipout 22/Sep pending AWB.; 2018-06-18: Monitoring; 2018-06-25: Close
400002298 | MULTI-TOOL COLLET & COMP. SCREW HPFT |  |  | 2018-04-02: EAGLE INDUSTRIES INC; 2018-04-09: 186015007 186015008; 2018-04-16: Wan Jing; 2018-04-30: Quality; 2018-05-07: 29 Sep 17 update: quality issue, contamination & waiting for further discussion between WPPL, WATERS Milford & VENTURE 22 Sep 17 update: TBA, contamination issue. O/H on hold by Waters. Pending for WATERS disposition on the rework.; 2018-06-18: Monitoring; 2018-06-25: Close
210000520 | ACQUITY ARC QSM-R |  |  | 2018-04-02: CEI; 2018-04-09: Various models; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 15 Sep 17 update: 475 ETA 3/Oct & 200 ETA 10/Oct. Common with FTN, CH, CM, BSM, & QSM.; 2018-06-18: Monitoring; 2018-06-25: Open
210000345 | ASSY PCB QSM PUMP ROHS |  |  | 2018-04-02: CEI; 2018-04-09: 186017000; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 22 Sep 17 update: CEI - 48pcs rec'd 20/Sep, 48pcs 26/Sep 15 Sep 17 update: CEI - 25pcs 22/9, 71pcs 26/9 Recovery shipment from Venture 2u ETD 27-Sep, 13u ETD 28-Sep, 8u ETD 29-Sep 08 Sep 17 update: 30U ETD 20/Sep, 1U ETD 29/Sep 11U ETD 29/Sep, 10U ETD 4/Oct 12U ETD 4/Oct, 12U ETD 6/Oct, 6U ETD 9/Oct CEI ETA 26 Sep 31 Aug 17 update : 10pcs ETA 4/Sep from Flex, 96pcs 26/Sep 11u ETD 29/Sep, 10u ETD 4/Oct; CEI - ETA 26/Sep CEI full kit material on 15sep, Venture to work with CEI to futher improve the delivery schedule. 25 Aug 17 update: Affecting ARC QSM (186017000) on wk 38 shipment due to upside. Flex able to support 10pcs, ETD 04 Sep. (Venture to issue PO) Remaing quanity, Venture to continue to expidite and will advice the expediting cost. Current commit date from CEI as below: 03/10/2017 96pcs 24/10/2017 96pcs; 2018-06-18: Monitoring; 2018-06-25: Open
210000396 | ASSY PCB DEGASSER TRANSDUCER |  |  | 2018-04-02: CEI; 2018-04-09: 186017000; 2018-04-16: Bethany/ Jie Hui; 2018-05-07: 08 Sep update: CEI 210000396 received 31 Aug 17 update : CEI - 30pcs ETA 4/Sep from Flex 30u ETD 20/Sep, 1u ETD 29/Sep 11u ETD 29/Sep, 10u ETD 4/Oct; CEI - ETA 26/Sep CEI full kit material on 15sep, Venture to work with CEI to futher improve the delivery schedule 25 Aug 17 update: Affecting ARC QSM (186017000) on wk 38 shipment due to upside Flex able to support 30pcs, ETD 04 Sep. (Venture to issue PO) Remaing quanity, Venture to continue to expidite and will advice the expediting cost. Current commit date from CEI as below: 03/10/2017 120pcs 24/10/2017 80pcs; 2018-06-18: Monitoring; 2018-06-25: Close
405000929 | HOUSING EM OPTICS BENCH MACHINING |  |  | 2018-04-02: B&E; 2018-04-09: 186247500 186015029; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 11 Aug 17 update: Current delivery date from B&E as below: 22/08/2017 - 30pcs 28/08/2017 - 30pcs Venture is still workinng with supplier for better delivery date 04 Aug 17 update : 3u Target ETD 8'Aug. Original 3u Put on hold for shipment is using alternate vendor (China Synergy) raw cast material. Only release the instruments for shipment upon FA approval of the new vendor material.; 2018-06-18: Monitoring; 2018-06-25: Close
405000928 | HOUSING, EM OPTICS BENCH, MACHINING |  |  | 2018-04-02: B&E; 2018-04-09: 186017006 186002475 186247500; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 11 Aug 17 update: Current delivery date from B&E as below: 22/09/2017 - 40pcs 29/09/2017 - 20pcs Venture is still workinng with supplier for better delivery date 28 July 17 update: Potential impact to ww38 & 39 production. B&E just received 300pcs raw cast from TPI. B&E needs 5 weeks LT to perform machining & surface treatment.Venture needs to closely monitor delivery schedule from B&E. Please refer to delivery tab for delivery.; 2018-06-18: Monitoring; 2018-06-25: Close
441001044 | ASSY CABLE LIGHT PIPE EXTENDED |  |  | 2018-04-02: ATRONIX; 2018-04-09: 186015017 186015046; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 14 July 2017 update : 1u 186015017 impact on ww30. Current ETA 24/Jul, Qty 400pcs to bridge up the gap. (ATRONIX is shortage of an unique child-part (# 405011011) 07 July 2017 update : Original ETA date from supplier is 12-Jul, Latest (current) ETA has been reschedule out to 31-Jul. Reason is that ATRONIX is shortage of an unique child-part (# 405011011 REV.A). Milford is facing shortage for this item as well therefore unable to support.; 2018-06-18: ASAP; 2018-06-25: Close
279000380 | ALLIANCE 2475 MULTICHANNEL FLR DETECTOR |  |  | 2018-04-02: SL Power; 2018-04-09: 186002475; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 21 July update: CoC obtained from SL Power, 40 pcs at IQC is being released. No impact to production. 14 July 2014 update : Will resume Production upon receive the 6 pcs(RoHs) from Milford to build the past due 3u and replace the 2u which previously build with non-RoHs power supply which already shipped to Europe. The 40pcs at IQC confirmed is RoHs material and to be released once receive CoC from SL power. 07 July 2017 Update : Per Venture feedback, SL power shipment being received with wrong revision. While pending findings from Venture, checking with Milford to support for July shipment.; 2018-06-18: ASAP; 2018-06-25: Close
279002268 | POWER SUPPLY 270 WATT INC INRUSH LIMIT |  |  | 2018-04-02: Venture; 2018-04-09: 186017000; 2018-04-30: Quality; 2018-05-07: 30 June 2017 update: Replacement part from supplier received, Venture activated overtime to complete the remaining 6 units to be ship on 5 July or else 6 units will be slip to Friday 7 July. 23 June 2017 update : 19u ETD 05/Jul, 6u ETD 07/Jul; W1279002268-R(SL Power) 100pcs cannot be use due carton damage when cargo received. Able to pull in next open PO from 07-Jul to ETA 28-Jun. 08 June 2017 Update : 19u ETD 05-Jul, 6u 07-Jul; W1279002268-R(SL Power) 100pcs cannot be use due carton damage when cargo received. Able to pull in next open PO from 07-Jul to ETA 28-Jun; 2018-06-25: Close
NA | NA |  |  | 2018-04-02: NA; 2018-04-09: 186001500; 2018-04-16: Edwin Desmond; 2018-04-30: Tester; 2018-05-07: 26-Jan-18 update : Tester issue resolved. 19 Jan 18 update : Failure symptom: UUT hang at Firmware download test step.; 2018-06-18: ASAP; 2018-06-25: Close
402000130 | Grating |  |  | 2018-04-02: OPTOMETRICS; 2018-04-09: 186002475 186247500 186017006 700002035 700003707 700009344; 2018-04-16: Edwin; 2018-04-30: Quality; 2018-05-07: 13 Apr 18 update : Based on the manufacturing data provided and the gratings samples shipped to US, it appears there is inconsistency in performance on the gratings manufactured by the new master grating that Waters approved in Sept 2017. The drift in performance likely happen on later lots from Dec 2017 onwards which leads Milford team to believe it a process related issue at this supplier Optometrics rather than a design issue. For Venture manufacturing - action is to continue alignment on 2475 models with sorted higher efficiency grating > 49.1% while Milford team and Optometrics works to address the problem. 06 Apr 18 update : Next incoming 177pcs ETA 9 Apr. Continue to use high efficiency grating for 247500. 29 Mar 18 update : Q1 customer orders is covered. However, Venture is failed to meet Q1 production plan. Venture is continuing build with new grating and provide daily update. 23 Mar 18 update : 10u+5spares away from customer orders. 53pcs grating received, 29pcs > 49.1% effeciency. Venture is continuing build with new grating and provide daily update. 16 Mar 18 update : As of 16-Mar-18 morning, 11u 186247500, 8u 186015029 and 1u 186017006 passed and shipped from Venture. Balance 43u 185247500, 8u 186015029, 1u 186017006 and 3u 186002475 to close the quarter. Milford is in progress to draft the TMD to allow Venture to use grating with energy level >900, with the condition it passed specification at final test level. 02 Mar 18 update : New batch is giving the same fallout results, Venture is continuing production by performing sorting. 30% of lot passing alignment to be used for 2475. Balance 70% will be used for 5029. Venture to pull in more material to support production. 25 Feb 18 update : New batch of parts ETA schedule (30 pieces ETA 26-Feb, and 70 pieces ETA 1-Mar). Upon receiving the new batch, Venture engineering will be assembling these into the Optics Bench, and from there, it will be determine whether does these still have the “Reference energy failure issue”. 15 Feb 18 update: FLR detector output are affected by output of optic bench - cannot achieve energy level after tuning. Suspected this is due to grating change. Still under investigation with supplier for more details.; 2018-06-18: ASAP; 2018-06-25: Open
430002640 430003271 | NEEDLE, .039 OD x .005 ID W/C'SINK (405013771) |  |  | Machine shop | 186015017 186015046 | Jen | Lisa McNarama | Quality | 13 Ap 18 update : No impact to production at GES There is no stop ship at instrument level as determined by PIM (Lisa McNarama) and Point of Contact at Waters Milford (Scott Gibsob). TMD 010489 sent to Venture to allow part# 405013771 out of tolerence for the true position at the tip of the needle, and true position at counterbore and straightness. 06 Apr 18 update : it was discovered in the machine shop that the needle on assembly 430005254 may be potentially bent which may result in functional failure. Stop ship issued to purge spares and kits with 430005254 of date code 02.Mar.2018 to 03.Apr.2018. In progress to confirm actual material impact at GES. | [5 empty] | Monitoring | Close
Note on G25: sgblim: 1U on hold for IQ Test [KL]
Note on H26: sgblim: 1U on hold for IQ Test[KL]
Note on H27: sgblim: 10units > [KL] 5 units used high efficiency grating for evaluation per Edwin request(4 units released on 18 Apr, will be shipping on 20-Apr. 1 unit still on hold). 1 unit failed the S/N ratio, 4 units passed, shipping on 20-Apr. In summary, total of 8 units shipping on 20-Apr.
Note on F28: sgblim: ETD 20'Apr 2u
Note on G28: sgblim: ETD 20'Apr 1u 23'Apr 5u
Note on I28: sgblim: ETD 27'Apr 1u 30'Apr 5u
Note on G29: sgblim: 7u ETD 18/Apr 5u ETD 20/Apr
Note on H29: sgblim: 6u ETD 25/Apr 6u ETD 27/Apr
Note on H30: sgblim: 12u shipped. 1u on hold for IQ test. [KL], 1u ETD 20/Apr [FGs], *reason -FT failed, per 18/Apr email.
Note on H31: sgblim: 1u on hold for IQ test. [KL]
Note on F32: sgblim: ETD 20'Apr 4u
Note on H32: sgblim: ETD 20'Apr 1u, 30'Apr 3u , 2'May 2u
Note on C33: sgblim: CH = Column Heater
Note on C34: sgblim: CH/C = Column Heater/Cooler
Note on C35: sgblim: ACQUITY Arc Bio 30cm Column Heater
Note on C36: sgblim: ACQUITY Arc Bio 30cm Col. Heater / Cooler

## CEI
[5 empty] | Shipped |  | OK |  | Potential delay, need to monitor |  |  |  | Delay, need immediate action
Updated On: | 2018-04-20 16:27 |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  |  | DO NOT CHANGE
|  | Q2 Forecast |  | WW14 | WW15 | WW16 | WW17 | WW18 | WW19 | WW20 | WW21 | WW22 | WW23 | WW24 | WW25 | WW26 | Type of Issue | Status
PN | Short Desc | Prod Plan | QTD Del'd | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | Material | Open
186015014 | CPSO | 80 | 26 | 8 | 10 | 8 | 8 | 6 | 8 | 8 | 8 | 6 | 7 | 3 | 0 | 0 | Quality | Close
186015020 | ASO | 15 | 0 | 0 | 0 | 0 | 2 | 3 | 4 | 3 | 1 | 0 | 2 | 0 | 0 | 0 | Tester
186015021 | ASO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Manufacturing
Tooling
Part No | Part Description |  |  | Supplier | Instrument Affected | WPPL Team (Lead) | Milford Contact | Type of Issue | Brief Description of Issue | [5 empty] | Target Recovery Date | Status
400006352 400001357 | SUPPORT TRAY, QSM, CPSO PANEL, SIDE, ELEVATOR |  |  | 2018-04-02: TREND; 2018-04-09: 186015014; 2018-04-16: Jen; 2018-04-30: Quality; 2018-05-07: 15-Jan-2016 update : CEI revised their incoming inspection checklist to remove criteria for gloss since it's not a requirement for them to check. QA has approved. Closed 08-Jan-16 update : CEI is working with Trend to optimize their process to meet gloss requirements for CEI parts and share the supporting data. Jen to follow up with Waters Milford on TMD to cover gloss levels of 3.8 to 4.7 for powder coat batch # 3R15I0033. 31-Dec-15 update : 405002979 - Supplier Accurounds shipment delinquent to ETD US 29-Dec, ETA 04-Jan-2016. AWB# 7193146295. (orignal committed ETA 28-Dec-2015). 400006352 rejected due to Delta E* Out Of Spec, physical has already returned to Trend. Status TBA until Monday due to Trend shut down.; 2018-06-18: ASAP; 2018-06-25: Close
290001063 | BOX, SHIP, SAMPLE ORG, DUAL H/C ENGINE |  |  | 2018-04-02: J&J; 2018-04-16: Yin Ying; 2018-04-30: Material; 2018-05-07: 23-Sep-2016 update : Milford team will review the report follow by ECR submission. Target to close by end of OCT 2016. 15-July-2016 update : Evaluation report already sent to reliability group for review. Status : TBA 13-May-2016 update : Status remain no progress. 15-Apr-2016 update : Report submitted to Mike Cook & Randy Chin. Will follow up with reply return date. 01-Apr-2016 update : Report received on 31-Mar-2016. Review in progress. 24-Mar-2016 update : Drop test performed on 22-Mar, pending report compilation from J&J and CEI. 11-Mar-2016 update: Waters dwg updated with correct dimension - Approved FA based on dwg prelim Rev B. Ethafoam 600 is used instead of Ethafoam 450. CEI to finalize and submit plan for WPPL review before proceed with physical drop test. 04-Mar-2016 update: Jen and WJ went to CEI for FA sample buyoff on 03-Mar. Unable to buyoff due to wrong dimension on Waters dwg – YinYing to send revised prelim dwg to CEI. FAI report also require amendment - CEI to resubmit. 26-Feb-2016 update : FA sample has been reschedule to buy off on 02-Mar. 19-Feb-2016 update : FA sample to be ready on 29-Feb for buy off. 15-Jan-2016 : Has activated CEI to proceed with FA samples using localized proposed material Ethafoam 600. FA samples and drop test is schedule to be completed on 15-Feb-16.; 2018-06-18: Oct; 2018-06-25: Open
405002950 | SHAFT, GUIDE, A/S TRANSFER |  |  | 2018-04-02: Rei Promax Accurounds; 2018-04-09: 186015020; 2018-04-16: Bethany Lim Wan Jing; 2018-04-30: Material Quality; 2018-05-07: 22-July-2016 update : Localized supplier Rei Promax is having problem to support due to "straightness issue after heat treatment process" (1st lot) & "surface roughness"(2nd lot) causing 100% part rejected.Next shipment from Accurounds ETD on 29-July-2016. Has extended LOI with Accurounds to continue support. 15-July-2016 update : Localized supplier Rei Promax is having problem to support the material due to straightness issue and causing 100% part rejected. Next shipment from Accurounds will ETD on 29-July-2016. Buyer is expediting.; 2018-06-18: ASAP; 2018-06-25: Close
279001917 | ASSY, PANEL, PNEUMATICS, CPSO |  |  | 2018-04-02: AIRLINE HYDRAULICS CORP; 2018-04-09: 186015014; 2018-04-16: Bethany; 2018-04-30: Material; 2018-05-07: 30-Sep-2016 update : CEI to continue follow up delivery date from Airline to ensure no impact to Q4 production. 15pcs - ETD 10/03. 23-Sep-2016 update : 4pcs(reworked Qty) of 279001917 received on 19-Sep. Q3 shipment no impact. Next incoming 30pcs on 21-Sep & 15pcs on 23-Sep. Pull-in 10units from ww40 to ww39, CEI is reviewing on the capacity and will advise. 16-Sep-2016 update : 186015014 upside. Supplier airline imposed expediting cost of USD 2717.50 to pull-in the material. - 1 unit shipment affected on ww 39 is due to fail decay test. - CEI is still working with supplier on the delivery schedule.; 2018-06-18: Monitoring; 2018-06-25: Close
NA | NA |  |  | 2018-04-02: NA; 2018-04-09: 186015014; 2018-04-16: Wesley Desmond; 2018-04-23: NA; 2018-04-30: Tester; 2018-05-07: 24-Feb-2017 update : Per CEI feeback, they can meet 120unit per quarter (simulation floor space, headcout and tooling, will activate when require) 6-Feb-17 update: Production Meeting discussion - attach rate probably at 430 units per year. Operations team to work with CEI to simulate at a realistic volume (150 or 200 per quarter). 20-Jan-2017 update : Wesley and Desmond to advise the Production and Tester capacity for Insturment 186015014 if were to support for 300units per quarter.; 2018-06-25: Close
289007707 (289004744) | ASSY, SHELF, SAMPLE ORGANIZER |  |  | 2018-04-02: Technimetal; 2018-04-09: 186015014 186015020; 2018-04-23: Dave A Mark Loney; 2018-04-30: Material; 2018-05-07: 10-Mar-2017 update : Bearing (child part#289004744) from NBM managed to improved to 1000pcs ETD Japan 20-Mar-2017. CEI is following up with Technimetal to ensure shipment is deliver on time to support for April shipment. Closed. 03-Mar-2017 update : Impacting 10-Apr-2017 shipment and onwards. Technimetal has shortage of bearing (child part#289004744) from NBM. Current committed date from NMB (bearing supplier) as below:- 3000pcs ETD Japan 07-Apr-2017 4000pcs ETD Japan 22-May-2017 Currently Dave A and Mark Loney are helping to expedite bearing from NBM, however there is no improvement at the moment. Will continue follow up and expedite. CEI is checking with Technimetal the turn around time to assemble into 289007707 upon bearing receive.; 2018-06-18: ASAP; 2018-06-25: Close
210000420 441000878 | ASSY, PCB, 2200 ELEVATOR PERSONALITY ASSY, CABLE, ELEVATOR D.C. POWER |  |  | CEI | 186015014 186015020 700002606 | Wan Jing | Bob Lincoln Gene Tancrell | Quality | 30 June 2017 update : Both ECO9214851 and ECO9214563 to CEI and implemented. 09 June 2017 update: Customer reported burned/melted power connector in several sample organizer instruments. - TMD010283 (expire on 05-May-2017) - expiration will be extended to 23 Jun 2017 (1) Rework existing PCB 210000420 into 210001161. (2) New PCB 210001161 must use with new cable 441001987. -Current status: TMD is active. Will be in progress for all fresh builds until TMD expires or upon ECO release. ECO9214851 – released new board. ECO9214563 – released new cable. - ECO 9213776 hves been released to have both part# 210001161 & 441001987 structured into BOM and update ASPs. - Status for spare new P/N - ECR9215383,to release spare part# 700011556 (Kit, 2200 Elevator Personality PCB/Cable) & 700011557 (ASSY, CABLE, ELEVATOR 24VDC POWER) ECO released. 21-Apr-2017 update: Customer reported burned/melted power connector in several sample organizer instruments. - TMD010283 (expire on 05-May-2017) - expiration will be extended to 23 Jun 2017 (1) Rework existing PCB 210000420 into 210001161. (2) New PCB 210001161 must use with new cable 441001987. -Current status: TMD is active. Will be in progress for all fresh builds until TMD expires or upon ECO release. ECO9214851 – released new board. ECO9214563 – released new cable. - Follow up to release ECR 9213776 to have both part# 210001161 & 441001987 structured into BOM and update ASPs. Current ECR status : Assigned - Status for spare new P/N TMD010308 - TMD has been closed. 07-Apr-2017 update: Customer reported burned/melted power connector in several sample organizer instruments. - TMD010283 (expire on 05-May-2017) (1) Rework existing PCB 210000420 into 210001161. (2) New PCB 210001161 must use with new cable 441001987. -Current status: TMD is active. Will be in progress for all fresh builds until TMD expires or upon ECO release. ECO9214851 – released new board. ECO9214563 – released new cable. - Follow up to release ECR 9213776 to have both part# 210001161 & 441001987 structured into BOM and update ASPs. - Status for spare new P/N TMD010308 For rework of units sent back to CEI from DC - TMD010308 (expire on 20-Jun-2017) (1)Remove shield only -WJ had buyoff CEI's rework instruction and first unit reworked. -Current status: TMD is active. -Total RMA is 101x RMA from ADC - 12x 20-Mar, 30x 22-Mar, 25x 23-Mar (Total 67x) RMA from Japan – 2x – 29-Mar (Total 2x) RMA from EDC - TBC (Total 32x) – Shipment delayed, scheduled to return to CEI on 10-Apr (Mon). -Follow up: (1) Rework for units from GDC to be confirmed 30-Mar-2017 update : Customer reported burned/melted power connector in several sample organizer instruments. TMD010283 (expire on 05-May-2017) (1) Rework existing PCB 210000420 into 210001161. (2) New PCB 210001161 must use with new cable 441001987. -Current status: TMD has been implemented. Will be in progress for all fresh builds until TMD expires or upon ECO release. - Follow up to release ECR 9213776 to have both part# 210001161 & 441001987 structured into BOM. - Current spare P/N will not be reworked until spare new P/N is released. Randy Ryder will follow up on this ECR. TMD010308 (expire on 20-Jun-2017) FOr rework of units sent back to CEI from DC (1)Remove shield only -Current status: TMD has been implemented. -Total RMA is 101x RMA from ADC - 12x 20-Mar, 30x 22-Mar, 25x 23-Mar (Total 67x) RMA from Japan - 2x 29-Mar (Total 2x) RMA from EDC - TBC (Total 32x) (arriving Singapore mid next week) -Follow up: (1) Rework for units from GDC to be confirmed - probably rework in Milford. Randy to confirm. 24-Mar-2017 update : Customer reported burned/melted power connector in several sample organizer instruments. - TMD010283 (expire on 05-May-2017) (1) Rework existing PCB 210000420 into 210001161. (2) New PCB 210001161 must use with new cable 441001987. -Current status: TMD has been implemented. Will be in progress for all fresh builds until TMD expires or upon ECO release. - Follow up to release ECR 9213776 to have both part# 210001161 & 441001987 structured into BOM. - Status for spare new P/N TMD010308 FOr rework of units sent back to CEI from DC - TMD010308 (expire on 20-Jun-2017) (1)Remove shield only -WJ had buyoff CEI's reowkr instruction and first unit reworked. -Current status: TMD has been implemented. -Total RMA is 101x RMA from ADC - 12x 20-Mar, 30x 22-Mar, 25x 23-Mar (Total 67x) RMA from Japan - TBC (Total 2x) RMA from EDC - TBC (Total 32x) -FOllow up: (1) Rework for units from GDC to be confirmed 17-Mar-2017 update : Customer reported burned/melted power connector in several sample organizer instruments. - TMD010283 (expire on 05-May-2017) (1) Rework existing PCB 210000420 into 210001161. (2) New PCB 210001161 must use with new cable 441001987. -New cable FA has been approved. -WJ and Edwin had buyoff CEI's rework instruction. -Current status: TMD has been implemented. 6 units of CPSO had completed buyoff under TMD010283. WJ to release list of S/N of first 6 units of CPSO. - Follow up to release ECR 9213776 to have both part# 210001161 & 441001987 structured into BOM. 10-Mar-2017 update : Customer reported burned/melted power connector in several sample organizer instruments. - TMD010283 (expire on 05-May-2017) (1) Rework existing PCB 210000420 into 210001161. (2) New PCB 210001161 must use with new cable 441001987. -Desmond and WJ to review CEI's TCN and rework instruction. -Current status: TMD has not been implemented. Implementation after cable 441001987 approval granted from Milford. - New cable 441001987, 2pcs FA sample will ETA Milford 13-Mar-2017, result should be available on 14-Mar-2017. - Has instructed CEI to proceed to build new PCBA 210001161. - Follow up to release ECR 9213776 to have both part# 210001161 & 441001987 structured into BOM. | [5 empty] | ASAP | Close
405002031 | BLOCK, CARRIAGE, LEADSCREW |  |  | 2018-04-02: Multisource; 2018-04-09: 186015020; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 01 Dec 17 update: FA approved. 24 Nov 17 update: FA sample received, CEI to perform measurement and will arrange with WPPL QA for buyoff. 17 Nov 17 update: FA sample + production lot estimate to dock at CEI 20 Nov. CEI will arrange with Jen for buy off. Potential impact 2 units ASO. 10 Nov 17 update: Reschedule to 10 Nov to resubmit FA sample to Milford , affecting 2 units ASO.; 2018-06-18: Monitoring; 2018-06-25: Close
400004470 | PLATE, INNER, DOOR, SAMPLE ORGANIZER |  |  | 2018-04-02: Mechanical Plastics; 2018-04-09: 186015014; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 19Jan 18 update: Supplier has shipped the material on 20-Jan(Waybill: 9387413991) 29 Dec 17 update: Supplier short of raw material. Impacting shipment on 22-Jan-2018.; 2018-06-18: Monitoring; 2018-06-25: Close
405002031 | BLOCK, CARRIAGE, LEADSCREW |  |  | 2018-04-02: Multisource; 2018-04-09: 186015020; 2018-04-16: Bethany/ Jie Hui; 2018-04-30: Material; 2018-05-07: 29 Dec 17 update: Impacting shipment on 12-Feb-2018 due to pull-in of Spare 700004468, shortage : 1pc; 2018-06-18: Monitoring; 2018-06-25: Close

## Fu Yu
|  |  |  | Potential delay, need to monitor |  |  |  | Delay, need immediate action |  |  |  |  | Shipped |  | OK
Updated On: | 2018-04-20 16:27 |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  |  | DO NOT CHANGE
Instrument |  | Q2 Forecast |  | WW14 | WW15 | WW16 | WW17 | WW18 | WW19 | WW20 | WW21 | WW22 | WW23 | WW24 | WW25 | WW26
PN | Short Desc | Prod Plan | QTD Del'd | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | Type of Issue | Status
205001247 | Bottle tray | 1287 | 198 | 55 | 0 | 143 | 55 | 198 | 55 | 44 | 132 | 143 | 154 | 143 | 110 | 55 | Material | Open
WAT271082 | Bottle tray | 168 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 28 | 0 | 28 | 28 | 28 | 0 | 28 | Quality | Close
205001139 | Bottle tray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tester
N2971044 | PL - 1139 BT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Manufacturing
N2971045 | PL - 1247 BT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tooling
Part No | Part Description |  |  | Supplier | Spare Affected | OPS Team (Lead) | Milford Contact | Type of Issue | Brief Description of Issue | [5 empty] | Target Recovery Date | Status
405019835 | ADAPTER, BARBED, ELBOW |  |  | 2018-04-02: FUYU; 2018-04-09: 205001247; 2018-04-16: Bethany; 2018-04-30: Material; 2018-05-07: 15-Jan-2016 update : 405019835 to be received by FUYU on 20-Jan-2015. WW03 remaining 33pcs shipment to be shipped on WW04. 08-Jan-2016 update : ECO 9200214, Supplier Sample only ETA FUYU on 13-Jan-2105. Fuyu is checking with supplier whether they still have inventory to support at old revision before they can implement with new Rev. TBA; 2018-06-18: ASAP; 2018-06-25: Close
205001139 | BOTTLE TRAY REWORK |  |  | 2018-04-02: FUYU; 2018-04-16: Zack/Kevin; 2018-04-30: Material; 2018-05-07: 17-Mar-2017 Update: Damaged inventory scrapped in system in plant SG20. Pending issuance of claim settlement from Expeditors, Claim Ref: "Claim20170222 – 205001139 damaged in ADC" 24-Feb-2017 update : Claim issued to Expeditors for the full cost of the 14 damaged units. Pending credit from Expeditors before scrapping the units 17-Feb-2017 update : Provision for scrap - TBA. - 14 units damaged at expeditor due to mishandling. - FUYU quoted USD 950 to cover the cost incurred for re-inspection / re-box as well as left over balance of MOQ of carton box (336pcs) 20-Jan-2017 update : Provision for scrap - TBA. - 14 units damaged at expeditor due to mishandling. - Getting FUYU to check on the condition of the physical - Pending FUYU to advise the quotation for the rework and re-box of 14pcs x 205001139 base on MOQ of 350pcs for the carton box. 05-Aug-2016 update : Rework activity need to be further push out until further notice. 29-Jul-2016 update : Final Qty to be salvaged is 182pcs(13 pallets). Working with FUYU on when to start to perform rework activity. Total cost : USD 7672.22 (USD 900 (labor cost) + USD 6772.22 (Rework cost)) 08-Apr-2016 update : Dismantle and rework activity estimated to be performed by early July 2016. Final Qty to be finalised. 01-Apr-2016 update : Revised quotation as attached to be reviewed on 05-Apr-2016 04-Mar-2016 update : Revised quotation as attached. 19-Feb-2016 update : Getting FUYU to re-quote for rework cost. (Dismantle the bottle tray). TBA 05-Feb-2016 update : Quotation obtain as attached 29-Jan-2016 update : Pending Fuyu to provide dismantle quotation and new quote for Part# 205001139. To explore feasibility to rework 205001139 to 205001247. Total 14 purchased parts involved. 4 parts - common to 205001247. 3 parts - unique, need to scrap. 7 parts - common to Milford or other CMs. Important note: The rework require major effort (strip / dismantle the bottle tray till individual piece part level) - may impose high rework cost and possess risk in part damage as well.; 2018-06-18: TBA; 2018-06-25: Close
400006520 400006447 | ASSY, BOTTLE TRAY SUPPORT/STIFFENER BRKT, TUBING GUIDE HOLDER |  |  | 2018-04-02: Paradigm; 2018-04-09: 205001247; 2018-04-16: Jen; 2018-04-30: Quality; 2018-05-07: 23 Mar 18 update : No Impact to shipment. Defect :40006520 & 400006447 found finishing paint surface rough/ contaminated/ pitted. Fuyu is working with Paradigm to sort part based on inspection at 30 inches for SPECK per spec WAT022557.; 2018-06-18: ASAP; 2018-06-25: Close
400006520 | Assy, Bottle Tray Support/Stiff |  |  | 2018-04-02: Paradigm; 2018-04-09: 205001247; 2018-04-16: Bethany; 2018-05-07: 13 Apr 18 update : Paradigm receive few batches(0n 02/14) of Sherwin William powder(PN: ULM2-90001) which is in harden condition. Estimated the new batch of powder will be reaching Paradigm on 17-Apr. Fuyu to continue expedite and follow up.; 2018-06-18: ASAP; 2018-06-25: Close

## Summary
Update as of WW16 2018:
Q2 2018 CTB Status
1 | Flextronics production CTB for Q2 2018 :
Material Shortage
405002568 OPTICS BENCH, MACHINING, 2998
Based on current Qty received 127pcs at Flex, can full fill production requirement till week 17. DC allocation :- 186299800 - 50 units on week 17 (Top priority customer order + forecast) 186015034 - 2 units by week 17 186002998 - 6 units by week 17 186017003 - 16 units by week 18
279003850 Bio-Chem Solenoid
200pcs intransit (ETA 23-Apr), Next ship date on 27-Apr
WAT270524 / 279001810 (Parker GPV)
Part# 279001810 - 100 ETA 23/Apr. 150 pc ETD on 20/Apr and 125 pc ETD on 21/Apr(Qty to be confirmed). Part# WAT270524 - 97pcs received. Parker is working this weekend and they will have a ship plan update for next week on 23/Apr
WAT026574 M&J
Localized from Ronco to asia supplier M&J. Due to short LT, M&J is pending for Marcorubber part for risk build & FA. Marcorubber committed to ship 5/4 with expediting fees paid, ETA 5/7 at M&J, and ETD M&J 5/9. Pre-alert, supplier’s expediting for improvement. Checking with Milford if able to support.
Quality
NA
Manufacturing
New sesal pack implementation
Flex have committed to output 20/day per recovery plan. Will be able to meet quarter number.
Tester
279002660 (Flex Senai)
Flex Senai will rent a unit to use for production, the rental unit will ETA Senai on 24-Apr (for noise and reference test).
2 | Venture production CTB for Q2 2018 :
Material Shortage
NA
Tester or Quality??
FLR Detector Optic Bench
Based on the manufacturing data provided and the gratings samples shipped to US, it appears there is inconsistency in performance on the gratings manufactured by the new master grating that Waters approved in Sept 2017. The drift in performance likely happen on later lots from Dec 2017 onwards which leads Milford team to believe it a process related issue at this supplier Optometrics rather than a design issue. For Venture manufacturing - action is to continue alignment on 2475 models with sorted higher efficiency grating > 49.1% while Milford team and Optometrics works to address the problem.
Quality
NA
3 | CEI production CTB for Q2 2018 :
Material Shortage
NA
4 | Fu Yu production CTB for Q2 2018 :
Material Shortage
NA
Quality
NA

## FA Tracker
No | CM | Supplier | Description | Status | CM FA submission date | WPPL FA buy off plan | To do/Owner | Target Phase-in date | Action item
1 | Flex/Venture/CEI | Foamtec | Foamtec will be relocating their office to Woodlands area and the manufacturing operation to Johor Bahru, Malaysia | Open | Refer to Foamtec FA tab |  | Wan Jing - Venture Eugene - Flex Jen - CEI | 2018-03-01 | 1.All buffer stock is being planned and committed by Foamtec to build prior to the machine shut down 2. FA to be buy off by respective WPPL QA 3. Foamtec is extending Singapore side production until July. CMs to continue placing order to support for production while pending Milford to update the drawings.
2 | Venture | Baiteng | Sheetmetal - Total 29 parts Changed from supplier Metal component to Baiteng - CR | Open | 2017-08-01 | 2017-09-01 | Wan Jing | Q1 2018 | 1. All 29 FA parts from BT at various dates/lots - 23 parts FA approved and implemented in Q1 2018. - 4 parts to be implemented in Q2 2018. - 1 parts(400000938) - getting Trend to support - 1 parts(WAT270632) Target to be implemented in Q2 2018
3 | Venture/Flex | Baiteng | Manufacturing Relocation Total 168 parts | Closed | TBA | TBA | Wan Jing - Venture Eugene - Flex | TBA | Baiteng has confirmed the Manufacturing Relocation plan will be pushing out to year 2020.
4 | Venture | B&E | 3 Optic benches Qualifying new raw cast supplier from TPI to China Synergy - CR, eliminate Quality and logistic issue | Closed | 2017-08-01 | 2017-08-10 | Wan Jing | 2017-11-01
5 | Flex | B&E | Launching new tool for child part# WAT207031(Child part for WAT207032) - Tool replacement | Closed | 2017-12-01 | 2017-12-01 | Flex SQE | Q2 2018 | 1. New tooling from B&E is approved for WAT207031 2. Flex is checking the ETA with B&E on the first lot using the new tool, TBA.
6 | Venture/Flex | PARKER HANNIFIN | Manufacturing Relocation | Closed |  |  | Milford QA - Rob Z | Q4 2017 | Parker has started to ship material from new plant.
7 | CEI | Multisource (Haus Specialty) | Manufacturing Relocation | Closed |  |  | Milford - Site buy off (John/Tom) WPPL FA - Jen | 2017-10-01 | 405002031 - FA approved, release to production.
8 | Flex | ETLA (Frencken Group Limited) | Change from JEP to ETLA (New supplier) - CR, eliminate Quality issue | Closed | 2017-09-01 | 2017-09-01 | Flex/Eugene 1st pass FA - Eugene site audit - Jen | Q3 18 | 1. Site audit - WPPL QA (Jen) --> Done 2. 405002568 - FA approved. Pending for final Quotation confirmation to ETLA. 3. 405006788 - FA approved 4. 405003295 - FA approved
9 | Flex | JEP | Optic bench - 405002568 - Faclity relocation | Closed | TBA | TBA | Flex/Eugene | TBA | ECO to match drawing therefore no need to raise TMD. (Void)
10 | Flex | Trend | Changed of child part WAT060671 (childpart for WAT057996) from A&one to Yangbum - CR | Closed | 2017-08-01 | 2017-08-01 | Eugene | 2017-11-01
11 | Flex | Flex Senai | PCBA conversion non-clean to Clean process | Closed | TBA | TBA | Shaynee | Q4 2017 | Kallang 1st shipment date Group 1 - FA reviewed and approved 210000411- 13 Dec, 210000416 - 15 Nov, 210000425 - 22 Nov, 210000384 - 15 Nov Group 2 - FA reviewed and approved 210000355 - 6 Dec, 210000444 - 13 Dec, 210000429 - 6 Dec, 210000428 - 6 Dec Group 3 - FA reviewed and approved 210000477 - 29 Nov, 210000404 - 29 Nov, 210000414 - 20 Dec, 210000415 - 6 Dec Group 4 - FA reviewed and approved 210000562 - 27 Dec, 210000345 - 27 Dec, 210000396 - 20 Dec, 210000417 - 20 Dec 210000421 - 7 Mar. Kallang is currently working with Senai on the spare demand from Milford, and will provide the revised implementation date with scrap quantity again

## Foamtec FA
| 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01
Venture Total: 43 parts | Buffer stock |  |  | Until March 2018
Site audit Done in Sept
FA submission Timeline |  | 22 | 21
Flex Total: 42 parts | Buffer stock |  |  | Until June 2018
Site audit 03.11.2017
FA submission Timeline |  |  | 21 | 19 | 2
CEI Total: 18 parts | Buffer stock |  |  | Until June 2018
Site audit Done on 10.10.2017
FA submission Timeline |  |  | 12 | 6
Foamtec shut down end Dec 2017

## Alliance
c
2998/PDA/eLambda Detectors Recovery Plan
| Monthly - Total Reqmt Vs Planned Recovery |  |  |  | Weekly - Total Reqmt Vs Planned Recovery | [12 empty] | Monthly - Total Reqmt Vs Actual |  |  |  | Daily Recovery Plan Vs Actual ==> | [16 empty] | 20u/day |  |  | OT |  |  | Holiday |  |  |  | OT | [6 empty] | OT | [6 empty] | OT | [6 empty] | OT |  |  | Holiday |  |  |  | OT | [6 empty] | OT | [5 empty] | Holiday | [7 empty] | OT
Models | Monthly | Apr | May | Jun | Weekly | Open + | [11 empty] | Monthly | Apr | May | Jun |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
[6 empty] | 2018-04-11 | 2018-04-18 | 2018-04-25 | 2018-05-02 | 2018-05-09 | 2018-05-16 | 2018-05-23 | 2018-05-30 | 2018-06-06 | 2018-06-13 | 2018-06-20 | 2018-06-27 | [82 empty] | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29 | time axis 2018-04-09 to 2018-06-23
[100 empty] | Jun | Jun | Jun | Jun | Jun | time axis 2018-04-09 to 2018-06-23
186269505 | Total Reqmt | 72 | 118 | 118 | Weekly Reqmt | 24 | 24 | 24 | 22 | 24 | 24 | 26 | 22 | 32 | 32 | 24 | 30 | Total Reqmt | 72 | 118 | 118 | Plan | [5 empty] | 0 | 0 |  | 5 | 11 | [5 empty] | 8 | 8 | 8 | 8 | 4 |  | 5 |  | 5 | 5 | 5 |  |  | 8 | 6 | 6 | 6 | 5 | 5 |  | 5 | 5 | 5 | 0 | 5 | 5 |  | 5 | 5 | 6 | 5 | 5 | 5 |  | 5 |  | 6 | 6 | 6 | 6 |  | 6 | 6 | 6 | 6 | 6 |  |  | 6 | 6 | 6 | 6 |  |  |  | 7 | 5 | 5 | 5 | 5 | 5 |  | 7 | 7 | 7 | 8 |  |  | 308
| Total Plan | 0 | 92 | 149 | Total Plan | 0 | 16 | 16 | 30 | 30 | 31 | 26 | 26 | 36 | 30 | 23 | 44 | Total Act Till Date | 20 | 0 | 0 | Actual | 2018-04-17: 5; 2018-04-18: 11; 2018-04-19: 4 | [7 empty] | 20
| Delta | -72 | -98 | -67 | Delta | -24 | -32 | -40 | -32 | -26 | -19 | -19 | -15 | -11 | -13 | -14 | 0 | Balance to go | -52 | -170 | -288 | Delta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | -4 | -12 | -20 | -28 | -32 | -32 | -37 | -37 | -42 | -47 | -52 | -52 |  | -60 | -66 | -72 | -78 | -83 | -88 |  | -93 | -98 | -103 | -103 | -108 | -113 |  | -118 | -123 | -129 | -134 | -139 | -144 |  | -149 | -149 | -155 | -161 | -167 | -173 |  | -179 | -185 | -191 | -197 | -203 | -203 |  | -209 | -215 | -221 | -227 | -227 | -227 |  | -234 | -239 | -244 | -249 | -254 | -259 |  | -266 | -273 | -280 | -288 | -288 | -288
186269506 | Total Reqmt | 202 | 356 | 262 | Weekly Reqmt | 45 | 79 | 78 | 62 | 78 | 78 | 76 | 62 | 70 | 70 | 60 | 62 | Total Reqmt | 202 | 356 | 262 | Plan | [5 empty] | 0 | 0 |  | 12 | 8 | 18 | 18 |  | 0 | 18 | 10 | 12 | 12 | 12 | 16 |  | 15 |  | 15 | 15 | 15 | 20 |  | 12 | 14 | 14 | 14 | 15 | 15 |  | 15 | 15 | 15 | 20 | 15 | 15 |  | 15 | 15 | 14 | 15 | 15 | 15 |  | 15 |  | 14 | 14 | 14 | 14 |  | 14 | 14 | 14 | 14 | 14 |  |  | 14 | 14 | 14 | 14 |  |  |  | 13 | 15 | 15 | 15 | 15 | 15 |  | 13 | 13 | 13 | 12 |  |  | 820
| Total Plan | 0 | 256 | 411 | Total Plan | 0 | 20 | 76 | 70 | 90 | 89 | 94 | 74 | 84 | 70 | 57 | 96 | Total Act Till Date | 48 | 0 | 0 | Actual | 2018-04-17: 12; 2018-04-18: 8; 2018-04-19: 14; 2018-04-20: 14 | [7 empty] | 48
| Delta | -202 | -302 | -153 | Delta | -45 | -104 | -106 | -98 | -86 | -75 | -57 | -45 | -31 | -31 | -34 | 0 | Balance to go | -154 | -510 | -772 | Delta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4 | -8 | -8 | -8 | -26 | -36 | -48 | -60 | -72 | -88 | -88 | -103 | -103 | -118 | -133 | -148 | -168 |  | -180 | -194 | -208 | -222 | -237 | -252 |  | -267 | -282 | -297 | -317 | -332 | -347 |  | -362 | -377 | -391 | -406 | -421 | -436 |  | -451 | -451 | -465 | -479 | -493 | -507 |  | -521 | -535 | -549 | -563 | -577 | -577 |  | -591 | -605 | -619 | -633 | -633 | -633 |  | -646 | -661 | -676 | -691 | -706 | -721 |  | -734 | -747 | -760 | -772 | -772 | -772
186017103 | Total Reqmt | 0 | 0 | 0 | Weekly Reqmt | [12 empty] | Total Plan | 0 | 0 | 0 | Plan
| Total Plan | 0 | 0 | 0 | Total Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Total Act Till Date | 0 | 0 | 0 | Actual
| Delta | 0 | 0 | 0 | Delta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Balance to go | 0 | 0 | 0 | Delta | 2018-04-09: 0; 2018-04-10: 0; 2018-04-11: 0; 2018-04-12: 0; 2018-04-13: 0; 2018-04-14: 0; 2018-04-15: 0; 2018-04-16: 0; 2018-04-17: 0; 2018-04-18: 0
| Total Reqmt | 0 | 0 | 24 | Weekly Reqmt | [5 empty] | 24 | [6 empty] | Total Reqmt | 0 | 0 | 24 | Plan
| Total Plan | 0 | 0 | 0 | Total Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Total Act Till Date | 0 | 0 | 0 | Actual
| Delta | 0 | 0 | -24 | Delta | 0 | 0 | 0 | 0 | 0 | -24 | -24 | -24 | -24 | -24 |  |  | Balance to go | 0 | 0 | -24 | Delta | 2018-04-09: 0; 2018-04-10: 0
| Monthly - Total Reqmt Vs Planned Recovery |  |  |  | Weekly - Total Reqmt Vs Planned Recovery | [12 empty] | Total Reqmt Vs Actual |  |  |  | Daily Recovery Plan Vs Actual ==>
Recovery Plan | Monthly | Apr | May | Jun | Weekly | [12 empty] | Monthly | Apr | May | Jun |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | 0
[6 empty] | 2018-04-11 | 2018-04-18 | 2018-04-25 | 2018-05-02 | 2018-05-09 | 2018-05-16 | 2018-05-23 | 2018-05-30 | 2018-06-06 | 2018-06-13 | 2018-06-20 | 2018-06-27 | [5 empty] | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2017-04-02 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2017-04-09 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2017-04-16 | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2017-04-23 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2017-04-30 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2017-04-30 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2017-04-30 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | 2018-06-01 | 2018-06-02 | 2017-04-30 | 2018-06-04 | 2018-06-05 | 2018-06-06 | 2018-06-07 | 2018-06-08 | 2018-06-09 | 2017-04-30 | 2018-06-11 | 2018-06-12 | 2018-06-13 | 2018-06-14 | 2018-06-15 | 2018-06-16 |  | 2018-06-18 | 2018-06-19 | 2018-06-20 | 2018-06-21 | 2018-06-22 | 2018-06-23 |  | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29 | 2018-06-30
All | Total Reqmt | 274 | 474 | 380 | Weekly Reqmt | 69 | 103 | 102 | 84 | 102 | 102 | 102 | 84 | 102 | 102 | 84 | 92 | Total Reqmt | 274 | 474 | 380 | Plan | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 17 | 19 | 18 | 18 | 0 |  | 18 | 18 | 20 | 20 | 20 | 20 |  | 20 | 0 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 0 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 0 |  | 20 | 20 | 20 | 20 | 0 | 0 |  | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 0 | 0 | 1128
| Total Plan | 0 | 348 | 560 | Total Plan | 0 | 36 | 92 | 100 | 120 | 120 | 120 | 100 | 120 | 100 | 80 | 140 | Total Act Till Date | 0 | 0 | 0 | Actual | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 17 | 19 | 18 | 14 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 68
| Delta | -274 | -400 | -220 | Delta | -69 | -136 | -146 | -130 | -112 | -94 | -76 | -60 | -42 | -44 | -48 | 0 | Balance to go | -274 | -748 | -1128 | Delta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4 | -4 | -4 | -22 | -40 | -60 | -80 | -100 | -120 | -120 | -140 | -140 | -160 | -180 | -200 | -220 |  | -240 | -260 | -280 | -300 | -320 | -340 |  | -360 | -380 | -400 | -420 | -440 | -460 |  | -480 | -500 | -520 | -540 | -560 | -580 |  | -600 | -600 | -620 | -640 | -660 | -680 |  | -700 | -720 | -740 | -760 | -780 | -780 |  | -800 | -820 | -840 | -860 | -860 | -860 |  | -880 | -900 | -920 | -940 | -960 | -980 |  | -1000 | -1020 | -1040 | -1060 | -1060 | -1060
Formulas:
Open + = [W]
M = [OT]+2
T = [M]+1
W = [T]+1
Note on K8: after 16-Apr shipment
Note on K12: after 16-Apr shipment.
Note on AP13: the rest of inventory is either failed carry over test and needs troubleshooting or still in final test. There are units waiting for test too.

## 299800
Detector # | 2018-04-04 | 2018-04-11 | 2018-04-18 | 2018-04-25 | 2018-05-02 | 2018-05-09 | 2018-05-16 | 2018-05-23 | 2018-05-30 | 2018-06-06 | 2018-06-13 | 2018-06-20 | 2018-06-27 | Q2'18
WAT-186002998 | 6 | 6 | 6 | 6 | 4 | 6 | 6 | 6 | 4 | 6 | 6 | 6 | 7 | 75
WAT-186299800 | 40 | 40 | 40 | 40 | 32 | 40 | 48 | 48 | 48 | 48 | 48 | 48 | 40 | 560
WAT-186015034 | 2018-04-11: 3; 2018-04-18: 3; 2018-05-09: 3; 2018-05-16: 3; 2018-06-06: 3; 2018-06-27: 5; Q2'18: 20
WAT-186015053 | 2018-04-04: 3; 2018-05-09: 3; 2018-05-23: 4; Q2'18: 10
WAT-186017003 | 14 | 12 | 12 | 14 | 8 | 12 | 12 | 16 | 12 | 16 | 16 | 9 | 12 | 165
WAT-186017013 | 2018-04-04: 5; 2018-04-11: 5; Q2'18: 10
Open PO/forecast gated by JEP 405002568 optic bench until 13-Apr resolution | [14 empty] | Recovery plan ===> | [15 empty] | no shipment (WH shift) | [8 empty] | recovery mode until 11-May
Detector # | 2018-04-04 | 2018-04-11 | 2018-04-18 | 2018-04-25 | 2018-05-02 | 2018-05-09 | 2018-05-16 | 2018-05-23 | 2018-05-30 | 2018-06-06 | 2018-06-13 | 2018-06-20 | 2018-06-27 | Q2'18 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2018-04-22 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29 | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2018-05-06 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2018-05-13 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | 2018-06-01 | 2018-06-02 | 2018-06-03 | 2018-06-04 | 2018-06-05 | 2018-06-06 | 2018-06-07 | 2018-06-08 | 2018-06-09 | 2018-06-10 | 2018-06-11 | 2018-06-12 | 2018-06-13 | 2018-06-14 | 2018-06-15 | 2018-06-16 | 2018-06-17 | 2018-06-18 | 2018-06-19 | 2018-06-20 | 2018-06-21 | 2018-06-22 | 2018-06-23 | 2018-06-24 | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29
WAT-186002998 | 2018-04-04: 6; 2018-04-11: 6; 2018-04-18: 6; 2018-04-25: 6; 2018-05-02: 4; 2018-05-09: 6; 2018-05-16: 6; 2018-05-23: 6; 2018-05-30: 4; 2018-06-06: 6; 2018-06-13: 6; 2018-06-20: 6; 2018-06-27: 7; Q2'18: 75; Recovery plan ===> 2018-04-24: 12; Recovery plan ===> 2018-04-26: 12; Recovery plan ===> 2018-04-30: 4; no shipment (WH shift) 2018-05-09: 6; recovery mode until 11-May 2018-05-16: 6; recovery mode until 11-May 2018-05-23: 6; recovery mode until 11-May 2018-05-30: 4; recovery mode until 11-May 2018-06-06: 6; recovery mode until 11-May 2018-06-13: 6; recovery mode until 11-May 2018-06-20: 6; recovery mode until 11-May 2018-06-27: 7
Cum 186002998 | 6 | 12 | 18 | 24 | 28 | 34 | 40 | 46 | 50 | 56 | 62 | 68 | 75 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 24 | 24 | 24 | 24 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 75 | 75 | 75
WAT-186299800 | 2018-04-04: 6; 2018-04-11: 40; 2018-04-18: 40; 2018-04-25: 40; 2018-05-02: 32; 2018-05-09: 40; 2018-05-16: 48; 2018-05-23: 48; 2018-05-30: 48; 2018-06-06: 48; 2018-06-13: 48; 2018-06-20: 48; 2018-06-27: 40; Q2'18: 526; Recovery plan ===> 2018-04-17: 16; Recovery plan ===> 2018-04-18: 20; Recovery plan ===> 2018-04-19: 14; Recovery plan ===> 2018-04-20: 16; Recovery plan ===> 2018-04-23: 20; Recovery plan ===> 2018-04-24: 4; Recovery plan ===> 2018-04-25: 10; Recovery plan ===> 2018-04-26: 6; Recovery plan ===> 2018-04-27: 17; no shipment (WH shift) 2018-05-07: 50; no shipment (WH shift) 2018-05-09: 25; recovery mode until 11-May 2018-05-16: 48; recovery mode until 11-May 2018-05-23: 48; recovery mode until 11-May 2018-05-30: 48; recovery mode until 11-May 2018-06-06: 48; recovery mode until 11-May 2018-06-13: 48; recovery mode until 11-May 2018-06-20: 48; recovery mode until 11-May 2018-06-27: 40
Cum 186299800 | 6 | 46 | 86 | 126 | 158 | 198 | 246 | 294 | 342 | 390 | 438 | 486 | 526 |  |  | 16 | 36 | 50 | 66 | 66 | 66 | 86 | 90 | 100 | 106 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 173 | 173 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 246 | 246 | 246 | 246 | 246 | 246 | 246 | 294 | 294 | 294 | 294 | 294 | 294 | 294 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 390 | 390 | 390 | 390 | 390 | 390 | 390 | 438 | 438 | 438 | 438 | 438 | 438 | 438 | 486 | 486 | 486 | 486 | 486 | 486 | 486 | 526 | 526 | 526
WAT-186015034 | 2018-04-11: 3; 2018-04-18: 3; 2018-05-09: 3; 2018-05-16: 3; 2018-06-06: 3; 2018-06-27: 5; Q2'18: 20; Recovery plan ===> 2018-04-24: 4; Recovery plan ===> 2018-04-26: 2; no shipment (WH shift) 2018-05-09: 3; recovery mode until 11-May 2018-05-16: 3; recovery mode until 11-May 2018-06-06: 3; recovery mode until 11-May 2018-06-27: 5
Cum 186015034 | 0 | 3 | 6 | 6 | 6 | 9 | 12 | 12 | 12 | 15 | 15 | 15 | 20 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 20 | 20 | 20
WAT-186015053 | 2018-04-04: 3; 2018-05-09: 3; 2018-05-23: 4; Q2'18: 10; Recovery plan ===> 2018-04-27: 3; no shipment (WH shift) 2018-05-09: 3; recovery mode until 11-May 2018-05-23: 4
Cum 186015053 | 3 | 3 | 3 | 3 | 3 | 6 | 6 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
WAT-186017003 | 2018-04-04: 10; 2018-04-11: 12; 2018-04-18: 12; 2018-04-25: 14; 2018-05-02: 8; 2018-05-09: 12; 2018-05-16: 12; 2018-05-23: 16; 2018-05-30: 12; 2018-06-06: 16; 2018-06-13: 16; 2018-06-20: 9; 2018-06-27: 12; Q2'18: 161; Recovery plan ===> 2018-04-19: 6; Recovery plan ===> 2018-04-20: 4; Recovery plan ===> 2018-04-25: 10; Recovery plan ===> 2018-04-30: 16; no shipment (WH shift) 2018-05-07: 20; no shipment (WH shift) 2018-05-09: 3; recovery mode until 11-May 2018-05-11: 9; recovery mode until 11-May 2018-05-16: 12; recovery mode until 11-May 2018-05-23: 16; recovery mode until 11-May 2018-05-30: 12; recovery mode until 11-May 2018-06-06: 16; recovery mode until 11-May 2018-06-13: 16; recovery mode until 11-May 2018-06-20: 9; recovery mode until 11-May 2018-06-27: 12
Cum 186017003 | 10 | 22 | 34 | 48 | 56 | 68 | 80 | 96 | 108 | 124 | 140 | 149 | 161 |  |  |  | 0 | 6 | 10 | 10 | 10 | 10 | 10 | 20 | 20 | 20 | 20 | 20 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 56 | 56 | 59 | 59 | 68 | 68 | 68 | 68 | 68 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 161 | 161 | 161
WAT-186017013 | 2018-04-04: 5; 2018-04-11: 5; Q2'18: 10; no shipment (WH shift) 2018-05-07: 10
Cum 186017013 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Sum Qty | 30 | 66 | 61 | 60 | 44 | 64 | 69 | 74 | 64 | 73 | 70 | 63 | 64 |  |  | 16 | 20 | 20 | 20 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 40 | 0 | 9 | 0 | 0 | 0 | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0
Cummulative Qty | 30 | 96 | 157 | 217 | 261 | 325 | 394 | 468 | 532 | 605 | 675 | 738 | 802 |  |  | 16 | 36 | 56 | 76 | 76 | 76 | 96 | 116 | 136 | 156 | 176 | 176 | 176 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 276 | 276 | 316 | 316 | 325 | 325 | 325 | 325 | 325 | 394 | 394 | 394 | 394 | 394 | 394 | 394 | 468 | 468 | 468 | 468 | 468 | 468 | 468 | 532 | 532 | 532 | 532 | 532 | 532 | 532 | 605 | 605 | 605 | 605 | 605 | 605 | 605 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 738 | 738 | 738 | 738 | 738 | 738 | 738 | 802 | 802 | 802
Actualized ==>
Detector # | 2018-04-04 | 2018-04-11 | 2018-04-18 | 2018-04-25 | 2018-05-02 | 2018-05-09 | 2018-05-16 | 2018-05-23 | 2018-05-30 | 2018-06-06 | 2018-06-13 | 2018-06-20 | 2018-06-27 | Q2'18 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2018-04-22 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29 | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2018-05-06 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2018-05-13 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | 2018-06-01 | 2018-06-02 | 2018-06-03 | 2018-06-04 | 2018-06-05 | 2018-06-06 | 2018-06-07 | 2018-06-08 | 2018-06-09 | 2018-06-10 | 2018-06-11 | 2018-06-12 | 2018-06-13 | 2018-06-14 | 2018-06-15 | 2018-06-16 | 2018-06-17 | 2018-06-18 | 2018-06-19 | 2018-06-20 | 2018-06-21 | 2018-06-22 | 2018-06-23 | 2018-06-24 | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29
WAT-186002998 | 2018-04-04: 6; 2018-04-11: 6; 2018-04-18: 6; 2018-04-25: 6; 2018-05-02: 4; 2018-05-09: 6; 2018-05-16: 6; 2018-05-23: 6; 2018-05-30: 4; 2018-06-06: 6; 2018-06-13: 6; 2018-06-20: 6; 2018-06-27: 7; Q2'18: 75
Cum 186002998 | 6 | 12 | 18 | 24 | 28 | 34 | 40 | 46 | 50 | 56 | 62 | 68 | 75 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WAT-186299800 | 2018-04-04: 6; 2018-04-11: 40; 2018-04-18: 40; 2018-04-25: 40; 2018-05-02: 32; 2018-05-09: 40; 2018-05-16: 48; 2018-05-23: 48; 2018-05-30: 48; 2018-06-06: 48; 2018-06-13: 48; 2018-06-20: 48; 2018-06-27: 40; Q2'18: 526; Actualized ==> 2018-04-17: 16; Actualized ==> 2018-04-18: 20; Actualized ==> 2018-04-19: 14; Actualized ==> 2018-04-20: 16
Cum 186299800 | 6 | 46 | 86 | 126 | 158 | 198 | 246 | 294 | 342 | 390 | 438 | 486 | 526 |  |  | 16 | 36 | 50 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66
WAT-186015034 | 2018-04-11: 3; 2018-04-18: 3; 2018-05-09: 3; 2018-05-16: 3; 2018-06-06: 3; 2018-06-27: 5; Q2'18: 20
Cum 186015034 | 0 | 3 | 6 | 6 | 6 | 9 | 12 | 12 | 12 | 15 | 15 | 15 | 20 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WAT-186015053 | 2018-04-04: 3; 2018-05-09: 3; 2018-05-23: 4; Q2'18: 10
Cum 186015053 | 3 | 3 | 3 | 3 | 3 | 6 | 6 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WAT-186017003 | 2018-04-04: 10; 2018-04-11: 12; 2018-04-18: 12; 2018-04-25: 14; 2018-05-02: 8; 2018-05-09: 12; 2018-05-16: 12; 2018-05-23: 16; 2018-05-30: 12; 2018-06-06: 16; 2018-06-13: 16; 2018-06-20: 9; 2018-06-27: 12; Q2'18: 161; Actualized ==> 2018-04-19: 6; Actualized ==> 2018-04-20: 4
Cum 186017003 | 10 | 22 | 34 | 48 | 56 | 68 | 80 | 96 | 108 | 124 | 140 | 149 | 161 |  |  |  | 0 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
WAT-186017013 | 2018-04-04: 5; 2018-04-11: 5; Q2'18: 10
Cum 186017013 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0