## Flex
Items S/N | Action items description | Owner | Target closure | Completion (Yes/ No) | Remark
1 | Loss Comm, Flex to submit evaluation form and get approval from WPPL | HZ | 2020-09-25 | Yes
| HZ to follow up with Flex on weekly update status | HZ | 2020-10-30
2 | SDS tester validation, EL/HZ to follow up and approve target 2 per week | EL/HZ | 2020-10-23
3 | Interface tubing update/ Waste line check, HZ to get Joel update effectiveness check | HZ | 2020-10-23
4 | HZ to check on PMS Station condition and keep necessary record/evidence for working condition | HZ | 2020-09-30
5 | Golden Unit list, HZ to discuss with Edwin on scrap disposition | HZ | 2020-10-09
6 | EvalS20025 Optice Bench from GVT, Desmond to follow up with Aldwin on evaluation status | DA | 2020-10-30
7 | HDD backup, HZ to follow up with Joel weekly progress update; HZ to check with Joel/Lwin if any other way to backup | HZ | 2020-11-09
8 | OESR for keithley 236, HZ to get Joel to update status | HZ | 2020-09-30
9 | OESR for pumptray tester repair, HZ to check with Mark on advice | HZ | 2020-09-30
10 | OESR for Small Shunt,HZ to get Joel to advise solution and close OESR. | HZ | 2020-09-30
11 | OESR for Aperture alignment station, HZ to check with Joel if can be closed | HZ | 2020-09-30
12

## Venture
Items S/N | Action items description | Owner | Target closure | Completion (Yes/ No) | Remark
1 | BSM Package, review by Milford, GY to follow up with Milford | GY | 2020-10-02
2 | SDS tester validation, EC/YH to follow up and approve target 2 per week | EC/YH | 2020-10-16
3
4
5
6
7
8
9
10
11
12

## CEI
Items S/N | Action items description | Owner | Target closure | Completion (Yes/ No) | Remark
1
2
3
4
5
6
7
8
9
10
11
12

## Others
Items S/N | Action items description | Owner | Target closure | Completion (Yes/ No) | Remark
1
2
3
4
5
6
7
8
9
10
11
12