## Flex
Items S/N | Action items description | Next course of action | Owner | Start Date | Target closure | Completion (Yes/ No) | Remark
1 | Loss Comm | Flex to submit evaluation form and get approval from WPPL | HZ |  | 2020-09-25 | Yes
|  | TE-8 direct LAN cable to run; Flex to update FPY; Fixed TE-13 port and continue evaluation and update FPY; | HZ | 2020-11-02 | 2020-11-11 | Yes | update project status to include Oct data; Split Direct/Normal data for TE-8; Updated
|  | Flex to send out project status with data；Split Direct/Normal data for TE-8 | HZ | 2020-11-02 | 2020-11-18 | Yes | Joel update table to splite Direct/Normal data as per discussion;
|  | Relay box from Eric was received; To verify on TE-8 | HZ | 2020-11-02 | 2020-12-04 | Yes | verified relay box, but relay box still cannot be controlled by Ethernet Switch. Feedback to Eric on 01 Dec 20.
|  | Flex to update latest FPY for nov FPY | HZ | 2020-12-04 | 2020-12-09
|  | Follow up with Eric on TE-8 repair; | HZ | 2020-12-07 | 2020-12-31
2 | Flex to provide weekly update status on Even loading | Owner follow up | HZ |  | 2020-10-30 | Yes | HZ and Flex to even out loading
|  | Flex update loading per sigmasure monthly | HZ | 2020-11-02 | 2020-11-11 | Yes | Flex to update with data; Updated with later date;
|  | Flex to update with sigmasure data | HZ | 2020-11-02 | 2020-11-18 | Yes
|  | Flex to review station TE82903-10 usage and update | HZ | 2020-11-23 | 2020-12-04 | No | Flex missed update;Move target closure date to 14 Dec;
|  | Flex to update latest status | HZ | 2020-11-02 | 2020-12-09
4 | BSM/QSM first pass yield improvement | Interface tubing update/ Waste line check; | HZ |  | 2020-10-23 | Yes | No impact on yield improvement and close
|  | 2 months monitoring on yield improvement | HZ | 2020-11-02 | 2020-12-31
6 | Golden Unit list | Owner to discuss with Edwin on scrap disposition | HZ |  | 2020-10-09 | Yes | Discussed
|  | Flex to update the latest list | HZ | 2020-11-23 | 2020-12-14
|  | Flex to update list with summary of EOL status/althernate test bench | HZ | 2020-11-02 | 2020-11-11 | No | Flex to send out summary; sent out by later date
|  | Flex to update list as per discussion | HZ | 2020-11-02 | 2020-11-18 | Yes | updated without summary page
|  | Flex to update latest list with summary page and clsoe this acitivity as discussed | HZ | 2020-11-02 | 2020-12-04 | Yes | updated
|  | Flex to update final list with pictures | HZ | 2020-12-04 | 2020-12-09
8 | Spare PC management due to unable to backup | Matt to update spare availablity and cost breakdown for 2 testers TE 82519 and TE 82973 - 1 | HZ | 2020-11-02 | 2020-11-25 | Yes | Updated matt with photo and models
|  | Follow up with Matt on cost breakdown | HZ | 2020-11-16 | 2020-12-11
9 | OESR for keithley 236 | Owner to escalate to Joel to update status | HZ |  | 2020-09-30 | Yes | Bernard updated status on 16 Oct but not addressed the concerns;
|  | Get Phani to address concerns | HZ | 2020-11-02 | 2020-11-06 | Yes | Email was sent to Joel/Phani to get update from Senai
|  | Flex to look into actual failure and fix it | HZ | 2020-11-02 | 2020-11-18 |  | Flex Senai updated status but didn't make it work on tester
|  | Flex to update complete date -- checking with Amy | HZ | 2020-11-16 | 2020-11-23 | Yes | Esclated to Amy/Phani/Vicent
|  | Flex to update with proposed solution | HZ | 2020-11-16 | 2020-12-04 | No | updated in CSMP; not able to adhere to dateline
|  | Flex to update with proposed solution | HZ | 2020-11-16 | 2020-12-18
14 | TSP 735001613 to study for inclusion of energy reading to mentioned at System Initialization test. | Flex to update comparison data before/after briefing this acitivity to production and review process if ASP/TSP update is required | HZ | 2020-11-02 | 2020-11-13 | yes | Flex to update with benefit from this briefing; sent at later date
|  | Flex to update as per discussion | HZ | 2020-11-02 | 2020-11-18 | Yes | Flex proposed to have TSP updated to align with practice
|  | Flex to update with justificaiton by email | HZ | 2020-11-18 | 2020-12-04 | Yes
|  | Flex to update on shunts and OB ernerge reading | HZ | 2020-12-04
15 | EVENT LOG | Flex to set up ELI | EL | 2020-11-02 | 2020-11-06 | No | Issue encourted during set up; Move target closure date: 11 Dec
|  | Eguene to follow up to get details of issue encourtered. | El | 2020-11-02 | 2020-11-20 | Yes
|  | Checking with Milford to resolve network issue | El | 2020-11-02 | 2020-11-30 | No
|  | status update after discussion with Chin Ping | EL | 2020-11-02 | 2020-12-16

## Venture
Items S/N | Action items description | Next course of action | Owner | Start Date | Target closure | Completion (Yes/ No) | Remark
1 | BSM Package | ECRO in creation stage | GY | 2020-11-02 | 2020-11-30 | No | ECR9238266 under review (23.Nov); In progress and pending for impact sheet; target to closure date: 31 Dec
3 | QSM testers flowrate accuracy | 1st batch collected 20% fallout; 2nd batch of 15 data collection in progress | HZ |  | 2020-10-31 | Yes | Venture collecting data; Result shows FPY of TE-1 improved from 20% to 12.5%; Overall FPY is 67 %, one of best working station.
|  | Put under monitoring of yield; Venture to update No.of units under monitoring | HZ | 2020-11-02 | 2020-12-31 |  | Discuss in Thursday (26 Nov)-- Decision to continue monitoring or close
6 | TMD for PCB test at box build | Approved and pending for execution; Checking with Jie Hui on execution status | HZ | 2020-11-23 | 2020-11-25
7
8
9
10
11
12

## CEI
Items S/N | Action items description | Next course of action | Owner | Start Date | Target closure | Completion (Yes/ No) | Remark
1 | OESR S204297 for TCM/PCM backup PC | To receive shipping information of the backup PC from Milford (Matt) | HZ | 2020-11-02 | 2020-12-31 | Yes | received PC
| Setup PC for TCM/PCM | Setup PC & IQ; CEI to update Asset Manual & Test Dashboard | HZ | 2020-11-16 | 2020-12-31
2
3
4
5
6
7
8
9
10
11
12

## Others
Items S/N | Action items description | Owner | Start Date | Target closure | Completion (Yes/ No) | Remark
1 | close PO status by 18 Nov | All | 2020-11-16 | 2020-11-18 | Yes | The rest are done; Sidd
| Sidd, YH & GY are going update it today. |  | 2020-11-16 | 2020-11-23
2
3
4
5
6
7
8
9
10
11
12

## close
Items S/N | Action items description | Next course of action | Owner | Start Date | Target closure | Completion (Yes/ No) | Remark | CM
7 | EvalS20025 Optice Bench from GVT | Owner follow up with Aldwin on evaluation status | DA |  | 2020-10-30 | Yes |  | Flex
10 | OESR for pumptray tester repair | Tester still restarting; Mark to advise again by 16.Oct | HZ |  | 2020-09-30 | Yes |  | Flex
11 | OESR for Small Shunt | Owner to get Joel to advise solution and close OESR. | HZ |  | 2020-09-30 | Yes | Joel to continue using existing; HZ to raise CEA by 16.Oct for spares | Flex
12 | OESR for Aperture alignment station | Owner to check with Joel if can be closed | HZ |  | 2020-09-30 | Yes | Tester already repaired, 210001164 for effectiveness check done | Flex
8 | HDD backup | Flex to update by 14.Oct | HZ |  | 2020-11-09 | Yes |  | Flex
13 | Evaluation of Alliance firmware | Flex to run evaluation per plan on 14.oct and review the results for anomalies | HZ |  | 2020-10-16 | Yes |  | Flex
5 | GTS 3 Fail* | Self test fixture still has issue: to get Venture for update | HZ |  | 2020-10-16 | Yes | Due for calibration by Mar 2021; needs to prioritise; | Venture
|  | Matt will take the self-test fixture for repair; Venture to ship this tester out for repair. | HZ | 2020-11-02 | 2020-11-13 | Yes | Fixture shipped Milford
2 | SDS tester validation | Owner follow up and approve target 2 per week | EC/YH |  | 2020-10-16 | Yes | 1st week validation completed per plan | Venture
4 | PREMIER validation | 1. Matt: CMA and CHA software update 2. Eric: FLR software/TSP update* | EC |  | 2020-10-16 | Yes | Can enquire with Chan
3 | SDS tester validation | Owner follow up and approve target 2 per week | EL/HZ |  | 2020-10-23 | Yes | Wk of 28Sep is delayed due to BSM issue | Venture
|  | Eugent continue last 3 station IQR | EL | 2020-11-02 | 2020-11-09 | No | On track to complete by 13 Nov
|  | Complete with approval | EL | 2020-11-02 | 2020-11-16 | No | Eguene has completed IQ; Pedning for KC approval due to KC availability;
|  | Eugent will follow up with KC for last 3 stations IQR | EL | 2020-11-02 | 2020-11-18 | Yes | Close
16 | Premier preparation | Training cert to be issued | EL/HZ | 2020-11-16 | 2020-11-17 | Yes | Close | Venture
5 | PMS Station condition | Owner check on condition and document evidence | HZ |  | 2020-09-30 | Yes
|  | Flex to update how to save and retrieve measurement data; | HZ |  | 2020-10-30 | Yes | No able to print; Failing test during verifying
|  | Flex to send out document; Ship out from Flex to WPPL on 10 Nov | HZ | 2020-11-02 | 2020-11-13 | Yes | Flex to fix the tubing leaking issue and send to WPPL by 13 Nov -- Fixed;
|  | Set up in WPPL | HZ | 2020-11-16 | 2020-11-27 | Yes | Done