## Flex
Items S/N | Action items description | Next course of action | Owner | Start Date | Target closure | Completion (Yes/ No) | Remark
1 | Loss Comm | Flex to submit evaluation form and get approval from WPPL | HZ |  | 2020-09-25 | Yes
|  | TE-8 direct LAN cable to run; Flex to update FPY; Fixed TE-13 port and continue evaluation and update FPY; | HZ | 2020-11-02 | 2020-11-11 |  | update project status to include Oct data; Split Direct/Normal data for TE-8
2 | Flex to provide weekly update status on Even loading | Owner follow up | HZ |  | 2020-10-30 | Yes | HZ and Flex to even out loading
|  | Flex update loading per sigmasure monthly | HZ | 2020-11-02 | 2020-11-11 |  | Flex to update with data
3 | SDS tester validation | Owner follow up and approve target 2 per week | EL/HZ |  | 2020-10-23 | Yes | Wk of 28Sep is delayed due to BSM issue
|  | Eugent continue last 3 station IQR | EL | 2020-11-02 | 2020-11-09 | No | On track to complete by 13 Nov
|  | Complete with approval | EL |  | 2020-11-16
4 | BSM/QSM first pass yield improvement | Interface tubing update/ Waste line check; | HZ |  | 2020-10-23 | Yes | No impact on yield improvement and close
|  | 2 months monitoring on yield improvement | HZ | 2020-11-02 | 2020-12-31
5 | PMS Station condition | Owner check on condition and document evidence | HZ |  | 2020-09-30 | Yes
|  | Flex to update how to save and retrieve measurement data; | HZ |  | 2020-10-30 | Yes | No able to print; Failing test during verifying
|  | Flex to send out document; Ship out from Flex to WPPL on 10 Nov | HZ | 2020-11-02 | 2020-11-13 |  | Flex to fix the tubing leaking issue and send to WPPL by 13 Nov -- Fixed;
6 | Golden Unit list | Owner to discuss with Edwin on scrap disposition | HZ |  | 2020-10-09 | Yes | Discussed
|  | Flex to update the latest list | HZ |  | 2020-10-14 | No | Flex to update list
|  | Flex to update list with summary of EOL status/althernate test bench | HZ | 2020-11-02 | 2020-11-11 |  | Flex to send out summary
8 | HDD backup | Flex to update by 14.Oct | HZ |  | 2020-11-09 | Yes
|  | Matt to update spare availablity and cost breakdown for 2 testers TE 82519 and TE 82973 - 1 |  | 2020-11-02 | 2020-11-25 | Yes | Flex sent out comfirmation
9 | OESR for keithley 236 | Owner to escalate to Joel to update status | HZ |  | 2020-09-30 | No | Bernard updated status on 16 Oct but not addressed the concerns;
|  | Get Phani to address concerns | HZ | 2020-11-02 | 2020-11-06 | Yes | Email was sent to Joel/Phani to get update from Senai
|  | Flex to look into actual failure and fix it | HZ | 2020-11-18
13 | Evaluation of Alliance firmware | Flex to run evaluation per plan on 14.oct and review the results for anomalies | HZ |  | 2020-10-16 | Yes
14 | TSP 735001613 to study for inclusion of energy reading to mentioned at System Initialization test. | Flex to update comparison data before/after briefing this acitivity to production and review process if ASP/TSP update is required | HZ | 2020-11-02 | 2020-11-13 |  | Flex to update with benefit from this briefing
15 | EVENT LOG | Flex to set up ELI | EL | 2020-11-02 | 2020-11-06 |  | Eugene to update

## Venture
Items S/N | Action items description | Next course of action | Owner | Start Date | Target closure | Completion (Yes/ No) | Remark
1 | BSM Package | ECRO in creation stage | GY | 2020-11-02 | 2020-11-30 |  | Drafting in progress
2 | SDS tester validation | Owner follow up and approve target 2 per week | EC/YH |  | 2020-10-16 | Yes | 1st week validation completed per plan
3 | QSM testers flowrate accuracy | 1st batch collected 20% fallout; 2nd batch of 15 data collection in progress | HZ |  | 2020-10-31 | Yes | Venture collecting data; Result shows FPY of TE-1 improved from 20% to 12.5%; Overall FPY is 67 %, one of best working station.
|  | Put under monitoring of yield; Venture to update No.of units under monitoring | HZ | 2020-11-02 | 2020-12-31 |  | Venture to put this evaluation into an evalution form; Evaluation form under reviewing by teo now.
4 | PREMIER validation | 1. Matt: CMA and CHA software update 2. Eric: FLR software/TSP update* | EC |  | 2020-10-16 | Yes | Can enquire with Chan
5 | GTS 3 Fail* | Self test fixture still has issue: to get Venture for update | HZ |  | 2020-10-16 | Yes | Due for calibration by Mar 2021; needs to prioritise;
|  | Matt will take the self-test fixture for repair; Venture to ship this tester out for repair. | HZ | 2020-11-02 | 2020-11-13 | Yes
6
7
8
9
10
11
12

## CEI
Items S/N | Action items description | Next course of action | Owner | Start Date | Target closure | Completion (Yes/ No) | Remark
1 | OESR S204297 for TCM/PCM backup PC | To receive shipping information of the backup PC from Milford (Matt) | HZ | 2020-11-02 | 2020-12-31 |  | Owner to track update
2
3
4
5
6
7
8
9
10
11
12

## Others
Items S/N | Action items description | Owner | Start Date | Target closure | Completion (Yes/ No) | Remark
1
2
3
4
5
6
7
8
9
10
11
12

## close
Items S/N | Action items description | Next course of action | Owner | Start Date | Target closure | Completion (Yes/ No) | Remark
7 | EvalS20025 Optice Bench from GVT | Owner follow up with Aldwin on evaluation status | DA |  | 2020-10-30 | Yes
10 | OESR for pumptray tester repair | Tester still restarting; Mark to advise again by 16.Oct | HZ |  | 2020-09-30 | Yes
11 | OESR for Small Shunt | Owner to get Joel to advise solution and close OESR. | HZ |  | 2020-09-30 | Yes | Joel to continue using existing; HZ to raise CEA by 16.Oct for spares
12 | OESR for Aperture alignment station | Owner to check with Joel if can be closed | HZ |  | 2020-09-30 | Yes | Tester already repaired, 210001164 for effectiveness check done