## Flex
Items S/N | Action items description | Next course of action | Owner | Target closure | Completion (Yes/ No) | Remark
1 | Loss Comm | Flex to submit evaluation form and get approval from WPPL | HZ | 2020-09-25 | Yes
2 | Flex to provide weekly update status | Owner follow up | HZ | 2020-10-30 |  | HZ and Flex to even out loading
3 | SDS tester validation | Owner follow up and approve target 2 per week | EL/HZ | 2020-10-23 |  | Wk of 28Sep is delayed due to BSM issue
4 | BSM/QSM first pass yield improvement | Interface tubing update/ Waste line check | HZ | 2020-10-23 |  | Ongoing
5 | PMS Station condition | Owner check on condition and document evidence | HZ | 2020-09-30 | Yes
| PMS Station condition | Flex to update how to save and retrieve measurement data | HZ | 2020-10-30
6 | Golden Unit list | Owner to discuss with Edwin on scrap disposition | HZ | 2020-10-09 | Yes
| Golden Unit list | Flex to update the latest list | HZ | 2020-10-14
7 | EvalS20025 Optice Bench from GVT | Owner follow up with Aldwin on evaluation status | DA | 2020-10-30 | Yes
8 | HDD backup | Flex to update by 14.Oct | HZ | 2020-11-09
9 | OESR for keithley 236 | Owner to escalate to Joel to update status | HZ | 2020-09-30 | No
10 | OESR for pumptray tester repair | Tester still restarting; Mark to advise again by 16.Oct | HZ | 2020-09-30 | No
11 | OESR for Small Shunt | Owner to get Joel to advise solution and close OESR. | HZ | 2020-09-30 | Yes | Joel to continue using existing; HZ to raise CEA by 16.Oct for spares
12 | OESR for Aperture alignment station | Owner to check with Joel if can be closed | HZ | 2020-09-30 | Yes | Tester already repaired, 210001164 for effectiveness check done
13 | Evaluation of Alliance firmware | Flex to run evaluation per plan on 14.oct and review the results for anomalies | HZ | 2020-10-16

## Venture
Items S/N | Action items description | Next course of action | Owner | Target closure | Completion (Yes/ No) | Remark
1 | BSM Package | ECRO in creation stage | GY | 2020-11-30
2 | SDS tester validation | Owner follow up and approve target 2 per week | EC/YH | 2020-10-16 |  | 1st week validation completed per plan
3 | QSM testers flowrate accuracy | 1st batch collected 20% fallout; 2nd batch of 15 data collection in progress | HZ | 2020-10-31 |  | Venture collecting data
4 | PREMIER validation | 1. Matt: CMA and CHA software update 2. Eric: FLR software/TSP update* | EC | 2020-10-16 |  | Can enquire with Chan
5 | GTS 3 Fail* | Self test fixture still has issue: to get Venture for update | HZ | 2020-10-16 |  | Due for calibration by Mar 2021; needs to prioritise
6
7
8
9
10
11
12

## CEI
Items S/N | Action items description | Next course of action | Owner | Target closure | Completion (Yes/ No) | Remark
1 | OESR S204297 for TCM/PCM backup PC | To receive shipping information of the backup PC from Milford (Matt) | HZ | 2020-12-31 |  | Owner to track update
2
3
4
5
6
7
8
9
10
11
12

## Others
Items S/N | Action items description | Owner | Target closure | Completion (Yes/ No) | Remark
1
2
3
4
5
6
7
8
9
10
11
12