## Flex
Items S/N | Action items description | Next course of action | Owner | Start Date | Target closure | Completion (Yes/ No) | Remark
1 | Loss Comm | Flex to submit evaluation form and get approval from WPPL | HZ |  | 2020-09-25 | Yes
|  | TE-8 direct LAN cable to run; Flex to update FPY; Fixed TE-13 port and continue evaluation and update FPY; | HZ | 2020-11-02 | 2020-11-11 | No | update project status to include Oct data; Split Direct/Normal data for TE-8
|  | Flex to send out project status with data；Split Direct/Normal data for TE-8 | HZ | 2020-11-02 | 2020-11-18
2 | Flex to provide weekly update status on Even loading | Owner follow up | HZ |  | 2020-10-30 | Yes | HZ and Flex to even out loading
|  | Flex update loading per sigmasure monthly | HZ | 2020-11-02 | 2020-11-11 | No | Flex to update with data
|  | Flex to update with sigmasure data | HZ | 2020-11-02 | 2020-11-18
3 | SDS tester validation | Owner follow up and approve target 2 per week | EL/HZ |  | 2020-10-23 | Yes | Wk of 28Sep is delayed due to BSM issue
|  | Eugent continue last 3 station IQR | EL | 2020-11-02 | 2020-11-09 | No | On track to complete by 13 Nov
|  | Complete with approval | EL | 2020-11-02 | 2020-11-16 | No | Eguene has completed IQ; Pedning for KC approval due to KC availability;
|  | Eugent will follow up with KC for last 3 stations IQR | EL | 2020-11-02 | 2020-11-18
4 | BSM/QSM first pass yield improvement | Interface tubing update/ Waste line check; | HZ |  | 2020-10-23 | Yes | No impact on yield improvement and close
|  | 2 months monitoring on yield improvement | HZ | 2020-11-02 | 2020-12-31
5 | PMS Station condition | Owner check on condition and document evidence | HZ |  | 2020-09-30 | Yes
|  | Flex to update how to save and retrieve measurement data; | HZ |  | 2020-10-30 | Yes | No able to print; Failing test during verifying
|  | Flex to send out document; Ship out from Flex to WPPL on 10 Nov | HZ | 2020-11-02 | 2020-11-13 | Yes | Flex to fix the tubing leaking issue and send to WPPL by 13 Nov -- Fixed;
|  | Set up in WPPL | HZ | 2020-11-16 | 2020-11-27
6 | Golden Unit list | Owner to discuss with Edwin on scrap disposition | HZ |  | 2020-10-09 | Yes | Discussed
|  | Flex to update the latest list | HZ |  | 2020-10-14 | No | Flex to update list
|  | Flex to update list with summary of EOL status/althernate test bench | HZ | 2020-11-02 | 2020-11-11 | No | Flex to send out summary
|  | Flex to update list as per discussion | HZ | 2020-11-02 | 2020-11-18
8 | Spare PC management due to unable to backup | Matt to update spare availablity and cost breakdown for 2 testers TE 82519 and TE 82973 - 1 | HZ | 2020-11-02 | 2020-11-25 | Yes | Updated matt with photo and models
|  | Follow up with Matt on cost breakdown | HZ | 2020-11-16 | 2020-12-11
9 | OESR for keithley 236 | Owner to escalate to Joel to update status | HZ |  | 2020-09-30 | No | Bernard updated status on 16 Oct but not addressed the concerns;
|  | Get Phani to address concerns | HZ | 2020-11-02 | 2020-11-06 | Yes | Email was sent to Joel/Phani to get update from Senai
|  | Flex to look into actual failure and fix it | HZ | 2020-11-02 | 2020-11-18 |  | Flex Senai updated status but didn't make it work on tester
|  | Flex to update complete date -- checking with Amy | HZ | 2020-11-16 | 2020-11-23
14 | TSP 735001613 to study for inclusion of energy reading to mentioned at System Initialization test. | Flex to update comparison data before/after briefing this acitivity to production and review process if ASP/TSP update is required | HZ | 2020-11-02 | 2020-11-13 | No | Flex to update with benefit from this briefing
|  | Flex to update as per discussion | HZ | 2020-11-02 | 2020-11-18
15 | EVENT LOG | Flex to set up ELI | EL | 2020-11-02 | 2020-11-06 | No | Issue encourted during set up
|  | Eguene to follow up to get details of issue encourtered. | El | 2020-11-02 | 2020-11-20
16 | Premier preparation | Training cert to be issued | EL/HZ | 2020-11-16 | 2020-11-17