## Sheet1
Where to use | Criticality | Total Testers | Total testers down | Impact to production | Status of Repair
| Critical testers | 34 | 1 |  | Open
Instrument Level | Sub-Critical testers | 55 | 0 | Low
| Standard testers | 28 | 0
PCB | FCT/ICT testers | 11 | 1
Priority (Impact to Production) | Total OESR | Open OESR | Last Week added OESR | Last Week Closed OESR
1- High(< 1 week) | 28 | 0 | 1 | 0
2- Medium (<4 weeks) | 56 | 6 | 0 | 0
3- Low (> 4 weeks & above) | 23 | 14 | 1 | 1
Grand Total | 108 | 20 | 2 | 1
Priority (Impact to Production) | Total WPPL OESR | Total OESR to Milford | Total Closed OESR | Total Open OESR | Remark
1- High(< 1 week) | 28 | 5 | 5 | 0
2- Medium (<4 weeks) | 56 | 10 | 8 | 2 | 1.[23Nov18] OESR 182936 to request a replacement valve or alternative part. [07Dec18] contacted the local supplier for the valve, wait for quotation 2. [23Nov18] OESR#182935 to request capillary tubings; [07Dec18] Received tubings and start evaluation in Jan 2019
3- Low (> 4 weeks & above) | 23 | 7 | 3 | 4 | 1. OESR 182626 to fix missing serial number issue. [19Oct18] Ed update: Made a Test Program code modification on the TE Lab PC and is under evaluation. 2. OESR 182633 to investigate the seal force failure rate issue. [17Dec18] R&D is looking to this case as shared last week. 3. OESR 171993 to fix the E cord interface issue; [ 24Sep18] The tester is under evalation. 4. OESR: 182975 to request spare parts for old 515 pump testers and wait for Milford to advise if they have spare for the parts identified as ciritial.
Grand Total | 108 | 22 | 16 | 6