## Sheet1
Log Number | Engineering Group | ASP TSP No | Date | TE Tool No | Originator | STATUS | Date Completed | Problem Summary | Summary | Assignee 1 | Assignee 2
161145 | Manufacturing Engineering | NA | 2016-10-12 | 999119905 | Desmond Ann | OPEN |  | Flex feedback that the fixture 999119905 is having a different press. It is using 99901154 instead of 999041264. The physical fixture do not have item 2, 5, 8,9,11 as stated in the 999119905 fixture drawing. Drawing for 999041250 is different from the physical part. Please see attached for details. | Nov 30, 2016: Correction is being made to the drawing two versions of the same part. Singapore uses a pneumatic press vs Milford Waters is a manual press. Tool qualification is not required documentation only. June 28, 2017: Both Singapore and Milford have MANUAL press, and Singapore has the latest version of the press due to cost saving changes per Steve. If the marked-up print was already provided to Steve to show the difference of the physical press in Singapore versus SAP drawing, Steve should help looking into updating the drawing to reflect the latest version. June 03, 2019: Pending Steve to update. | Stephen Wright
161186 | Test Engineering | N/A | 2016-10-26 | N/A | Desmond Ann | OPEN |  | "CEA 16009" is to build the Universal Coarse and Fine Align Station for PDA optics benches. | May 30, 2017: Model shop will cut the chasis for control box in first week of June. Chau continues putting the fixtures together. Chau to check with Eric about effect of the new PDA chip on these two universal testers. June 27, 2017: Model Shop just complete two sheetmetal boxes today to be picked up for the Universal Fine Alignement Fixture. Eric confirms that no effect of new PDA chip on these two universal testers. July 27, 2017: Works in progress. Sep 26, 2017: Plan to ship at end of month so Eric can set it up at Flex. (A few alignment tools might be shipped later on.) Oct 24, 2017: Shipped and being set up at Flex. Building Target Cell, Aperture. Mar 6, 2018: Flex has all parts short of the 2998 target. Oct 26, 2018: Waiting for WPPL to work on capital to build 1 or 2 control boxes. Dec 18, 2018: Edwin already replied on 2Dec18 that it is ok to utilize the budget for the CEA. Waiting for clarification from WPPL to know which budget to use and to build 1 or 2 control boxes. June 03, 2019: CEA# WPPL19002 for 2 control box. Pending Milford to Fabricate box. ASK ERIC FOR COMPLETION DATE. | Eric Turner | Chau Nguyen | Pending Milford to update
171657 | Test Engineering | 735000445 | 2017-04-20 | TE82723 | Edwin Koh | OPEN |  | During product audit, it found that the operator cannot execute to TSP procedure 735000445 on per section 3.0 without completing additional step of Water DHCP download. Understand this additional step is necessary previously due to PC failure and it a temporary fix to access the program for testing. Action options 1. If arrangement is permanent, can TSP procedure 735000445 to be revised 2. Can Test Engineer update the TE82723 to link this additional step back into the standard program. Preferred option 2 if possible. Attached is the supporting information on the additional step and document mark-up. | June 28, 2017: This is a TSP change anybody can do, but will need spec alignment - low volume, low priority. If categorize it as an OFI, an timeline for completion should be provided. | Eric Turner
171694 | Test Engineering | NA | 2017-04-27 | N/A | Yeap Siew Yee | OPEN |  | Files pending in the 'sendbuffer' folders yet to be sent out. Affected testers as below: 1) TE83013 (HTCH tester) 2) TE83013-2 (HTCH tester) 3) TE83026-1 (CM tester) 4) TE83026-2 (CM tester) | June 27, 2017: Both of these to be fixed with test software upgrade for SIgmasure, TE83026 is first followed by TE83013. 27-JUL-2017: this will be corrected during up-commoing software revision for Camstar. Sept 26, 2017: Work has started on an update to TE83013, TE83026 is next. 23-JAN-2018 Hope to get time in February to get this moving 30 JAN 2018 Working on TE83013, complete update (win 10, SIgmasure 7, fix OESRs etc) 27-FEB-2018 Actively working on this, Test running working on EDV and bugs as they are found 24-APR-2018 TE83013-EDV drafted, code complete, all hardware delivered, working on PC config, build, validation. TE83026 will be started soon 20, AUG 2018, Fixing Ecord test bug, one duplicate tester built. 27-FEB-2019 Hope to get time to get this going in 2019 May 2019: Still at same status, second on project priority list | Matt Brule
171714 | Test Engineering | WAT242102 | 2017-05-05 | N/A | Yeap Siew Yee | OPEN |  | Proposed to update TSP Doc No: WAT242102 Rev 4 1) To include Waters PN 279003385, 279002592, 279003250 on the cover sheet | June 27, 2017: Have not looked into this one yet, should not be an issue, except specification alignment will take time. 27-JUL-2017: Have not looked into yet, will require specification alignment 20, AUG 2018 No action taken yet 29-Nov-2018 No Change 17-DEC-2018 No Change 27-FEB-2019 No Change July 02, 2019: WPPL : Matt reply in May 2019, Procedure update, low priority, no change, requires specification alignment | Matt Brule
171993 | Test Engineering | 735002064 | 2017-08-25 | TE83013 | Yeap Siew Yee | OPEN |  | TE83013-1 is observed to experience a test sequence error at "Ecord Interface Test" by skipping to instruct to connect "Ecord" to the UUT while testing for 186015042. They have recently changed the tester PCBA P/N:210000367 (ASSY PCB CPSM CONTROLPCB) Rev H because existing P/N:210000367 Rev G was faulty on 14-Aug-2017. Refer to videos for failure occurrence. | 25-SEP-2017: In progress. 30-JAN-2018 Actively working on this 27-FEB-2018 working on bug fixes and EDV 24-APR-2018 TE83013-EDV drafted, code complete, all hardware delivered, working on PC config, build, validation. 25, June 2018 Emailed Desmond this AM with proposed upgrade plan 20, AUG 2018 working on Ecord bug. 24-Nov-2018 Working on bug as time allows expect resolution soon, working to prove theory about Ecord formatting 17 DEC 2018 Same status (Pending Matt Brule.) 23-FEB-2019, expect to get freed up to complete this soon July 02, 2019: Matt reply in May 2019, First on his project priority list | Matt Brule
172012 | Manufacturing Engineering | N/A | 2017-09-01 | N/A | Chau Nguyen | OPEN |  | Work with Chau on Target Cells and other required tools and associated drawings to complete and transfer the two fixtures to WPPL by Mid-October 2017 . | Need a list of the targets SW......... not enough info provided ......Oct 2017. SW Oct 26, 2018: Chau will sort through components on hand to build spares. June 03, 2019: Universal Coarse Fine Alignment station pending Milford to fabricate. June 17, 2019: Universal Coarse Fine Alignment station already built and shipped. This request is to document the process to make Target Cells and other required tools to build spares when required. If there is enough materials on hands and available to build any target, it would be built if required. Chau Nguyen. June 17, 2019: WPPL: Milford to advise more details on what is required for this OESR. These will be required when 2 control boxes completed. Request for completion date of 2 control boxes from Eric to provide to Finance in WPPL. | Stephen Wright | Chau Nguyen
182626 | Test Engineering | N/A | 2018-06-27 | TE82943 | Desmond Ann | OPEN |  | Missing serial number at the bottom of the test report (Ser.No) of Acquity BSM 18K PLUS and Acquity Arc QSM test in some Test record and it is encountered across all test stations TE82943 #1,#19,#20,#21,#22 and #24. Please kindly refer to the examples "BSM Test Record.JPG" and "QSM Test Record.JPG". Do help to resolve the issue. | Oct 2018: Made a Test Program code modification on the TE Lab PC and is under evaluation. 17Dec1: Check with Venture to see if this is resolved. 29Jan2019: It has not been resolved and still require support to solve the issue. 29-Jan-2019: A fix for this intermittent condition has been added to the latest test programs. It was going to be released along with Firebrick firmware in January. However, Firebrick firmware is now being rolled up into Gold firmware. So now it will be released in April with the Gold firmware release. Feb: same status. Apr23: same status. expecting release soon. July 02, 2019: WPPL: Validation in progress. | Edward Jackson
182922 | Manufacturing Engineering | N/A | 2018-11-16 | N/A | Cheah Su Fern | OPEN |  | There are few errors found on the Part Drawing for Belt Tightening Fixture 999038298. Details will be attached in the email. | It looks like maybe a repair was made in Singapore by the CM that needs addressing. Area of concern is clearance only Desmond requested a print change to open up tolerance for concerns of an audit. June 03, 2019: Pending Steve to update the drawings. Drawing in Concept status. July 02, 2019: WPPL : Pending Steve to update | Stephen Wright
193124 | Test Engineering | N/A | 2019-02-14 | TE82526 | Chan Yee Hwa | OPEN |  | Request additional Pump Tray Tester TE82526 to support Alliance Production for high demand. The tester is currently running at 92% capacity; Besides, we also see high chance of tester break down according to past years data. Please provide the cost for WPPL to raise CEA. Thanks. | June 03, 2019: Mark has begun looking at this, and is reviewing best path forward regarding component and PC obsolescence. CEA# WPPL19003 Updated CAD file with new bracket and bracket was added manual parts list S.W. Sept. 5 Fluidic diagram needs to be updated per change. | Mark Jussaume | Mike Aubin
193148 | Test Engineering | 735000615 | 2019-02-25 | TE82760 | Luo HuaZhen | OPEN |  | During meeting with Venture for First Pass Yield (FPY), the FLR detector yield was 3 consecutive months lower than target yield (97% for UPLC detector and 90% for 2475 detector). The venture feedback they're seeing Signal to Noise Ratio failure increased, it's the top failure after Raman/Rayleigh failure. The units are failed the 1st test with readings approximately zero (~0.00) and the 2nd test (retest) passed with over thousands (>1000). 55.56% of Signal/Noise Ratio failure are failed with readings nearly to "zero". And we tried to use Diagnostic on test program to troubleshoot this failure, but it's always blanked out. Could you please kindly help to check this issue and advise the possible root cause? Thanks | July 02, 2019: WPPL: It is under monitoring while waiting for Eric to enable to diagnostic feature. | Matt Franklin | Eric Turner
193244 | Test Engineering | WAT271129 | 2019-04-04 | 186000139 | Luo HuaZhen | OPEN |  | Flex Singapore feedback this Alliance Final Test workstation 3 has frequently hanging issue. They request to replace this workstation with a windows 7 workstation. Can you please help to access if this PC hang issue can be fixed? or have to replace the workstation? If replacing workstation, can you please advise the spec of workstation for Alliance Final Tester? Thanks. Below is message from Flex, 1. Problem Statement : Alliance Final Test Station 3 having frequent hang during Final Test execution . Refer to attached file. 2. Acceptance Criteria Not Met: The test station must be able to execute Final Tester of 4 units simultaneously without system hang during test . Not able to complete test an need to restart the CPU leaving down station 3. Info on whether this issue impacts revenue : No impact yet to revenue but sure one day will hit when the numbers are up. This is to prepare for upsize of Alliance. | July 02, 2019: WPPL : Matt reply that he is working on it. | Matt Brule
193266 | Test Engineering | N/A | 2019-04-12 | N/A | Chan Yee Hwa | OPEN |  | Would like to request for new shunts to support detector production test capacity at Flex Sg. We'll need below shunt with programmed chips. Thanks. i. 289002450 -- TUV Shunt ; 3 Ea. ii. 289002227 -- PDA Small Shunt; 1 Ea. iii. 289002226 -- PDA Medium Shunt; 3 Ea. | Request for CEA from WPPL to place actual order in SAP to determine which components available and which to be sourced to complete building these shunts. June 03, 2019: YH to raise PO for Shunts. July 02, 2019: WPPL : Pending for WPPL to raise CEA (and or PO?) to enter order. | Eric Turner | Chau Nguyen
193267 | Test Engineering | 735001613 | 2019-04-15 | TE82882 | Luo HuaZhen | OPEN |  | New ECO is required Flex Singapore to supply 2 new spare Part Number 700012245 and 700012243. Please kindly help to review/update the TSP 735001613 to support new part number 700012245 and 700012243 test. Below is request sent by Flex, FYI 1. Problem Statement. - TE82882 PDA Final Test and TSP 735001613 Rev W does not have Spare OB PN 700012245 - Optics Bench, eLambda (On-Semi) and 700012243 - Assy, Optics Bench, 2998 (On-Semi) 2. Acceptance criteria that is not met. (e.g. relevant specification number and revision) - TE82882 PDA Final Test and TSP 735001613 Rev W must have to support Production run of the 2x Spare OB. 3. Relevant records (e.g. Incomin QA, Test Records, Photos, trackise NCRs numbers and related issue) - Relevant PDA Family Test Report for Spare Optic Bench have dedicated PN on the test station and TSP. 4. Info on whether this issue impacts revenue. - This impact the spare bench testing. | July 02, 2019: WPPL : Validation in progress. | Eric Turner
193349 | Test Engineering | 735001645 | 2019-05-17 | TE82956 | Luo HuaZhen | OPEN |  | TE82956-2 failed test with high ambient temp (130 deg.C). Could it be this Thermistor faulty? What is PN of this Thermistor? Please kindly send us a repair part if you think it's a thermitor faulty too and you have a spare of thermistor. Thank you. Below is message from Venture, FYI TE82956-2 cannot perform "Column Heater Test" due to Thermistor Error. During initializing of the test, Ambient Temp is shown as 130 (Deg.C) instead of ambient temperature. Please refers to attached screenshorts for reference. We have performed as below. 1) Checked all cable connections between tester & UUT and PC & Tester. No issue found. 2) Checked cables connection inside of tester.No issue found. 3) Shut Down and restart PC.Then,retested. Still having same failure. 4) Tried to test using (x3) differnet UUTs and still having same failure. Request the help on this tester issue. | July 02, 2019: WPPL : Verification in progress in Venture. | Tony Fontes
193373 | Test Engineering | 735000698 | 2019-05-29 | TE82774 | Edward Jackson | OPEN |  | IQ has not been preformed on assemblies to be tested on this tester. Please perform all validations required. See Emma Pierce in Milford if there are any validation questions or concerns. Thank you. | July 02, 2019: WPPL: Pending execution of IQ. Aug 27,2019: WPPL: YeeHwa was assigned to execute this IQ, Estimate to be completed on 30 Aug | Yeehwa Chan
193382 | Test Engineering | N/A | 2019-06-06 | TE82743 | Luo HuaZhen | OPEN |  | Venture is running QDA production too. Some of testers are using dynamic IP address and those testers are sharing the same network with Milford testers. Therefore it can cause IP address conflict, while tester from Milford is power off and the tester from QDA production is assigned a same IP address by server. Can Milford assign a range of IP address for QDA testers? I will work with local team/Waters UK to check if they can assign a fixed IP address within this range for each of testers for QDA production. So we can avoid the same issue happening again. | July 02, 2019: WPPL: Milford to advise the range of IP address to use for UK equipments. This is urgent to get IP conflicts resolved for CM Production. | Matt Brule
193411 | Test Engineering | N/A | 2019-06-24 | TE82760 | Luo HuaZhen | OPEN |  | New FLR Detector tester (Win7) don’t get the Factory Order and TMD # on new test report template and the new template format is slightly different from xp template although the same parameters were tested. To standardize the report, we need Milford help to update the report templates to the same format as the one on the old testers(WinXP). Please refer to page 2 for details of differences on 2 report templates. | July 02, 2019: WPPL : Pending Eric to update. | Eric Turner
193413 | Test Engineering | 735000615 | 2019-06-24 | TE82760 | Luo HuaZhen | OPEN |  | TSP735000615 Rev P, page 8 of 9, the TSP is missing a step during keypad test after passing the functional test . For 2475 mode, we need to set the date for the lamp installed. Press “DIAG”, “7” ,” 1” as per red line TSP attached at page 2 of this OESR Please review this step and update the TSP if necessary. Thanks | July 02, 2019: WPPL : Pending for Milford to update TSP. | Eric Turner
193421 | Test Engineering | 735001613 | 2019-06-27 | TE82882 | Luo HuaZhen | OPEN |  | Flex report that this TE82882-10 have loss communication issue, all position 1-4 affected. Test program cannot proceed to Noise Test and Drift Test, especially eLamda. The UUT can be connected in initial test, but failing subsequent looping and show it's loss communication in failing test report. Tester qualification is not able to proceed to other model (eg 700012245) due to loss communication during test.A test report is attached on page 2 of this OESR. Flex will connect a UUT on TE82882-10 port 4 for troubleshooting tonight. Please kindly check and advise a solution for this lost communication issue. Thank you. |  | Eric Turner
193436 | Test Engineering | N/A | 2019-07-16 | TE82988 | Luo HuaZhen | OPEN |  | Flex Malaysia did onsite calibration by following GTS PM/Calibration Procedure yesterday. But they found the GTS is failing the self test and power supply 2 voltage 30v above is slight out of the calibration range. We asked Flex to collect a spare calibrated power supply 2 from WPPL to recover this GTS, and need your help to repair on this self test failing issue. We may ask Flex to standby for this self test repair tonight if you can remote GTS. Please kindly advise if this PS2 30v above may affect any test fixtures in Flex and kindly let us know how to fix this self test failing issue. Flex did known good board test on all their test fixtures and all tests are pass before/after calibration. Please kindly advise if they can test result as an alternate verification since GTS is failing self test. Thank you | MB 28 AUG 2019 - Issues to date: One power supply needed to be swapped out for calibration One load module was not working correctly under load and has been swapped out. Numerous relay failures, many of which work after some exercising Relay still has unresolved failure that is being troubleshot. System is functioning adequately to test PCBs | Matt Brule
193459 | Test Engineering | 735002010 | 2019-07-29 | TE82943 | Luo HuaZhen | OPEN |  | Since last year, we were facing multiple(4 times) BSM/QSM tester breakdown due the weighing balance faulty in Flextronics. Each time it will take around 3 months to get the weighing balance repaired in Japan due to lack of repair parts in ITS Singapore (AnD local representative). The repair turnaround time is very long and costly (around USD1500 for each repair). So we checked with ITS again recently regarding supportability of this HR200 model. They sent us a product discontinuation letter and its successor model GR-200 info as attached Can we replace the current old HR-200 weighing balance with its successor mode GR-200 since these HR200 are frequently breaking down? If can, how can we proceed with this replacement? Or do you have any other better solution for HR200 support? Please refer to GR200 user manual and discontinuation letter in Pg2 & 3. Thank you | 21-Aug-2019: A discussion took place between Jaaffar Ismail, Matt Brule, and Ed Jackson. We decided to first pursue a direction of maintaining the HR-200 balances. We will ask Paul Deschenes next week if he can identify any spare balances throughout the building that we may be able to use to support the TE82943 testers. The long term solution, at least a year away, is to replace the TE82943 testers with a new design that will eliminate the balances by replacing them with flow meters. Ed J.. | Edward Jackson | Paul Deschenes
193460 | Test Engineering | N/A | 2019-07-29 | TE82475 | Luo HuaZhen | OPEN |  | Based on tester utilization calculation, this pressure decay tester in Flex has been used up 91.56% of total tester capacity. So we plan to buy another TE82475 tester by raising CEA. Please kindly advise the total price and estimated complete date to build this tester. Thank you Tester utilization data, FYI Tester Utilization based on Q1 & Q2’20 numbers: Prime is 79.3% Prime + Spares is 91.56% Q3 & Q4’19 numbers: Prime is 78.2% Prime + Spares is 91.5% |  | Mark Jussaume
193482 | Manufacturing Engineering | N/A | 2019-08-02 | TE83064 | Mike Cotter | OPEN |  | Please provide the dates/date codes of inject valves currently being installed in I-Class FTN sample managers (186015088). This is to help understand the speed of material throughout the entire process. (this is part of the same project as OESR 193310) Thanks, Mike |  | Desmond Ann | Luo Hua Zhen
193535 | Manufacturing Engineering | n/a | 2019-08-26 | 999120000 | Cheah Su Fern | OPEN |  | Concentric circle (999043026) that used in tooling 999120000 was found cracked due to wear and tear. (Photo is attached in email) Request Steve Wright to provide spare. | Working with WPPL to find replacement parts. This is a good exercise for WPPL to use the released documentation for replacement parts. SW | Stephen Wright
193545 | Manufacturing Engineering | n/a | 2019-08-28 | 999026619 | Cheah Su Fern | OPEN |  | Alignment target (999026619) was found cracked, suspect due to impact. Please see attached photo. We would like to request Steve to provide spare for 999026619. | Working with WPPL to find replacement parts. This is a good exercise for WPPL to use the released documentation for replacement parts. SW | Stephen Wright
193550 | Test Engineering | 735001613 | 2019-09-02 | TE82882 | Luo HuaZhen | OPEN |  | Flex feedback they have issue to test spare PN 700011652 on PDA test station. They suspect UPDOB2 needs to be changed to UPDOB3. Please kindly help to change this configuration to enable spare part 700011652 test or advise if Flex can change this to fix the issue. Please advise if validation is required 1. Problem Statement. -PDA Final Test System TE82882-8,9,10,11,13, and 14 have missing Spare OB PN 700011652. 2. Acceptance criteria that is not met. (e.g. relevant specification number and revision) - All PDA Final Test System TE82882-8,9,10,11,13 and 14 shall have Spare PB PN 7000011652 3. Relevant records (e.g. Incomin QA, Test Records, Photos, trackise NCRs numbers and related issue) - N/A 4. Info on whether this issue impacts revenue - Impact 1x unit of shipment for Spare OB. |  | Matt Franklin | Eric Turner
193551 | Test Engineering | 735002011 | 2019-09-02 | TE83032 | Luo HuaZhen | OPEN |  | The existing optics bench alignment stations are using a Golden flow cell to align all the optics benches. The flow cell used to align 5029 FLR optics benches had been using since year 2013 product transferred period and it had never been replaced. Venture observed the white colour residue on the glass window of the flow cell and it can not be removed although it was purging/priming through with MeOH for long hours. Refer to attached slide. Venture should have one back up golden flow cell in any case of flow cell degrading over a few years of usage and also for not interrupting production line while it waiting Milford to send over new Golden flow cell. |  | Eric Turner | Matt Franklin
193552 | Test Engineering | 73500615 | 2019-09-02 | TE82760 | Luo HuaZhen | OPEN |  | On the month of Jul, Venture production found some Ram-Ray Valley Energy failures during FLR detectors final test for 5029 models. The UUTs were passed when they swapped with new flow cells. The failed flow cells were used in another UUTs and passed the test. Refer to attached slides for failure details. Raised OESR to follow up and get some advices from WPPL/Milford Engineering to look into the possible root causes of this failure. |  | Eric Turner | Matt Franklin
193563 | Test Engineering | 735001613 | 2019-09-06 | TE82969 | Luo HuaZhen | OPEN |  | Flex feedback the latest PDA Final test TSP 735001613 Rev Y has part numbers which is listed in the other TSP 735002531. This will create confusion. Please remove the duplicate numbers per attached redline TSP and also some other updates shown in the table. |  | Eric Turner | Matt Brule
193577 | Test Engineering | N/A | 2019-09-11 | TE82743 | Luo HuaZhen | OPEN |  | The PC of the Racal FCT tester not able to power on. Venture has verified the PC offline but they are encountered the same thing. Please kindly help to check and advise if you have spare PC for replacement because currently Venture has production board W12100033120 for testing. The PC not able to power when turning on. Suspected that the PC Mother board get faulty PC Model: IPC-610MB-300 Manufacturer: Advantech OS: Windows 2000 Ram: 2 GB |  | Bill Bates | Luo Hua Zhen
193590 | Test Engineering | N/A | 2019-09-18 | TE82865 | Luo HuaZhen | OPEN |  | Tester TE82865-5 unable to download firmware and it shows on the note as Invalid Ethernet address. Checked there was a pass record on 8 Mar 2018 it happened on this tester too. It was that the Ethernet address was full which cause to show this error. No production impact for now. Please refer to attached picture for error message. Please kindly teach us how to fix this kind of reoccurring issue. So that we can do first level troubleshooting in the future. Thanks
193593 | Test Engineering | N/A | 2019-09-18 | TE82865 | Luo HuaZhen | OPEN |  | CEI was performing PC maintenance found at "Step 1.7 Check for unsent test files" in all the 3 tester below. There were number of files in the folder Directory C: \program files\sigmaQuest\sigmaProbe\sigmaQueue\Sendbuffer and C:\program files\sigmaQuest\sigmaProbe\sigmaQueue. Testers found have unsent files as shown below: TE82865-5 CPSO Final Test Station TE82865-6 CPSO Final Test Station TE82865-2 ASO Final Test Station Please kindly teach us the way to clear these files. So that we can avoid the repeating request in the future. Thank you