## Venture
Log Number | Engineering Group | ASP TSP No | TE Tool No | STATUS | Problem Summary | Summary
171657 | Test Engineering | 735000445 | TE82723 | OPEN | During product audit, it found that the operator cannot execute to TSP procedure 735000445 on per section 3.0 without completing additional step of Water DHCP download. Understand this additional step is necessary previously due to PC failure and it a temporary fix to access the program for testing. Action options 1. If arrangement is permanent, can TSP procedure 735000445 to be revised 2. Can Test Engineer update the TE82723 to link this additional step back into the standard program. Preferred option 2 if possible. Attached is the supporting information on the additional step and document mark-up. | June 28, 2017: This is a TSP change anybody can do, but will need spec alignment - low volume, low priority. If categorize it as an OFI, an timeline for completion should be provided. Feb 26, 2020: Low Priority Per Eric
193552 | Test Engineering | 73500615 | TE82760 | OPEN | On the month of Jul, Venture production found some Ram-Ray Valley Energy failures during FLR detectors final test for 5029 models. The UUTs were passed when they swapped with new flow cells. The failed flow cells were used in another UUTs and passed the test. Refer to attached slides for failure details. Raised OESR to follow up and get some advices from WPPL/Milford Engineering to look into the possible root causes of this failure. | 26 Feb 2020: Reassigned to Matt Frankline per Eric and updates seen below: This should no longer be an issue. I remember checking the test data and everything seemed to be back to normal. If they are no longer having this issue this OESR should be closed.

## Flex
Log Number | Engineering Group | ASP TSP No | TE Tool No | STATUS | Problem Summary | Summary
171657 | Test Engineering | 735000445 | TE82723 | OPEN | During product audit, it found that the operator cannot execute to TSP procedure 735000445 on per section 3.0 without completing additional step of Water DHCP download. Understand this additional step is necessary previously due to PC failure and it a temporary fix to access the program for testing. Action options 1. If arrangement is permanent, can TSP procedure 735000445 to be revised 2. Can Test Engineer update the TE82723 to link this additional step back into the standard program. Preferred option 2 if possible. Attached is the supporting information on the additional step and document mark-up. | June 28, 2017: This is a TSP change anybody can do, but will need spec alignment - low volume, low priority. If categorize it as an OFI, an timeline for completion should be provided. Feb 26, 2020: Low Priority Per Eric
171714 | Test Engineering | WAT242102 | N/A | OPEN | Proposed to update TSP Doc No: WAT242102 Rev 4 1) To include Waters PN 279003385, 279002592, 279003250 on the cover sheet | June 27, 2017: Have not looked into this one yet, should not be an issue, except specification alignment will take time. 27-JUL-2017: Have not looked into yet, will require specification alignment 20, AUG 2018 No action taken yet 29-Nov-2018 No Change 17-DEC-2018 No Change 27-FEB-2019 No Change July 02, 2019: WPPL : Matt reply in May 2019, Procedure update, low priority, no change, requires specification alignment Feb 26, 2020: Specification alignment will take time and Low Priority Per Matt
193552 | Test Engineering | 73500615 | TE82760 | OPEN | On the month of Jul, Venture production found some Ram-Ray Valley Energy failures during FLR detectors final test for 5029 models. The UUTs were passed when they swapped with new flow cells. The failed flow cells were used in another UUTs and passed the test. Refer to attached slides for failure details. Raised OESR to follow up and get some advices from WPPL/Milford Engineering to look into the possible root causes of this failure. | 26 Feb 2020: Reassigned to Matt Frankline per Eric and updates seen below: This should no longer be an issue. I remember checking the test data and everything seemed to be back to normal. If they are no longer having this issue this OESR should be closed.
193814 | Test Engineering | 735001613 | TE82882 | OPEN | The final test record for Detector(TE82882-All and TE82969-1) and SDS ( TE82943-All) has incomplete of 'start time' and 'end time' print out. The second of time is disappeared from test record. Please kindly update the final test record template to print out the complete time, including the seconds on test record. Please refer to attachment on page 2 for the details. | This is a known issue with the test record formatting file and will be updated as time is available. 26 Feb 2020: Changed to OFI with no clear date on completion
193244 | Test Engineering | WAT271129 | 186000139 | OPEN | Flex Singapore feedback this Alliance Final Test workstation 3 has frequently hanging issue. They request to replace this workstation with a windows 7 workstation. Can you please help to access if this PC hang issue can be fixed? or have to replace the workstation? If replacing workstation, can you please advise the spec of workstation for Alliance Final Tester? Thanks. Below is message from Flex, 1. Problem Statement : Alliance Final Test Station 3 having frequent hang during Final Test execution . Refer to attached file. 2. Acceptance Criteria Not Met: The test station must be able to execute Final Tester of 4 units simultaneously without system hang during test . Not able to complete test an need to restart the CPU leaving down station 3. Info on whether this issue impacts revenue : No impact yet to revenue but sure one day will hit when the numbers are up. This is to prepare for upsize of Alliance. | July 02, 2019: WPPL : Matt reply that he is working on it. Nov 15, 2019: The frequency of PC freeze sent to Matt. 26 Feb 2020: Matt is working on it and coordinating with HuaZhen