## Flex Senai 2019_2020
Log Number | Engineering Group | OESR Date Received | TE Tool No | Problem Summary | Site | Originator | Assignee 2 (WPPL) | Date Completed | Remark/Closure | OESR to Milford | 1- High(< 1 week) | STATUS | Time for closure (Days)
S190013 | Test Engineering | 2018-11-27 | TE82988-2 | 1. Model 210000384 boards failing at TE82988-2 GTS Tester but when test at 2690 TE 82510 Tester the boards able to passed. Failed Test UUT Power : (GTS TE82988-2) 1.Power Supply Status - Failed 2.Test 3.3V Supply - marginal failure Note : shipment will be at risk . | Flex | ST | HuaZhen |  | [07Dec18] Milford is evaluating if need to change the spec or not [11Jan19] OESR 182950 : 28-Nov-2018: The failure has been assessed. A VAF has been created, reviewed and approved. 29-Nov-2018: An EDV is required, (created, reviewed, approved, executed). Then an EDV Report will need to be created, reviewed and approved. From this point the new test program can be released to production. Current thinking is that we may have these documents in approved at the earliest 03-Dec-2018. [08Feb19] Sent the schematic to Flex and asked them to focus on troubleshooting of 'Test UUT Power' as it's the majority of failures. [14Feb19] Test program was upgraded to version 0.1. Waiting for validation from Milford | Yes | 3- Low (> 4 weeks & above) | Close | 49
S190015 | Test Engineering | 2018-12-05 | TE82534 | SPARE PARTS REQUEST : DESCRIPTION Qty Required: 1. PCBA Controller PN SC2072 ASSY181310-02 National Instruments 1 pc. 2. Waters Pump Conctrol Module - PN not available from Front/Back View 1 pc Note: Above parts not able to source by Flex. Refer to Attach TE 82534 515 Final Tester | Flex | ST | HuaZhen |  | OESR: 182975, shared OESR with above OFI | No | 3- Low (> 4 weeks & above) | Close | 5
S190020 | Test Engineering | 2018-12-26 | TE82900-2 | Request for functional tester wiring diagram to aid in troubleshooting. | Flex | ST | HuaZhen |  | OESR183012 [26th Dec 18] Senai's ST Ng raised a request for schematics on wiring diagram of functional testers [01Jan19] Received Diagram | YES | 2- Medium(<4 weeks) | Close | 4
S190023 | Test Engineering | 2019-01-09 | TE82988-2 | Model 2100001203 & 2100001164 tested using same FT Fixture TE0084037-2 failure FT Test with Error message prompted "Is Scope Triggered?" . Retest 5 boards each model also failure above similar failure mode. Senai engineer was try to change cable from TE82888 card to UUT but still having similar failure. I also change spare cable from TE82888 card to 210000415 cards in fixture but still same failure. | Flex | Erzad | HuaZhen |  | [10Jan19] OESR 193041 [11Jan19] Test Sequence online debug option was enabled. Richard deselected the option as Administrator | Yes | 1- High(< 1 week) | Close | 2
S190024 | Test Engineering | 2019-01-11 | TE82510 | 1. 210000411 board were tested on the Alliance tester with the fixture (Job# 3011206), the test output a corrupted display on the backlit LCD along the test and failed at the test sequence "FLOPPY INTERFACE TEST, TESTING FLOPPY ON J-27 **** ACCESSING FILE **** 2. For the display output corruption issue, display were swapped with another assembly with the display producing very dim output, we were able to see that the output was still corrupted as in the sample image attached together in email. 3. For "FLOPPY INTERFACE TEST, TESTING FLOPPY ON J-27 **** ACCESSING FILE **** , we've swapped the floppy disk along with the IDE cable. The floppy drive were able to be turned on and were actuating the floppy disk for reading. 4. All probes changed. | Flex | Erzad | HuaZhen |  | [11Jan19] OESR 193051 [15Jan19] Received a text file from Edward Jackson and asked Flex to rerun the test with file from Milford [31Jan19] Flex KP sent 411 fixture to Flex Senai and ETA to Flex Senai on 4th Feb 2019 [08Feb19] Ed has confirmed the fixture was verified in Milford and Flex Senai did verification of fucationality too. Both verification shows the fixture is in good working and fit for prodution test. | Yes | 2- Medium(<4 weeks) | Close | 20
S190078 | Test Engineering | 2019-05-15 | TE 83012-2 | Repair worn out 210000345 ICT fixture on bottom access cause pin alignment issue between Interface Board. | Flex | Erzad | HuaZhen | 2019-10-07 | [07Jun19] Advise Flex Senai to laise with Petracarbon for repair and claim under qauterly expense. [20Jun19] Senai to advise when this repair can be completed and OESR close [25jun2019] Edwin - Huazhen to advise by 26jun2019 [27Jun2019] KC - ICT fixture will preceed repair on 3July with VCCA validation [08Jul2019] Checked with Erzad/KC regarding repair status [10Jul2019] The fixtures were repaired and the verification is in progress | No | 2- Medium(<4 weeks) | Close | 104
S190088 | Test Engineering | 2019-06-17 | TE82961-2 | Tester TE 82961-2 program unable to rtest due to error with 'Personality Bd. failed to initialize properly'. Request for waters help to reviews tester system configuration will impact production shiptment 17 Jun 2019 | Flex | Erzad | HuaZhen |  | [18Jun2019] Emailed to Joel to work with Erzad on 1st level troubleshooting and advise the impact to Flex Kallang. [20Jun2019] Issue is due to jumper missing, Fixed | No | 1- High(< 1 week) | Close | 3
S190089 | Test Engineering | 2019-06-17 | TE82940 | Tester TE 82940 unable to power up due to power supply defect. Request for replacement power supply, provide by Flex Kallang. | Flex | Erzad | HuaZhen |  | [18Jun2019] Emailed to Erzad to get a replacement power supply from Flex Kallang; [20Jun2019] Senai advise the target close date. [25Jun2019] Huazhen to update status and close | No | 2- Medium(<4 weeks) | Close | 5
S190090 | Test Engineering | 2019-06-17 | TE82895-0 | Tester TE 82895 software unable to run due to disk space full ('C' folder). Temporary action backup a few data transfer to folder 'D'. Request for waters help to reviews configuration data on disk Big size folder location : C:\Empower\Oracle\admin\WAT6\bdump. | Flex | Erzad | HuaZhen |  | [18Jun2019] Need to check Flex Senai about details of data and raise an OESR to Milford if necssary [21Jun2019] check the issue onsite and going to raise OESR [24Jun2019] OESR 193410 was raised to Milford [01Jul2019] Checked with Bill Bates regarding these *.trc files [04Jul2019] Bill replied thse trc file can be deleted. He will set up a routine task for system to delete it. | Yes | 3- Low (> 4 weeks & above) | Close | 11
S190102 | Test Engineering | 2019-07-18 | TE 82988-2 | Tester GTS TE 82988-2 instrument Lambda GENH60-12.5-LAN Power Supply S/N: 09M1035A fail calibration on 15 July 2019. Fail during measurement 30V with over spec value 30.121V. (spec : 29.910V to 30.090). Due to calibration out of specification, tester GTS TE 82988-2 don’t have approval to release for production use. Impact production shipment for 8 Model : 1) 210000345 2) 210000384 3) 210000411 4) 210000414 5) 210000415 6) 210000444 7) 210001164 8) 210001203 Request replacement for new Lambda GENH60-12.5-LAN Power Supply. | Flex | Erzad | HuaZhen | 2019-08-02 | [22Jul2019] Arranged Poswer supply and some other parts for this repair. Flex Senai will collect parts once they have approval from custom. OESR: 193436 [24Jul2019] All parts collected by Flex Senai and trhoubleshooting is on going [02Aug2019] Waiting for self test full test complete and spare parts back from Flex Senai [04Sep2019] Joel to ask Flex Senai return all parts [10Sep19] Emailed Erzad to advise the date of return [11Sep19] Erzad -- ETA 23rd September [24Sep19] Sent a chaser to Erzad; Erzad -- For below item will be ship out by today due to delay of customs approval. For the part that still remain here, Calibration fixture and Pickering Mux card, I will prepare for customs approval first to avoid delay time for next shipping. [11Oct2019] 2x TDK power supply and 1x Chroma load received from Flex. The 1x faulty power supply and 1x Chroma Load is under repair arrangement. Sent a chaser to Erzad for the Pickering MUX card and venture self test fixture shipment [31Oct19] 1. TDK power returned from Micro Precision. Pending for Chroma Load before returning to Flex Senai. 2. Chroma Load, pending for Micro Precision confirmatioin. Check status. 3. Picking Mux Pending for Chroma Load before returning to Flex Senai 4. Venture self fixture should be returned from Flex Senai [20Nov19] Close this OESR and under monitoring as it's only waiting for Venture to receive this self test fixture and return Flex senai their original parts. | Yes | 3- Low (> 4 weeks & above) | Close | 12
S190104 | Test Engineering | 2019-07-19 | TE82988-2 | Problem statement : Tester GTS TE 82988-2 instrument Lambda GENH60-12.5-LAN Power Supply S/N: 09M1035A fail calibration on 15 July 2019. Fail during measurement 30V with over spec value 30.121V. (spec : 29.910V to 30.090). Due to calibration out of specification, tester GTS TE 82988-2 don’t have approval to release for production use. Impact production shipment for 8 Model : 1) 210000345 2) 210000384 3) 210000411 4) 210000414 5) 210000415 6) 210000444 7) 210001164 8) 210001203 Request below instrument ship to Senai for investigation purpose : 1)PXI 2586 relay card 2)Pickering relay mux (40-612-002) 3)Lambda Power Supply GENH60-12.5A 4)Self Test Fixture 5)Chroma Load 63103 | Flex | Erzad | HuaZhen |  | [22Jul2019] Parts will be ready for collection except PXI2586, which cannot be found in WPPL. [02Aug2019] All parts are still in Flex senai. Flex should return all repair parts once the self test fully complete [20Sep2019] Close this OESR and tracking parts under the other parts' OESR as per discussion with Edwin | No | 2- Medium(<4 weeks) | Close | 1
S190108 | Test Engineering | 2019-08-01 | TE82988-2 | Problem statement : Existing functional testers or functional fixture did not have CPU cards as spare although FT tester currently is still running good. We need spare to ensure tester downtime is low. Spare part request as per attached excel file. Tester/Fixture# CPU Card # PCBA # 1) TE 83044 210000273 Rev G 210000345 2) TE 83002 N/A 210000414 3) TE82718 487 CPU 081060 279002660 4) TE82961-2 PCB 210000182 210000565 5) TE82940 PCB 210000333 210000355 & 210000404 | Flex | Erzad | Huazhen |  | [04Sep19] Edwin will review/advise [05Sep19] Approve the spare ordering. Huazhen to order the spares [12Sep19] CPU 273, 182 and 333 are obsolete, cannot be ordered. Flex has CPU 520 as spare | No | 3- Low (> 4 weeks & above) | Close | 26
S190117 | Test Engineering | 2019-08-19 | TE 82988-2 | Problem statement : Tester GTS TE 82988-2 model 210000411 unable to verify 'Alliance' logo display. Base of 'Test specification and procedure, 2695 Universal PCB Tester' document #: WAT-RF-SKI00333 page 6 of 7 : "The operator must ensure the proper firmware is loaded on the PCB by observing the TE82510 Test Station display, shows the proper boot-up screen for the pcb. The operator must verify this observation for each board test. The 210000411 will display "alliance". Boards not displaying these screens as shown are considered a failure and will require repair." Request to upgrade system verification on GTS for model 210000411 to check 'Alliance' logo display and meet the test specification. | Flex | Erzad | HuaZhen | 2019-09-04 | [21Aug2019] Typler -- I would use the alliance tester until a method to verify the u53 firmware is determined. That way they will be able to verify by looking at the display. There is not a possible way to check that on FCT right now. I think the solution to this is to some how check the firmware after the chips are programmed at ICT. [04Sep2019] Flex senai to confirm Alliance logo checking stated TSP. Is it checksum check in TSP? If not in TSP, will close this case. Printing out email and check into OESR folder. | No | 2- Medium(<4 weeks) | Close | 13
S190124 | Test Engineering | 2019-08-27 | TE# | Request TE# for new ICT Fixture 210001344 - Currently did not have TE# number | Flex | Erzad | HuaZhen | 2019-09-13 | [28Aug2019] OESR 193544 was created for this request. [13Sep19] New TE# from Paul was sent to Flex | Yes | 2- Medium(<4 weeks) | Close | 14
S190140 | Test Engineering | 2019-09-11 | TE82940 | Problem statement : Tester TE 82940 for model 210000355 to be use for new model 210001344 with different test method. PCBA model 210001344 unable to measure at 2 regulated voltage point '3.3v to GRD' and '2.5V to GRD'. Its required new test specification procedure. | Flex | Erzad | HuaZhen |  | [13Sep19] Matt Brule -- I think I am going to ‘release’ a procedure for this PCB via TMD (Temporary Manufacturing Deviation), this will ensure that the process is no longer valid upon release of the new test fixture for the GTS. Attached is a draft of the procedure, can you verify that it is correct and mark up if necessary. I will complete TMD after I get your feedback. [24Sep19] Erzad has updated Matt with comments on temporary procedure for this test. Matt will release TMD for this test [27Sep19] Matt will work on this TMD and close this case as no action from WPPL | No | 2- Medium(<4 weeks) | Close | 12
S190161 | Test Engineering | 2019-10-11 | TE82988-2 | Problem statement : Tester GTS TE 82988-2 unable to pass for selftest verification. Investigation found the failure related with Pickering MUX relay value over spec. Already change new Pickering Relay MUX card but the failure still occur. Plan to change cable interface for pickering MUX. Request to get new cable for replacement. Items: 1) CABLE PICKERING 40-612-002 | Flex | Erzad | HuaZhen | 2019-10-31 | [14Oct19] Asked Flex Senai to collect this requested cable for verification only. [15Oct19] Flex Senai Erzad has collected the cable for this verification. [31Oct19] Flex Senai to update repair status for parts | No | 3- Low (> 4 weeks & above) | Close | 15
S190164 | Test Engineering | 2019-10-18 | TE82558 | PROBLEM STATEMENT Model 210000425 facing continuous fail at FCT test with failure ‘Pump driver interface failed! Unable to reset the primary motor drive’. ACTIVITIES DONE: 1. Verify fixture 210000425 with a few pass board and the result all fail with same failure ‘Pump driver interface failed! Unable to reset the primary motor drive’. 2. Verify base tester TE82510 with running other fixture model 210000411 and 210000416 and the tester function well without any failure. Initial suspect failure not related tester & more related to fixture issue. Verify fixture model 210000425, measure all pin continuity to the rear panel interface, all connection is good. Production Impact- Pending 68pcs at the FT station.Shipment commit this week 35pcs | Flex | Erzad | HuaZhen | 2019-10-25 | [18Oct2019] Flex was advised to provide the parts info and troubleshooting support details [21Oct2019] Flex collected the old version of CPU and a power supply from Flex Kallang [25Oct2019] The problem was fixed by replace faulty IC in the fixture. Asked Flex Senai to return the old version of CPU board | Yes | 1- High(< 1 week) | Close | 6
S190189 | Test Engineering | 2019-12-04 | TE82988-2 | Problem statement : 210000384 at FCT GTS tester facing high failure with 4.5% fall out reject for 1 week output (300 boards) Waters 210000384 GTS Test have 2 very marginal failure mode ( both related to Voltage supply): 1. 3.3V SUPPLY 2. BLACKLIGHT CONTROL LED OUT IS DIM Request WPPL to review specification of this failure mode *Refer excel attachment for data collection | Flex | Erzad | HuaZhen | 2019-12-11 | [10Dec19] Asked Flex to check if it's repeating failing and try to separate if the failure from tester or UUT. [12Dec19] Checked with Edward J, the spec is matched to the component tolerance. Need to raise OESR to Matt if it's required | No | 2- Medium(<4 weeks) | Close | 6
S190190 | Test Engineering | 2019-12-04 | TE# | Request TE# for new Alliance Box - Currently did not have TE# number | Flex | Erzad | HuaZhen | 2019-12-10 | [10Dec19] Close this request as it's not applicable for this alliance from Flex KL | No | 2- Medium(<4 weeks) | Close | 5
S20012 | Test | 2020-02-08 | TE82988-2 | 1. Problem Statement. -210000414 at FCT GTS tester facing POS11 Failed. Actual Reading 1.0V ,Hi- 11.2 Lo-10.8 -210000415 at FCT GTS tester facing Motor Drive Failed. Check hold State- Winding 2 Actual Reading 23.984, Hi-10 Lo-0. 2. Acceptance criteria that is not met. (e.g. relevant specification number and revision) - Must be able to pass pcba FCT testing. 3. Relevant records (e.g. Incomin QA, Test Records, Photos, trackise NCRs numbers and related issue) - N/A 4. Info on whether this issue impacts revenue -Impact on 21000345, 21000415, 21000414 and 21001164 | Flex | Bernard | HuaZhen | 2020-02-14 | [11Feb20] 210000414- PASSED. Original CPU Card repaired by changing U16 and U18. 210000415- PASSED(11/02/2020). Original CPU Card repaired by changing burned L1. [14Feb20] The tester is working and pending for spare parts from Milford under existing OESR 203852 | Yes | 1- High(< 1 week) | Close | 5
S20030 | Test | 2020-04-03 | TE82720-1 | 1. Problem Statement. -Keithley 236 SN 0810603 found caliration failed at 3rd party calibration facility. Details to be shared once supplier send out the failed calibration report. 2. Acceptance criteria that is not met. (e.g. relevant specification number and revision) - Must be able to pass calibration requirements 3. Relevant records (e.g. Incomin QA, Test Records, Photos, trackise NCRs numbers and related issue) - Calibration Report 4. Info on whether this issue impacts revenue -Impact on 279002660/279001098/081318 for April month requirement | Flex | Bernard | HuaZhen | 2020-04-06 | [06Apr20] Asked Bernard to laise with Tektronics with calibraion and do repair if necessary. Flex KL to update the latest status | No | 1- High(< 1 week) | Close | 2
S20035 | Test | 2020-04-27 | TE084004- 2 | . Problem Statement. -Add-in detectability/coverage on ICT test locations U1,U2,U3,U4,U5,U6,U7,U12,U13, U16 and U17 2. Acceptance criteria that is not met. (e.g. relevant specification number and revision) - Must be able to pass top assembly requirements 3. Relevant records (e.g. Incomin QA, Test Records, Photos, trackise NCRs numbers and related issue) - Test Record 4. Info on whether this issue impacts revenue -No impact on the revenue, improvement only | Flex | Bernard | HuaZhen | 2020-05-11 | [30Apr20] Emailed Milford for this request as eOESR is refersh itself and cannot create a new OESR now. [18May20] Informed Milford regarding this request.No action required for now. Close | Yes | 2- Medium(<4 weeks) | Close | 11
S20058 | Test | 2020-07-27 | TE82988-2 | 1. Problem Statement. -TDK-Lambda with serial number 09M1037A found voltage rotary knob is not responding during the calibration at 3rd party (MicroPrecision)calibration facility. Details on the attached. 2. Acceptance criteria that is not met. (e.g. relevant specification number and revision) - Must be able to pass calibration requirements 3. Relevant records (e.g. Incomin QA, Test Records, Photos, trackise NCRs numbers and related issue) - Calibration Report 4. Info on whether this issue impacts revenue -Impact on 210000415,210000345,210000414,210000384,210001164,210001203 and 210000444 for August month 150k requirement | Flex | Bernard | HuaZhen | 2020-08-06 | [02Aug20] Spare power supply has been calibrated and all equipment was shipped back to Flex Senai. Flex to update status [06Aug20] Flex updated the GTS is covered. Close. | NO | 1- High(< 1 week) | Close | 9
S20064 | Test | 2020-08-11 | TE82720-1 | 1. Problem Statement. -Keithley 236 SN 0810603 found failed during verification after repair and calibrate from Tektronix US. Attached the failures encounter. 2. Acceptance criteria that is not met. (e.g. relevant specification number and revision) - Must be able to pass calibration requirements 3. Relevant records (e.g. Incomin QA, Test Records, Photos, trackise NCRs numbers and related issue) - Test Record 4. Info on whether this issue impacts revenue -Impact on 279002660/279001098/081318 for September month requirement | Flex | Bernard | HuaZhen | 2020-08-13 | [13Aug20] Flex should confirm the repaired unit performance and claim warranty if ncessary. Void this OESR as it's Close under previous OESR. | No | 1- High(< 1 week) | Close | 1
S20069 | Test | 2020-08-26 | TE82988-2 | 1. Problem Statement. -NI- DAQmx devices no communciation. Attached the screenshoot for system status showing PCI and NI not detected. 2. Acceptance criteria that is not met. (e.g. relevant specification number and revision) - Must be able to pass test requirements 3. Relevant records (e.g. Incomin QA, Test Records, Photos, trackise NCRs numbers and related issue) - Test Record 4. Info on whether this issue impacts revenue -Impact on 210000345 for this month of August requirement and all associated model for month of September. | Flex | Bernard | HuaZhen | 2020-09-21 | [27Aug20] Advised Flex to check power supply to/in NI chassis, PC and PXI-8360 card. OESR 204256 was raised to Milford. [28Aug20] Flex found the faulty power supply in chassis and confirmed by using an equivalent power supply. Flex is repair the original power and verify the system performance before production. [21Sep20] No acitons from WPPL and equivalent solution was in place. Close this OESR and park under monitoring | Yes | 1- High(< 1 week) | Close | 15
S20085 | Test | 2020-09-21 | TE82988-2 | 1. Problem Statement. - Test Noise Failed. Charge Injection Actual reading 20xxx.xxx Spec Low 8000, High 18400 2. Acceptance criteria that is not met. (e.g. relevant specification number and revision) - Must be able to pass test requirements 3. Relevant records (e.g. Incomin QA, Test Records, Photos, trackise NCRs numbers and related issue) - Test Record 4. Info on whether this issue impacts revenue -Impact on 210001164 for this month of Sept requirement. | Flex | Bernard | HuaZhen | 2020-09-28 | [23Sep20] From information provided by Flex, the same tester and fixture pass the test on another model. Recommend to continue the test and fulfill the sept order, meanwhile working on investigate the root cause if it's from process or materials. Flex to provide the data collection for investigation [28Sep20] the root cause was identitified. The issue is from U8 on UUT. No problem with tester. Close this OESR | Yes | 1- High(< 1 week) | Close | 6
S20123 | Test | 2020-12-04 | TE82510 | Problem Statement. - Communication error for model WT210000416 and WT0000425 2. Acceptance criteria that is not met. (e.g. relevant specification number and revision) - Must be able to pass test requirements 3. Relevant records (e.g. Incomin QA, Test Records, Photos, trackise NCRs numbers and related issue) - Test Record 4. Info on whether this issue impacts revenue -Impact on model 210000416 and 210000425 weekly requirement | Flex | Bernard | HuaZhen | 2020-12-08 | [06Dec20] Senai will collect a spare cpu from waters on Monday. [10Dec20] Tester is recovered by replacing old CPU board from Waters | Yes | 1- High(< 1 week) | Close | 3