## Capex Fcst
WPPL Capex Forecast 2019
|  |  | Budget Appropriation - 2019 |  |  |  |  | Budget Spending - 2019 | [5 empty] | Forecast Appropriation - 2019 |  |  |  |  | Forecast Spending - 2019
Cost Center | Capex brought forward: | Capex No | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | 2020 Carryover | Q1 Act | Q2 Act | Q3 Fcst | Q4 Fcst | Total | Q1 Act | Q2 Act | Q3 Fcst | Q4 Fcst | Total | 2020 Carryover | Comments
WP21 | 2690 Heater Cooler Test system | WPPL14014 | [5 empty] | 5700 | 0 | 0 | 0 | 5700 | 0 | [5 empty] | 0 | 0 | 5700 | 0 | 5700 | 0 | Received TE0084018-1 - Edwin
WP21 | Additional capacity for the Final Testing of detectors at GES | WPPL16003 | [5 empty] | 1740 | 0 | 0 | 0 | 1740 | 0 | [5 empty] | 0 | 0 | 1740 | 0 | 1740 | 0 | Received TE83760-7 - Edwin
WP21 | Valve Drive Assembly Tester & Encoder | WPPL16015 | [5 empty] | 4080 | 0 | 0 | 0 | 4080 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Cancel CEA, not transferring - per discussed with Yin Ying (29th May 2019)
WP21 | Drive Injector Valve Assembly Toolings | WPPL16017 | [5 empty] | 8804 | 0 | 0 | 0 | 8804 | 0 | [5 empty] | 0 | 0 | 8804 | 0 | 8804 | 0 | Push back to 2019 - Venture can perform OT for 2018 AT - are we going to do this capex in 2019?
WP21 | GTS Calibration Fixture | WPPL16018 | [5 empty] | 660 | 0 | 0 | 0 | 660 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Complete
WP21 | Tooling for WAT270033 Carousel, 24 Position | WPPL16020 | [5 empty] | 13200 | 0 | 0 | 0 | 13200 | 0 | [5 empty] | 0 | 0 | 13200 | 0 | 13200 | 0 | YY 05-Apr-19 - Work with Milford team on functional test. Target to complete and approval by June 2019. AT - what is status? Who are we working with in Milford?
WP21 | Alliance Column Heater & Cooler Tester at Venture | WPPL17001 | [5 empty] | 1450 | 0 | 0 | 0 | 1450 | 0 | [5 empty] | 0 | 0 | 1450 | 0 | 1450 | 0 | Received TE82774-4 - Edwin
WP21 | Flow Cell and Optic Bench | WPPL17021 | [5 empty] | 4100 | 0 | 0 | 0 | 4100 | 0 | [5 empty] | 0 | 0 | 4100 | 0 | 4100 | 0 | YY 05-Apr-19 - FA is not approved. Cannot bill final payment. AT - Status update ? What is the holdup?
WP21 | Crank Arm Casting | WPPL17022 | [5 empty] | 1758 | 0 | 0 | 0 | 1758 | 0 | [5 empty] | 0 | 0 | 1758 | 0 | 1758 | 0 | YY 05-Apr-19 - FA is not approved. Cannot bill final payment. AT - Status update ? What is the holdup?
WP21 | Alliance evaluation tester | WPPL18004 | [5 empty] | 1498 | 0 | 0 | 0 | 1498 | 0 | [5 empty] | 0 | 0 | 1498 | 0 | 1498 | 0 | Received and completed - Edwin
WP21 | Casting Tool 418000133 | WPPL18006 | [5 empty] | 3490 | 0 | 0 | 0 | 3490 | 0 | [5 empty] | 0 | 3316.5 | 0 | 0 | 3316.5 | 0 | Billing complete
WP21 | MSV Tester - TE84040 | WPPL18015 | [5 empty] | 6460 | 0 | 0 | 0 | 6460 | 0 | [5 empty] | 0 | 0 | 6460 | 0 | 6460 | 0 | Chau - Q4 2018, but under review of management for the transfer plan - Kris Bujold, Edwin Koh, and others are discussing changes in Tranfer Plan AT - Edwin - any further update on this? Any transfer plans?
WP21 | SQT Test Station Workbench Setup | WPPL18017 | [5 empty] | 2680 | 0 | 0 | 0 | 2680 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Complete
WP21 | Critical Injection tools | WPPL18021 | [5 empty] | 8760 | 0 | 0 | 0 | 8760 | 0 | [5 empty] | 0 | 0 | 8760 | 0 | 8760 | 0 | YY 05-Apr-19 - Work with Milford team on PPAP. Target to complete and approval by June 2019. AT - approval obtained? Who are we working with in Milford?
WP21 | Instruments required for 4 test bays, QDa project | WPPL18022 | [5 empty] | 7050 | 0 | 0 | 0 | 7050 | 0 | [5 empty] | 4458.76 | 0 | 0 | 0 | 4458.76 | 0 | Complete
WP21 | Helium Leak Checker | WPPL18031 | [5 empty] | 25350 | 0 | 0 | 0 | 25350 | 0 | [5 empty] | 25710.34 | 0 | 0 | 0 | 25710.34 | 0 | Complete
WP21 | QDA Test Bays X 4 | WPPL18026 | [5 empty] | 11390 | 0 | 0 | 0 | 11390 | 0 | [5 empty] | 2229.38 | 0 | 0 | 0 | 2229.38 | 0 | Complete - 3 units were recycled from another project so there is no charge
WP21 | Aluminium hot foaming tool (401001048 & 401001049) | WPPL18024 | [5 empty] | 4020 | 0 | 0 | 0 | 4020 | 0 | [5 empty] | 4015 | 0 | 0 | 0 | 4015 | 0 | Billing complete
WP21 | Tooling for INSULATOR, DOOR, DETECTOR, COMMON (415002256) | WPPL18029 | [5 empty] | 2750 | 0 | 0 | 0 | 2750 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Yu Xue: Supplier decided to drop this project
WP21 | EPP foam parts localization |  | 25000 | 0 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 25000 | 25000 | 0 | YY 05-Apr-19: Push out from Q2 to Q4. AT - what is the reason for the push back to Q4?
WP21 | ICT tester to improve PCBA testing coverage |  | 0 | 20000 | 0 | 0 | 20000 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 22457 | 40000 | 62457 | 0 | 0 | 22457 | 40000 | 62457 | 0 | Appropration increase to $80K per Terri Charbonneau email (25th Apr) - 210001344 to replace 210000355 (CEA - $17,543 in May 2019) AT - Edwin, status & if amount reasonable?
WP21 | ICT FIXTURE DEVELOPMENT FOR 210001344 | WPPL19008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17543 | 0 | 0 | 17543 | 0 | 0 | 17543 | 0 | 17543 | 0 | Utilise ICT tester to improve PCBA testing coverage budget
WP21 | FCT tester for PCBA testing coverage - 19 FCT fixtures need to migrate |  | 0 | 80000 | 0 | 0 | 80000 | 0 | 0 | 80000 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Able to remove as NRE is bear by Engineering for new PCBAs ($80K)
WP21 | GVT HTL Assy (PACT - 2nd Phase) test rig, vacuum test chamber |  | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 20000 | 0 | 20000 | 0 | AT - YY how is the HTL testing for PACT? When is completion expected?
WP21 | Helium Leak Checker at GVT |  | 0 | 0 | 24000 | 0 | 24000 | 0 | 0 | 24000 | 0 | 24000 | 0 | 0 | 0 | 24000 | 0 | 24000 | 0 | 0 | 24000 | 0 | 24000 | 0
WP21 | IT Infrastructure upgrade at CM sites (Switches, PC, network cable GBP100K 1.31) |  | 132000 | 0 | 0 | 0 | 132000 | 0 | 70000 | 62000 | 0 | 132000 | 0 | 0 | 0 | 132000 | 0 | 132000 | 0 | 0 | 132000 | 0 | 132000 | 0 | Edwin - are we going to raise CEA for this? Who is working with David Moss? This will be review once servers are migrated. Only CEI Batam and CEI Singapore migrated - Apr AT - Server migration almost complete. Are we planning to move ahead with this?
WP21 | Injection tools renewal |  | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 24495 | 25505 | 50000 | 0 | 0 | 24495 | 25505 | 50000 | 0 | YY 05-Apr-19: 3 MRPC tools need replacement. Reuse mold base with new core & cavity insert - USD 24,495. AT - how about the remaining 25.5K? When will CEA be raised for all these?
WP21 | QDA (Refub) x 2 |  | 0 | 0 | 0 | 16000 | 16000 | 0 | 0 | 0 | 16000 | 16000 | 0 | 0 | 0 | 0 | 16000 | 16000 | 0 | 0 | 0 | 16000 | 16000 | 0 | AT - EK what is happening here?
WP21 | Equipment replacement at CM |  | 0 | 12000 | 0 | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 0 | 0 | 0 | 12000 | 0 | 12000 | 0 | 0 | 12000 | 0 | 12000 | 0 | AT - EK what is happening here?
WP21 | Production Tool renewal |  | 0 | 50000 | 0 | 0 | 50000 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 50000 | 0 | 50000 | 0 | AT - EK what is happening here?
WP21 | Alliance Test bay upgrade |  | 240000 | 0 | 0 | 0 | 240000 | 240000 | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 190329 | 0 | 190329 | 0 | 0 | 190329 | 0 | 190329 | 0 | Utilise Alliance Test and SIT project (Edwin: $16284.72 (SIT I Class) + $5400) = $21,684.72) Hoist System - $10K - Q3 QDA - Nitrogen generators ($120K) if cannot fix contimination for Qda.
WP21 | DETECTOR CONTROL BOX | WPPL19002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9215 | 0 | 0 | 0 | 9215 | 0 | 0 | 9215 | 0 | 9215 | 0 | Utilise Alliance Test bay upgrade budget
WP21 | ALLIANCE PUMP TRAP | WPPL19003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18870 | 0 | 0 | 0 | 18870 | 0 | 0 | 18870 | 0 | 18870 | 0 | Utilise Alliance Test bay upgrade budget
WP21 | DROP TEST INSTRUMENT | WPPL19006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16609 | 0 | 0 | 16609 | 0 | 16741.48 | 0 | 0 | 16741.48 | 0 | Complete
WP21 | PC for SIT Test Bays | WPPL19007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4977 | 0 | 0 | 4977 | 0 | 0 | 4977 | 0 | 4977 | 0 | Utilise Alliance Test bay upgrade budget
WP21 | China for China (Tools) |  | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 20000 | 20000 | 0
WP21 | China for China (Testers) |  | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 100000 | 100000 | 0
|  |  | 397000 | 162000 | 44000 | 186000 | 789000 | 379940 | 70000 | 268000 | 186000 | 903940 | 0 | 28085 | 39129 | 475281 | 226505 | 769000 | 36413.48 | 20057.98 | 579356 | 226505 | 862332.46 | 0
Note on D12: Under YY's Group