## FORM
Section 1: Introduction
Requester | Jason wang | Date |  | 2020-03-06
Evaluation# | EVALS20004 | Version # |  | 0
Category | Others | TMD/ NCR #
Affected P/N(s) | 186015014 | P/N Description(s) |  | CPSO
Section 2: Evaluation Assessment
Problem Statement (Describe briefly of the issue. Any impacts to the production capacity, output, resources, or product designs. Include serial numbers and document numbers with revision where applicable. List down potential causes.)
We are facing numbers of failure on the adjust plate latch actuation speed during functional setup for CPSO model. Adjust according to TSP 735002510 Rev D CPSO final test, follow on screen the Latch Actuation Speed step by preset plate latch flow knob controls by loosening the stops nuts, then rotate the flow control knob clockwise all the way, then turn counterclockwise 1.5 turns on the upper flow control and 0.75 turns on the lower flow control. Production feedback when click 'OK' they don’t have enough time to adjust the knob before test program pop out to "fail". This will result in final test fail and affecting FPY. Total 34 latch failures have reported in the FPY in 2019. Request for test program update to allow enough time for plate actuation adjustment. Milford has advised the following action to overcome this adjustment timing request. Try to find a best way of pre-adjusting to shorten the adjusting time during fuctional test, such that it is closer and does not require the adjustment.
Evaluation Plan (Actions must be listed in a sequential manner.)
Action Owner | Action Description |  |  |  | Expected Completion Date
Jason Wang / HuaZhen | Determine how many turns to optimize the preset value for the Micro-valve. |  |  |  | 2020-03-24
Jason Wang / HuaZhen | Plan to run 10 pcs of Micro-Valve to finialise the setting is correct and ensure pass the latch test. |  |  |  | 2020-03-26
Jason Wang | Brief technician on the new setting. |  |  |  | 2020-03-27
Jason Wang | Target to have lower or no latch testing fail from April to May |  |  |  | 2020-05-30
Section 3: Evaluation Approvals
| Name / Title |  | Signature |  | Date
CMO Mfg Lead
Waters Mfg Engineer
Waters Quality Engineer

## Sheet1
TMD
First Article
NCR
Failure Analysis
Others