## VMP
Equipment/ System # | Equipment/System Name | Location | Site | Validation Type | Validation Reason | Validation Execution | Project | Validation Status | Priority | Active Date | Est. Date of Complete | Complete Date | Assigned | Validation Assessment
TE83064-08 | CPSM Final Test System | United States | Milford White Room | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2018-04-02 | 2018-05-01 | 2018-05-03 | Emma Pierce | TE83064-02APR2018-VAF
TE83064-19 | CPSM Final Test System | United States | Milford White Room | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2018-04-02 | 2018-05-02 | 2018-05-03 | Emma Pierce | TE83064-02APR2018-VAF
TE82943-09 | ACQUITY SDS Final Test System | United States | Milford NPI | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2018-03-28 | 2018-04-25 | 2018-04-30 | Emma Pierce | TE82943-28MAR2018-VAF
TE82995-4 | ACQUITY CPSM RTZ Assembly Test System | United States | Milford White Room | IQ | Initial | Full | Physical Move | Complete | Urgent | 2018-04-05 | 2018-04-30 | 2018-04-26 | Jim Stors | VAL001218-26MAR18-VAF
TE82943-03 | ACQUITY SDS Final Test System | United States | Milford NPI | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2018-03-28 | 2018-04-20 | 2018-04-18 | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-23 | ACQUITY SDS Final Test System | United States | Milford NPI | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2018-03-28 | 2018-04-20 | 2018-04-18 | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-23 | ACQUITY SDS Final Test System | United States | Milford NPI | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-02-14 | 2018-04-30 | 2018-04-13 | Jim Stors | TE82943-19JAN2018-VAF
TE82943 | ACQUITY SDS Final Test System BiFrost | United States | Design | EDV | Initial | Partial | New Product Intro | Complete | Normal | 2018-03-30 | 2018-04-06 | 2018-04-12 | Emma Pierce | TE82943-28MAR2018-VAF
TE82758-2 | 2414 Final Test System | United States | Milford Clean Room | IQ | Requalification | Partial | TE Improvement | Complete | Urgent | 2018-04-03 | 2018-04-13 | 04/11/2018 | Jim Stors | TE82758-06APR2018-VAF
TE83064-21 | CPSM Final Test System | United States | Milford NPI | IQ | Initial | Full | New Product Intro | Complete | Normal | 2018-04-02 | 2018-04-27 | 2018-04-10 | Tyler Modelski | TE83064-02APR2018-VAF
TE83064-20 | CPSM Final Test System | United States | Milford NPI | IQ | Initial | Full | New Product Intro | Complete | Normal | 2018-04-02 | 2018-04-27 | 2018-04-09 | Tyler Modelski | TE83064-02APR2018-VAF
TE84037 | Charge Amp PCB Assembly Test Fixture | United States | Design | EDV | Requalification | Partial | TE Improvement | Complete | Normal | 2018-02-09 | 2018-04-06 | 2018-03-23 | Emma Pierce | TE0084037-05FEB2018-VAF
TE84002-1 | Trap Valve Manager Final Test System | United States | Milford Clean Room | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2018-01-15 | 2018-03-31 | 2018-03-12 | Tyler Modelski | TE0084002-11JAN2018-VAF
TE82503-1 | Injector/Seal Pack Tester | United States | Milford NPI | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2018-02-20 | 2018-03-16 | 2018-03-08 | Emma Pierce | TE82503-26FEB2018-VAF
TE82503-3 | Injector/Seal Pack Tester | United States | Milford NPI | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2018-02-20 | 2018-03-16 | 2018-03-08 | Emma Pierce | TE82503-26FEB2018-VAF
VAL001115 | Cleaning Process Measurement Method | United States | Milford Critical Clean | TMV | Initial | Full | Critical Clean | Complete | Normal | 2017-07-01 | 2018-02-16 | 2018-03-08 | Jim Stors
TE82969-2 | ACQUITY Arc Bio 2998 PDA Detector | United States | Milford Refurb | IQ | Requalification | Partial | TE Improvement | Complete | Normal | 2018-01-09 | 2018-02-28 | 2018-02-22 | Jim Stors | TE82969-03JAN2018-VAF
TE82669 | Carbamate PCRM Reaction Coil Tester | United States | Milford White Room | VAF | Initial | Partial | Physical Move | Complete | Normal | 2018-01-18 | 2018-03-30 | 2018-02-16 | Jim Stors | TE0082669-14FEB2018-VAF
TE82943-03 | ACQUITY SDS Final Test System | United States | Milford NPI | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-02-14 | 2018-02-28 | 2018-02-09 | Jim Stors | TE82943-19JAN2018-VAF
TE84005-1 | Fraction Manager Analytical Final Test System | United States | Milford NPI | IQ | Initial | Full | New Product Intro | Complete | Normal | 2017-04-03 | 2018-02-02 | 2018-02-08 | Tyler Modelski
TE82943-09 | ACQUITY SDS Final Test System | United States | Milford NPI | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-02-02 | 2018-02-28 | 2018-02-06 | Jim Stors | TE82943-19JAN2018-VAF
TE83064-03 | CPSM Final Test Station | United States | Milford NPI | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-25 | 2018-02-01 | 2018-01-31 | Emma Pierce | TE83064-25JAN2018-VAF
TE83064-04 | CPSM Final Test Station | United States | Milford NPI | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-25 | 2018-02-01 | 2018-01-31 | Emma Pierce | TE83064-25JAN2018-VAF
TE83064-06 | CPSM Final Test Station | United States | Milford Clean Room | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-25 | 2018-02-01 | 2018-01-31 | Emma Pierce | TE83064-25JAN2018-VAF
TE83064-07 | CPSM Final Test Station | United States | Milford Clean Room | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-25 | 2018-02-01 | 2018-01-31 | Emma Pierce | TE83064-25JAN2018-VAF
TE83064-08 | CPSM Final Test System | United States | Milford Clean Room | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-25 | 2018-02-01 | 2018-01-31 | Emma Pierce | TE83064-25JAN2018-VAF
TE83064-09 | CPSM Final Test System | United States | Milford Clean Room | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-25 | 2018-02-01 | 2018-01-31 | Emma Pierce | TE83064-25JAN2018-VAF
TE83064-18 | CPSM Final Test System | United States | Milford Clean Room | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-25 | 2018-02-01 | 2018-01-31 | Emma Pierce | TE83064-25JAN2018-VAF
TE83064-19 | CPSM Final Test System | United States | Milford Clean Room | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-25 | 2018-02-01 | 2018-01-31 | Emma Pierce | TE83064-25JAN2018-VAF
TE83064-REFRB | CPSM Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-25 | 2018-02-01 | 2018-01-31 | Emma Pierce | TE83064-25JAN2018-VAF
TE83064-REFRB2 | CPSM Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-25 | 2018-02-01 | 2018-01-31 | Emma Pierce | TE83064-25JAN2018-VAF
TE82943-05 | ACQUITY SDS Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | TE Improvement | Complete | Normal | 2018-01-01 | 2018-01-31 | 2018-01-24 | Tyler Modelski
TE82882-15 | 2998 PDA Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | TE Improvement | Complete | Normal | 2017-12-27 | 2018-01-19 | 2018-01-19 | Jim Stors | TE82882-27DEC17-VAF
TE82950 | Flow Splitter Test | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-12-01 | 2018-01-31 | 2018-01-15 | Emma Pierce | Quality Plan 2017-002
TE82943-07 | ACQUITY SDS Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | TE Improvement | Complete | Normal | 2018-01-01 | 2018-01-31 | 2018-01-05 | Tyler Modelski
TE82903-01 | TUV Detector Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | TE Improvement | Complete | Normal | 2017-12-18 | 2018-01-31 | 2018-01-03 | Jim Stors | TE82903-08NOV2017-VAF
TE82023 | Universal Sparge Tester | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-12-19 | 2017-12-29 | 2017-12-21 | Emma Pierce | Quality Plan 2017-002
TE82943-06 | ACQUITY SDS Final Test System | United States | Milford Clean Room | IQ | Requalification | Full | New Product Intro | Complete | Normal | 2017-12-19 | 2017-12-29 | 2017-12-21 | Tyler Modelski
TE82943-08 | ACQUITY SDS Final Test System | United States | Milford Clean Room | IQ | Requalification | Full | New Product Intro | Complete | Normal | 2017-12-19 | 2017-12-29 | 2017-12-21 | Tyler Modelski
VAL000566 | Bally 3678-3-P Walk-In Cooler - SN: DX1007965-01 | United States | Franklin GDC | IQ | Requalification | Full | Physical Move | Complete | Urgent | 2017-12-13 | 2017-12-29 | 2017-12-19 | Jim Stors
TE82778-1 | Universal Back Pressure/ Decay Tester | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-12-14 | 2017-12-29 | 2017-12-18 | Emma Pierce | Quality Plan 2017-002
TE82943-04 | ACQUITY SDS Final Test System | United States | Milford Clean Room | IQ | Initial | Full | New Product Intro | Complete | Normal | 2015-04-01 | 2017-12-29 | 2017-12-15 | Tyler Modelski
VAL001112 | Organic Contamination by Flow Injection-MS | United States | Milford Quality Lab | TMV | Initial | Full | Critical Clean | Complete | Normal | 2017-11-17 | 2017-12-29 | 2017-12-14 | Tetiana Morse
VAL000533 | So-Low DHW20-20MDP Freezer - SN: 0708173 | United States | Franklin GDC | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-11-01 | 2017-12-15 | 2017-12-08 | Jim Stors
VAL000567 | So-Low DH30-49SDSS Freezer - SN: 11211862 | United States | Franklin GDC | IQ | Requalification | Full | Physical Move | Complete | Urgent | 2017-10-19 | 2017-12-29 | 2017-12-08 | Jim Stors
VAL001079 | So-Low DH30-49SDSS Freezer - SN: 12309468 | United States | Franklin GDC | IQ | Requalification | Partial | Physical Move | Complete | Urgent | 2017-11-20 | 2017-11-30 | 2017-12-08 | Jim Stors
VAL000935 | Pero N2/007-EX7897 Solvent Cleaner | United States | Milford Critical Clean | IQ | Initial | Full | Critical Clean | Complete | Normal | 2017-08-17 | 2017-12-29 | 2017-12-07 | Jim Stors
VAL000565 | So-Low DHW20-17SMDP Freezer - SN: 1011396 | United States | Franklin GDC | IQ | Requalification | Full | Physical Move | Complete | Urgent | 2017-10-01 | 2017-12-15 | 2017-12-05 | Jim Stors
TE82943-03 | ACQUITY SDS Final Test System | United States | Milford NPI | IQ | Requalification | Full | New Product Intro | Complete | Urgent | 2017-10-10 | 2017-11-30 | 2017-11-28 | Tyler Modelski
TE82943 | ACQUITY SDS Final Test System ISM | United States | Design | EDV | Initial | Full |  | Complete | Normal | 2017-08-01 | 2017-09-29 | 2017-11-22 | Tyler Modelski
TE82774-1 | Alliance Column Heater/Cooler Test Station | United States | Milford Refurb | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2017-11-10 | 2017-11-30 | 2017-11-21 | Emma Pierce | TE82774-09NOV2017-VAF
TE82467 | 717 Bezel tester | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Urgent | 2017-09-27 | 2017-10-31 | 2017-11-20 | Emma Pierce | Quality Plan 2017-002
TE82903-06 | TUV Detector Final Test System | United States | Flextronics | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2017-11-17 | 2017-12-29 | 2017-11-20 | Jim Stors | TE82903-08NOV2017-VAF
TE82981-1 | Quaternary Gradient Module (QGM) Final Test System | United States | Milford White Room | IQ | Initial | Full |  | Complete | Urgent | 2017-11-14 | 2017-11-30 | 2017-11-20 | Emma Pierce | TE82981-13NOV2917-VAF
TE82943-02 | ACQUITY SDS Final Test System | United States | Milford Clean Room | IQ | Requalification | Full | TE Improvement | Complete | Normal | 2017-11-06 | 2017-12-29 | 2017-11-16 | Tyler Modelski
VAL001107 | Normalization Worksheet for Xevo G2/G2-XS MS Data | United States | Milford Clean Room | EDV | Initial | Full | Critical Clean | Complete | Normal | 2017-10-01 | 2017-11-30 | 2017-11-16 | Tetiana Morse
TE82903-01 | TUV Detector Final Test System | United States | Milford Refurb | IQ | Initial | Partial | TE Improvement | Complete | Normal | 2017-11-03 | 2017-11-30 | 2017-11-15 | Jim Stors | TE82903-28SEP17-VAF
TE82882-15 | 2998 PDA Final Test System | United States | Milford Refurb | IQ | Initial | Full | New Product Intro | Complete | Urgent | 2017-10-27 | 2017-11-30 | 2017-11-14 | Emma Pierce | Per TE82882-14NOV17-VAF
VAL000521 | So-Low DH30-49DSS Freezer - SN: 11513548 | United States | Franklin GDC | IQ | Requalification | Full | Physical Move | Complete | Urgent | 2017-10-01 | 2017-11-30 | 2017-11-14 | Jim Stors
VAL001099 | Cummins Model C60 N6 Back-Up Generator | United States | Franklin GDC | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-10-06 | 2017-10-31 | 2017-11-14 | Jim Stors
TE81478 | 410 Solenoid/ Relief Valve Tester | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Urgent | 2017-11-02 | 2017-11-30 | 2017-11-10 | Emma Pierce | Quality Plan 2017-002
TE82882-11 | 2998 PDA Final Test System | United States | Flextronics | IQ | Initial | Partial | New Product Intro | Complete | Urgent | 2017-10-17 | 2017-11-30 | 2017-11-07 | Emma Pierce | TE82882-14NOV17-VAF
VAL001082 | Sensitech ColdStream Site Temp Monitoring System | United States | Franklin GDC | IQ | Initial | Full | Physical Move | Complete | Urgent | 2017-10-06 | 2017-11-30 | 2017-11-07 | Jim Stors
TE82882-10 | 2998 PDA Final Test System | United States | Flextronics | IQ | Initial | Partial | New Product Intro | Complete | Urgent | 2017-10-27 | 2017-11-30 | 2017-11-01 | Emma Pierce | TE82882-14NOV17-VAF
TE82882-13 | 2998 PDA Final Test System | United States | Flextronics | IQ | Initial | Partial | New Product Intro | Complete | Urgent | 2017-10-17 | 2017-11-30 | 2017-11-01 | Emma Pierce | TE82882-14NOV17-VAF
TE82882-14 | 2998 PDA Final Test System | United States | Flextronics | IQ | Initial | Partial | New Product Intro | Complete | Urgent | 2017-10-17 | 2017-11-30 | 2017-11-01 | Siew Yee Yeap | TE82882-14NOV17-VAF
TE84037 | Charge Amp PCB Assembly Test Fixture | United States | Design | EDV | Initial | Full | New Product Intro | Complete | Urgent | 2017-10-02 | 2017-11-30 | 2017-11-01 | Emma Pierce | Submission Form
TE82943-09 | ACQUITY SDS Final Test System | United States | Milford NPI | IQ | Requalification | Full | New Product Intro | Complete | Normal | 2017-10-06 | 2017-10-31 | 2017-10-20 | Tyler Modelski | TE82943-26SEP2017-VAF
TE82943-23 | ACQUITY SDS Final Test System ArcQSM | United States | Milford NPI | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-10-05 | 2017-10-31 | 2017-10-20 | Tyler Modelski | TE82943-26Sep2017-VAF
TE82503-1 | Injector/Seal Pack Tester | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-09-26 | 2017-10-31 | 2017-10-16 | Emma Pierce | Quality Plan 2017-002
TE82162 | 717 Carriage Drive Tester | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-09-21 | 2017-09-29 | 2017-10-13 | Emma Pierce | Quality Plan 2017-002
TE82969-2 | ACQUITY Arc Bio 2998 PDA Detector | United States | Milford Refurb | IQ | Initial | Partial | New Product Intro | Complete | Normal | 2017-10-12 | 2017-10-31 | 2017-10-13 | Emma Pierce | TE82969-28SEP17-VAF
VAL001077 | So-Low DH30-49SDSS Freezer - SN: 12309466 | United States | Franklin GDC | IQ | Initial | Full | Physical Move | Complete | Urgent | 2017-09-20 | 2017-10-31 | 2017-10-12 | Jim Stors
VAL001079 | So-Low DH30-49SDSS Freezer - SN: 12309468 | United States | Franklin GDC | IQ | Initial | Full | Physical Move | Complete | Urgent | 2017-09-20 | 2017-10-31 | 2017-10-12 | Jim Stors
VAL001080 | So-Low DH30-49SDSS Freezer - SN: 12309473 | United States | Franklin GDC | IQ | Initial | Full | Physical Move | Complete | Urgent | 2017-09-20 | 2017-10-31 | 2017-10-12 | Jim Stors
VAL001096 | StarLight 150 PDA Alignment System | United States | Design | TMV | Initial | Full | New Product Intro | Complete | Urgent | 2017-09-25 | 2017-10-31 | 2017-10-12 | Tanya Morse
VAL001034 | So-Low DH30-49SDSS Freezer - SN: 115113549 | United States | Franklin GDC | IQ | Initial | Full | Physical Move | Complete | Urgent | 2017-09-20 | 2017-10-31 | 2017-10-11 | Jim Stors
VAL001078 | So-Low DH30-49SDSS Freezer - SN: 12309467 | United States | Franklin GDC | IQ | Initial | Full | Physical Move | Complete | Urgent | 2017-09-20 | 2017-10-31 | 2017-10-11 | Jim Stors
VAL001081 | Bally 3678-3-P Walk-In Cooler - SN: DX1703640-01 | United States | Franklin GDC | IQ | Initial | Full | Physical Move | Complete | Urgent | 2017-09-20 | 2017-10-31 | 2017-10-11 | Jim Stors
TE82774-1 | Alliance Column Heater/Cooler Test Station | United States | Milford Refurb | IQ | Initial | Full | New Product Intro | Complete | Normal | 2017-09-25 | 2017-10-31 | 2017-10-03 | Emma Pierce
TE82943 | ACQUITY SDS Final Test System ArcQSM | United States | Design | EDV | Requalification | Partial |  | Complete | Normal | 2017-09-28 | 2017-10-31 | 2017-10-02 | Tyler Modelski | TE82943-26SEP17-VAF
TE83074-1 | ACQUITY H/I Class Actuator Tester | United States | Milford White Room | IQ | Requalification | Partial | TE Improvement | Complete | Normal | 2017-09-29 | 2017-10-31 | 2017-10-02 | Emma Pierce | TE83074-28SEP2017-VAF
TE83074-2 | ACQUITY H/I Class Actuator Tester | United States | Milford Clean Room | IQ | Requalification | Partial | TE Improvement | Complete | Normal | 2017-10-02 | 2017-10-02 | 2017-10-02 | Emma Pierce | TE83074-28SEP2017-VAF
TE82943 | ACQUITY SDS Final Test System UPC2 | United States | Design | EDV | Initial | Full |  | Complete | Normal | 2017-08-01 | 2017-10-31 | 2017-09-26 | Tyler Modelski
TE83007-1 | HTCH Pre-Heater Test System | United States | Milford White Room | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-08-24 | 2017-09-29 | 2017-09-22 | Jim Stors | TE83007-31AUG17-VAF
TE82503-3 | Injector/Seal Pack Tester | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-08-23 | 2017-09-29 | 2017-09-21 | Emma Pierce | Quality Plan 2017-002
TE82653 | 2790 XYZ Alignment Fixture | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-08-21 | 2017-09-29 | 2017-09-18 | Emma Pierce | Quality Plan 2017-002
TE82653 | 2790 XYZ Alignment Fixture | United States | Design | EDV | Initial | Full | Physical Move | Complete | Normal | 2017-09-11 | 2017-09-29 | 2017-09-15 | Emma Pierce | Quality Plan 2017-002
TE83064-03 | CPSM Final Test System | United States | Milford NPI | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-09-07 | 2017-09-29 | 2017-09-12 | Tyler Modelski | TE83064-02AUG2017-VAF
TE83064-04 | CPSM Final Test System | United States | Milford NPI | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-09-01 | 2017-09-29 | 2017-09-12 | Tyler Modelski | TE83064-02AUG2017-VAF
TE83064-06 | CPSM Final Test System | United States | Milford Clean Room | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-08-28 | 2017-09-29 | 2017-09-12 | Tyler Modelski | TE83064-02AUG2017-VAF
TE83064-07 | CPSM Final Test System | United States | Milford Clean Room | IQ | Requalification | Partial | TE Improvement | Complete | Normal | 2017-08-28 | 2017-09-29 | 2017-09-12 | Tyler Modelski | TE83064-02AUG2017-VAF
TE83064-08 | CPSM Final Test System | United States | Milford Clean Room | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-08-07 | 2017-09-29 | 2017-09-12 | Tyler Modelski | TE83064-02AUG2017-VAF
TE83064-09 | CPSM Final Test System | United States | Milford Clean Room | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-08-07 | 2017-08-31 | 2017-09-12 | Tyler Modelski | TE83064-02AUG2017-VAF
TE83064-18 | CPSM Final Test System | United States | Milford Clean Room | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-08-07 | 2017-09-29 | 2017-09-12 | Tyler Modelski | TE83064-02AUG2017-VAF
TE83064-Refrb | CPSM Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-08-07 | 2017-09-29 | 2017-09-12 | Tyler Modelski | TE83064-02AUG2017-VAF
TE83064-Refrb2 | CPSM Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-08-07 | 2017-09-29 | 2017-09-12 | Tyler Modelski | TE83064-02AUG2017-VAF
TE83064-Refrb | CPSM Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | Firmware | Complete | Normal | 2017-08-02 | 2017-08-31 | 2017-09-08 | Emma Pierce | TE83064-13-JUL-2017-VAF
TE83064-Refrb2 | CPSM Final Test System | United States | Milford NPI | IQ | Requalification | Partial | Firmware | Complete | Normal | 2017-07-14 | 2017-08-31 | 2017-09-08 | Emma Pierce | TE83064-13-JUL-2017-VAF
TE82449-2 | In-Line Degasser Final Instrument Tester | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-08-03 | 2017-08-31 | 2017-08-31 | Emma Pierce | Quality Plan 2017-002
TE82956 | ACQUITY High Temperature Column Heater Tester Veyron | United States | Design | TMV | Initial | Full |  | Complete | Normal | 2017-08-15 | 2017-09-29 | 2017-08-28 | Jim Stors
TE82943 | ACQUITY SDS Final Test System QSM | United States | Design | EDV | Initial | Full |  | Complete | Normal | 2017-06-01 | 2017-08-31 | 2017-08-25 | Tyler Modelski
VAL000996 | SACFA - Semi-Automated Cartridge Filter | United States | Milford Clean Room | PQ | Initial | Full |  | Complete | Urgent | 2017-08-08 | 2017-08-31 | 2017-08-23 | Tetiana Morse
TE82758-2 | 2414 Final Test System | United States | Milford Clean Room | TEQ | Initial | Full |  | Complete | Normal | 2016-06-01 | 2017-06-30 | 2017-08-22 | Tyler Modelski
VAL000996 | SACFA - Semi-Automated Cartridge Filter | United States | Milford Clean Room | EDV | Initial | Full |  | Complete | Urgent | 2017-07-10 | 2017-08-31 | 2017-08-21 | Tetiana Morse
VAL000996 | SACFA - Semi-Automated Cartridge Filter | United States | Milford Clean Room | IQ | Initial | Full |  | Complete | Urgent | 2017-08-01 | 2017-08-31 | 2017-08-21 | Tetiana Morse
TE82943-05 | ACQUITY SDS Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | Firmware | Complete | Normal | 2017-07-01 | 2017-08-31 | 2017-08-10 | Emma Pierce | TE82943-13-JUL-2017-VAF
TE82943-07 | ACQUITY SDS Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | Firmware | Complete | Normal | 2017-07-27 | 2017-08-31 | 2017-08-10 | Emma Pierce | TE82903-13-JUL-2017-VAF
TE82523-1 | Fluidics Tray Tester | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-08-03 | 2017-08-31 | 2017-08-07 | Emma Pierce | Quality Plan 2017-002
TE83064-19 | CPSM Final Test System | United States | Milford Clean Room | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-08-07 | 2017-08-07 | 2017-08-07 | Tyler Modelski | TE83064-02AUG2017-VAF
TE81729-2 | Universal Gas Pressure Tester | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-07-27 | 2017-08-31 | 2017-08-02 | Emma Pierce | Quality Plan 2017-002
VAL000995 | ACQUITY 15k Valve Press Process (2) Presses | United States | Milford Clean Room | IQ | Initial | Full |  | Complete | Normal | 2017-06-19 | 2017-07-31 | 2017-07-31 | Tyler Modelski
TE82956-1 | ACQUITY High Temperature Column Heater Tester | United States | Milford Refurb | IQ | Initial | Full |  | Complete | Normal | 2017-07-20 | 2017-08-31 | 2017-07-28 | Jim Stors
TE83064-03 | CPSM Final Test System | United States | Milford NPI | IQ | Requalification | Partial | Firmware | Complete | Normal | 2017-07-14 | 2017-07-31 | 2017-07-25 | Emma Pierce | TE83064-13-JUL-2017-VAF
TE83064-04 | CPSM Final Test System | United States | Milford NPI | IQ | Requalification | Partial | Firmware | Complete | Normal | 2017-07-14 | 2017-07-31 | 2017-07-25 | Emma Pierce | TE83064-13-JUL-2017-VAF
TE82956 | ACQUITY High Temperature Column Heater Tester | United States | Design | EDV | Initial | Full |  | Complete | Normal | 2017-06-15 | 2017-08-31 | 2017-07-21 | Jim Stors
TE82869-1 | Shuttle Tester | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-06-28 | 2017-07-31 | 2017-07-12 | Emma Pierce | Quality Plan 2017-002
TE82656 | 2690/2790 Syringe Drive Tester | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-06-26 | 2017-07-31 | 2017-07-06 | Emma Pierce | Quality Plan 2017-002
TE82765-1 | System Fluidics Organizer (SFO) Test System | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-06-20 | 2017-06-30 | 2017-06-30 | Jim Stors | Quality Plan 2017-002
VAL000992 | SigmaSure7 Change - GUID Config XML Test Equipment | United States | Milford Clean Room | IQ | Initial | Full | TE Improvement | Complete | Urgent | 2017-06-19 | 2017-07-31 | 2017-06-30 | Jim Stors | VAL000992-19JUN2017-VAF
TE82817-1 | PCM II Final Test System | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-06-20 | 2017-06-30 | 2017-06-29 | Emma Pierce | Quality Plan 2017-002
TE83026-4 | ACQUITY Column Manager Test System | United States | Milford NPI | IQ | Initial | Full |  | Complete | Normal | 2017-05-01 | 2017-07-31 | 2017-06-29 | Jim Stors | TE83026-26OCT2016-TEQA
TE84005 | Fraction Manager Analytical Final Test System | United States | Design | TEV | Initial | Full | New Product Intro | Complete | Normal | 2017-04-03 | 2017-06-30 | 2017-06-28 | Tyler Modelski
TE83064-06 | CPSM Final Test System - IVD | United States | Milford Clean Room | IQ | Requalification | Partial |  | Complete | Normal | 2017-06-19 | 2017-07-31 | 2017-06-22 | Tyler Modelski | TE83064-19JUN17-VAF
TE83064-07 | CPSM Final Test System | United States | Milford Clean Room | IQ | Requalification | Partial |  | Complete | Normal | 2017-06-19 | 2017-06-30 | 2017-06-22 | Tyler Modelski | TE83064-19JUN17-VAF
TE82029-2 | 510/590 Pump Tester | United States | Milford NPI | IQ | Initial | Full | Physical Move | Complete | Normal | 2017-06-13 | 2017-06-30 | 2017-06-21 | Jim Stors | Quality Plan 2017-002
TE82854-Refrb | ACQUITY Sample Manager Final Test | United States | Milford Refurb | IQ | Initial | Full |  | Complete | Normal | 2017-06-15 | 2017-06-30 | 2017-06-20 | Tyler Modelski
TE82903-01 | TUV Detector Final Test System | United States | Milford Refurb | IQ | Initial | Full |  | Complete | Normal | 2017-06-13 | 2017-07-31 | 2017-06-19 | Jim Stors
TE82943 | ACQUITY SDS Final Test System BSM | United States | Design | TEV | Initial | Full |  | Complete | Normal | 2017-05-01 | 2017-06-30 | 2017-06-19 | Tyler Modelski
TE83026 | ACQUITY Column Manager (CM-S) Veyron program | United States | Design | EDV | Initial | Full |  | Complete | Normal | 2017-05-01 | 2017-06-30 | 2017-06-12 | Jim Stors | TE83026-26OCT2016-TEQA
TE82854-4 | ACQUITY Sample Manager Final Test | United States | Milford Clean Room | IQ | Initial | Partial |  | Complete | Normal | 2017-05-25 | 2017-06-30 | 2017-06-06 | Tyler Modelski | TE82854-15MAY2017-VAF
TE82854-5 | ACQUITY Sample Manager Final Test | United States | Milford Clean Room | IQ | Initial | Partial |  | Complete | Normal | 2017-05-25 | 2017-06-30 | 2017-06-06 | Tyler Modelski | TE82854-15MAY2017-VAF
VAL000587 | Micromass Q-Tof micro Mass Spectrometer - SN: YA183 | United States | Milford Quality Lab | PVal | Initial | Full |  | Complete | Normal | 2015-05-26 | 2015-11-30 | 2017-05-26 | Tetiana Morse
TE82943-23 | ACQUITY SDS Final Test System | United States | Milford NPI | TEQ | Requalification | Full |  | Complete | Normal | 2017-02-01 | 2017-06-30 | 2017-05-25 | Tyler Modelski
TE83061-11 | ACQUITY High Pressure Leak Tester | United States | Milford Clean Room | IQ | Initial | Full |  | Complete | Urgent | 2017-05-10 | 2017-06-30 | 2017-05-19 | Jim Stors | TE83061-08-May-2017-TEQA
TE83061-12 | ACQUITY High Pressure Leak Tester | United States | Milford Clean Room | IQ | Initial | Full |  | Complete | Urgent | 2017-05-10 | 2017-06-30 | 2017-05-19 | Jim Stors | TE83061-08-May-2017-TEQA
TE83061-13 | ACQUITY High Pressure Leak Tester | United States | Milford Clean Room | IQ | Initial | Full |  | Complete | Urgent | 2017-05-10 | 2017-06-30 | 2017-05-19 | Jim Stors | TE83061-08-May-2017-TEQA
TE83061-14 | ACQUITY High Pressure Leak Tester | United States | Milford Clean Room | IQ | Initial | Full |  | Complete | Urgent | 2017-05-10 | 2017-06-30 | 2017-05-19 | Jim Stors | TE83061-08-May-2017-TEQA
VAL000936 | Excel Spreadsheet Tubing Restrict Calculator | United States | Milford Machine Shop | EDV | Initial | Full |  | Complete | Normal | 2017-05-01 | 2017-05-31 | 2017-05-19 | Tyler Modelski
TE83064-03 | CPSM Final Test System | United States | Milford NPI | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-04 | CPSM Final Test System | United States | Milford NPI | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-06 | CPSM Final Test System | United States | Milford Clean Room | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-07 | CPSM Final Test System | United States | Milford Clean Room | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-08 | CPSM Final Test System | United States | Milford Clean Room | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-09 | CPSM Final Test System | United States | Milford Clean Room | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-18 | CPSM Final Test System | United States | Milford Clean Room | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-19 | CPSM Final Test System | United States | Milford Clean Room | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-Refrb | CPSM Final Test System | United States | Milford Refurb | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-Refrb2 | CPSM Final Test System | United States | Milford Refurb | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE82920 | ACQUITY Active Check Valve Cartridge Tester | United States | Milford Clean Room | TEQA | Requalification | Partial |  | Complete | Normal | 2017-05-05 | 2017-05-31 | 2017-05-05 | Tyler Modelski | TE82903-04MAY17-TEQA
TE83057-1 | RI Detector Download-Configure Test Station | United States | Milford Clean Room | TEQ | Requalification | Partial |  | Complete | Normal | 2017-04-24 | 2017-05-31 | 2017-04-28 | Tyler Modelski | TE0083057-21APR17-TEQA
TE83057-3 | RI Detector Download-Configure Test Station | United States | Milford Clean Room | TEQ | Initial | Partial |  | Complete | Normal | 2017-04-24 | 2017-05-31 | 2017-04-28 | Tyler Modelski | TE83057-21APR17-TEQA
TE82920 | ACQUITY Active Check Valve Cartridge Tester | United States | Milford Clean Room | TEQA | Requalification | Partial |  | Complete | Normal | 2017-04-26 | 2017-05-31 | 2017-04-26 | Tyler Modelski | TE82903-26APR17-TEQA
TE83074-2 | ACQUITY H/I Class Actuator Tester | United States | Milford White Room | TEQ | Initial | Full |  | Complete | Normal | 2017-03-01 | 2017-04-28 | 2017-04-18 | Benjamin Scott | TE0083074-01-23FEB17-TEQA
TE82903 | TUV Detector Final Test System | United States | Design | TEV | Initial | Full |  | Complete | Normal | 2017-04-01 | 2017-04-28 | 2017-04-17 | James Stors
TE82943 | ACQUITY SDS Final Test System M-Class | United States | Design | TEV | Initial | Full |  | Complete | Normal | 2017-02-01 | 2017-04-28 | 2017-04-17 | Tyler Modelski
TE83074-1 | ACQUITY H/I Class Actuator Tester | United States | Milford White Room | TEQ | Initial | Full |  | Complete | Normal | 2017-04-01 | 2017-04-28 | 2017-04-04 | Benjamin Scott | TE0083074-01-23FEB17-TEQA
TE82736 | Alliance Empower Workstation | United States | Milford Clean Room | TEQA | Requalification | Partial |  | Complete | Normal | 2017-03-30 | 2017-03-31 | 2017-03-30 | Tetiana Morse | TE82736-30MAR17-TEQA
TE82758 | 2414 Final Test System | United States | Design | TEV | Initial | Full |  | Complete | Normal | 2017-02-01 | 2017-02-28 | 2017-03-30 | Ben Scott
TE84016 | 2690 Front Panel PCB Functional Test Fixture | United States | Design | TEV | Initial | Full |  | Complete | Normal | 2016-09-01 | 2017-03-31 | 2017-03-24 | Tyler Modelski
TE83068-1 | UPC2 BSM Actuator Tester | United States | Milford Clean Room | TEQA | Requalification | Partial |  | Complete | Normal | 2017-03-17 | 2017-03-31 | 2017-03-21 | Benjamin Scott | TE0083068-01-03MAR17-TEQA
TE84010-2 | ARC Actuator Test System | United States | Milford White Room | TEQ | Initial | Full |  | Complete | Normal | 2017-02-01 | 2017-03-31 | 2017-03-17 | Jim Stors
TE84010 | ARC Actuator Test System | United States | Design | TEV | Initial | Full |  | Complete | Normal | 2017-01-02 | 2017-02-28 | 2017-02-28 | James Stors
TE83064-03 | CPSM Final Test System | United States | Milford NPI | TEQA | Requalification | Partial | Firmware | Complete | Normal | 2017-02-13 | 2017-02-28 | 2017-02-13 | Tyler Modelski | TE83064-31JAN17-TEQA
TE83064-04 | CPSM Final Test System | United States | Milford NPI | TEQA | Requalification | Partial | Firmware | Complete | Normal | 2017-02-13 | 2017-02-28 | 2017-02-13 | Tyler Modelski | TE83064-31JAN17-TEQA
TE83064-06 | CPSM Final Test System | United States | Milford Clean Room | TEQA | Requalification | Partial | Firmware | Complete | Normal | 2017-02-13 | 2017-02-28 | 2017-02-13 | Tyler Modelski | TE83064-31JAN17-TEQA
TE83064-07 | CPSM Final Test System | United States | Milford Clean Room | TEQA | Requalification | Partial | Firmware | Complete | Normal | 2017-02-13 | 2017-02-28 | 2017-02-13 | Tyler Modelski | TE83064-31JAN17-TEQA
TE83064-08 | CPSM Final Test System | United States | Milford Clean Room | TEQA | Requalification | Partial | M-Class Micro FL Firware | Complete | Normal | 2017-02-13 | 2017-02-28 | 2017-02-13 | Tyler Modelski | TE83064-31JAN17-TEQA
TE83064-09 | CPSM Final Test System | United States | Milford Clean Room | TEQA | Requalification | Partial | Firmware | Complete | Normal | 2017-02-13 | 2017-02-28 | 2017-02-13 | Tyler Modelski | TE83064-31JAN17-TEQA
TE83064-Refrb | CPSM Final Test System | United States | Milford Refurb | TEQA | Requalification | Partial | Firmware | Complete | Normal | 2017-02-13 | 2017-02-28 | 2017-02-13 | Tyler Modelski | TE83064-31JAN17-TEQA
TE83064-Refrb2 | CPSM Final Test System | United States | Milford Refurb | TEQA | Requalification | Partial | Firmware | Complete | Normal | 2017-02-13 | 2017-02-13 | 2017-02-13 | Tyler Modelski | TE83064-31JAN17-TEQA
TE83064-18 | CPSM Final Test System | United States | Milford Clean Room | TEQ | Requalification | Full |  | Complete | Normal | 2016-12-26 | 2017-02-28 | 2017-02-08 | Tyler Modelski | TE83064-TEQA
TE83064-19 | CPSM Final Test System | United States | Milford Clean Room | TEQ | Requalification | Full |  | Complete | Normal | 2016-12-26 | 2017-02-28 | 2017-02-08 | Tyler Modelski | TE83064-TEQA
TE82995-1 | ACQUITY CPSM RTZ Assembly Test System | United States | Milford Clean Room | TEQ | Requalification | Full |  | Complete | Urgent | 2016-12-01 | 2017-02-28 | 2017-02-01 | James Stors | TE82995-12DEC2016-TEQA
TE83080 | ACQUITY CM-30S Test System | United States | Design | EDV | Initial | Full |  | Complete | Normal | 2017-01-02 | 2017-01-31 | 2017-01-31 | Tetiana Morse | TE0083080-1-04JAN17-TEQA
TE83064 | CPSM Final Test System - IVD | United States | Design | TEV | Initial | Partial |  | Complete | Normal | 2017-12-01 | 2017-02-28 | 2017-01-30 | Tyler Modelski
TE82995-4 | ACQUITY CPSM RTZ Assembly Test System | United States | Milford Clean Room | TEQ | Requalification | Full |  | Complete | Urgent | 2017-01-02 | 2017-01-31 | 2017-01-25 | Jim Stors | TE82995-12DEC2016-TEQA
TE83064-06 | CPSM Final Test System | United States | Milford Clean Room | TEQ | Requalification | Full |  | Complete | Normal | 2016-12-21 | 2017-01-01 | 2017-01-10 | Benjamin Scott | TE83064-TEQA
TE83064-03 | CPSM Final Test System | United States | Milford NPI | TEQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-01-01 | 2017-01-31 | 2017-01-06 | Tyler Modelski | TE83064-21DEC16-TEQA
TE83064-04 | CPSM Final Test System | United States | Milford NPI | TEQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-01-01 | 2017-01-31 | 2017-01-06 | Tyler Modelski | TE83064-21DEC16-TEQA
TE83064-08 | CPSM Final Test System | United States | Milford Clean Room | TEQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-01-02 | 2017-01-31 | 2017-01-06 | Tyler Modelski | TE83064-21DEC16-TEQA
TE83064-09 | CPSM Final Test System | United States | Milford Clean Room | TEQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-01-02 | 2017-01-31 | 2017-01-06 | Tyler Modelski | TE83064-21DEC16-TEQA
TE83064-Refrb | CPSM Final Test System | United States | Milford Refurb | TEQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-01-02 | 2017-01-31 | 2017-01-06 | Tyler Modelski | TE83064-21DEC16-TEQA
TE83064-Refrb2 | CPSM Final Test System | United States | Milford Refurb | TEQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-01-01 | 2017-01-31 | 2017-01-06 | Tyler Modelski | TE83064-21DEC16-TEQA
TE82736 | Alliance Empower Workstation | United States | Milford Clean Room | TEQA | Initial | Partial |  | Complete | Normal | 2017-01-02 | 2017-01-06 | 2017-01-05 | Jim Stors | TE82736-05JAN2017-TEQA
TE82897 | ACQUITY XYZ Tester | United States | Milford Clean Room | TEQA | Requalification | Partial |  | Complete | Normal | 2017-01-04 | 2017-01-31 | 2017-01-05 | Tyler Modelski | TE82897-04JAN17-VAF
TE83064 | CPSM Final Test System | United States | Design | TEV | Requalification | Partial |  | Complete | Normal | 2017-01-03 | 2017-01-31 | 2017-01-05 | Tyler Modelski | TE83064-21DEC16-TEQA
TE83064-07 | CPSM Final Test System | United States | Milford Clean Room | TEQ | Requalification | Full |  | Complete | Normal | 2016-12-15 | 2017-01-31 | 2017-01-04 | Benjamin Scott | TE83064-TEQA
TE84021-1 | Arc Metering Syringe Drive Tester | United States | Milford NPI | TEQ | Initial | Full |  | Complete | Normal | 2016-12-01 | 2016-12-30 | 2016-12-27 | Tyler Modelski
TE84033-1 | nanoACQUITY Fitting Leak Tester | United States | Milford Tubing Assembly | TEQ | Initial | Full |  | Complete | Urgent | 2016-11-01 | 2016-12-30 | 2016-12-22 | Jim Stors
VAL000639 | Finger Tight Fitting Crimper - SN: 999042491 | United States | Milford Tubing Assembly | PVal | Initial | Full |  | Complete | Normal | 2016-09-01 | 2016-12-30 | 2016-12-22 | Jim Stors | VAL000639-PVAF-999042491
TE83060-2 | ACQUITY RI Detector Response Test System | United States | Milford Clean Room | TEQ | Initial | Full |  | Complete | Normal | 2016-12-14 | 2016-12-30 | 2016-12-20 | Tyler Modelski | TE83060-13DEC16-TEQA
TE84021 | Arc Metering Syringe Drive Tester | United States | Design | TEV | Initial | Full |  | Complete | Normal | 2016-10-03 | 2017-01-31 | 2016-12-20 | Tyler Modelski
TE83064-08 | CPSM Final Test System | United States | Milford Clean Room | TEQ | Initial | Full |  | Complete | Normal | 2016-11-29 | 2016-12-30 | 2016-12-12 | Tyler Modelski | TE83064-TEQA
TE83064-09 | CPSM Final Test System | United States | Milford Clean Room | TEQ | Requalification | Full |  | Complete | Normal | 2016-11-29 | 2016-12-30 | 2016-12-07 | Tyler Modelski | TE83064-TEQA
TE82758-1 | 2414 Final Test System | United States | Milford Clean Room | TEQ | Requalification | Partial |  | Complete | Normal | 2016-10-05 | 2016-10-31 | 2016-11-30 | Tyler Modelski
VAL000701 | Milli-Q Gradient A10 Water Filtration System | United States | Milford NPI | PVal | Initial | Full |  | Complete | Normal | 2016-07-01 | 2016-08-31 | 2016-11-14 | Tetiana Morse
TE83064-Refrb2 | CPSM Final Test System | United States | Milford Refurb | TEQ | Requalification | Full |  | Complete | Normal | 2016-10-28 | 2016-11-30 | 2016-11-04 | Tyler Modelski | TE83064-TEQA
TE83064-03 | CPSM Final Test System | United States | Milford NPI | TEQ | Requalification | Full |  | Complete | Normal | 2016-09-01 | 2016-11-30 | 2016-11-03 | Tyler Modelski | TE83064-TEQA
TE83064-04 | CPSM Final Test System | United States | Milford Refurb | TEQ | Requalification | Full |  | Complete | Normal | 2016-11-01 | 2016-11-01 | 2016-11-03 | Tyler Modelski | TE83064-TEQA
TE83057-1 | RI Detector Download-Configure Test Station | United States | Milford Clean Room | TEQ | Requalification | Partial | TE Improvement | Complete | Normal | 2016-10-10 | 2016-11-30 | 2016-10-31 | Tyler Modelski | TE83057-TEQA-10Oct2016
TE83057-3 | RI Detector Download-Configure Test Station | United States | Milford Clean Room | TEQ | Requalification | Partial | TE Improvement | Complete | Normal | 2016-10-10 | 2016-11-30 | 2016-10-31 | Tyler Modelski | TE83057-TEQA-10Oct2016
TE82995-1 | ACQUITY CPSM RTZ Assembly Test System | United States | Milford Clean Room | TEQ | Requalification | Full |  | Complete | Urgent | 2016-10-27 | 2016-11-30 | 2016-10-27 | Jim Stors | TE82995-1-TEQA 25 OCT 2016
TE83064-Refrb | CPSM Final Test System | United States | Milford Refurb | TEQ | Requalification | Full |  | Complete | Normal | 2016-10-25 | 2016-11-30 | 2016-10-27 | Tyler Modelski | TE83064-TEQA
TE83064 | CPSM Final Test System - Non IVD | United States | Design | TEV | Requalification | Full |  | Complete | Normal | 2015-04-01 | 2016-10-31 | 2016-10-24 | Tyler Modelski | TE83064-TEQA
TE82758-1 | 2414 Final Test System | United States | Milford Clean Room | TEQ | Requalification | Partial |  | Complete | Normal | 2016-09-08 | 2016-09-30 | 2016-09-28 | Tyler Modelski
TE84013 | 2x9x Column Heater/Cooler PCB Funtional Test Fixture | United States | Design | TEV | Initial | Full |  | Complete | Normal | 2016-08-01 | 2016-08-31 | 2016-09-08 | Tyler Modelski
VAL000591 | So-Low DHW20-20MDP Freezer - SN: 1011396 | United States | Milford Quality Lab | PVal | Initial | Full |  | Complete | Normal | 2016-07-20 | 2016-08-31 | 2016-08-18 | Tetiana Morse | VAL000591-PVAF-2016
TE82995-1 | ACQUITY CPSM RTZ Assembly Test System | United States | Milford Clean Room | TEQ | Initial | Full |  | Complete | Urgent | 2016-08-01 | 2016-08-31 | 2016-08-04 | Jim Stors
VAL000578 | Botron Elite ESD Tester - Model B88025 | United States | Milford NPI | PVal | Initial | Full |  | Complete | Normal | 2016-05-09 | 2016-08-31 | 2016-08-04 | Jim Stors
TE82798-2 | ELSD-2424 Final Pre-Test Station | United States | Milford Clean Room | TEQ | Requalification | Partial |  | Complete | Urgent | 2016-07-25 | 2016-08-31 | 2016-08-02 | Tetiana Morse
TE82995-4 | ACQUITY CPSM RTZ Assembly Test System | United States | Milford Clean Room | TEQ | Initial | Full |  | Complete | Urgent | 2016-07-25 | 2016-08-31 | 2016-08-02 | Jim Stors | TE0082995-4-TEQA-22JUL2016
TE82995-1 | ACQUITY CPSM RTZ Assembly Test System | United States | Milford Clean Room | TEQ | Requalification | Full |  | Complete | Urgent | 2016-08-01 | 2016-08-31 | 2016-08-01 | Jim Stors | TE0082995-1-TEQA-15AUG2016
TE82798 | ELSD-2424 Final Pre-Test Station | United States | Design | TEV | Requalification | Partial |  | Complete | Normal | 2015-09-01 | 2016-07-29 | 2016-07-13 | Tyler Modelski
TE82798-2 | ELSD-2424 Final Pre-Test Station | United States | Milford Clean Room | TEQ | Requalification | Partial |  | Complete | Urgent | 2016-07-12 | 2016-07-29 | 2016-07-13 | Tyler Modelski | TE82798-2-TEQA-3OCT2016
TE82920 | Acuity Active Check Valve Cartridge Tester | United States | Design | TEV | Initial | Full |  | Complete | Normal | 2016-07-01 | 2016-07-29 | 2016-07-08 | Tyler Modelski | TE82903-TEQA
TE82920 | ACQUITY Active Check Valve Cartridge Tester | United States | Milford Clean Room | TEQ | Initial | Full |  | Complete | Normal | 2016-06-27 | 2016-08-31 | 2016-07-08 | Tyler Modelski | TE82903-10-TEQA
VAL000583 | Milli-Q Integral 3 Water Filtration System | United States | Milford Quality Lab | PVal | Initial | Full |  | Complete | Normal | 2016-05-23 | 2016-07-29 | 2016-07-01 | Tetiana Morse
TE82660 | 2690D Test Spreadsheet | United States | Milford Refurb | PVal | Initial | Full |  | Complete | Normal | 2016-06-01 | 2016-06-30 | 2016-06-22 | Tyler Modelski
TE82799-1 | ELSD 2420 Lamp Alignment Assembly | United States | Milford Clean Room | TEQ | Initial | Full |  | Complete | Urgent | 2016-06-15 | 2016-06-30 | 2016-06-17 | Jim Stors
TE82799 | ELSD 2420 Lamp Alignment Assembly | United States | Design | TEV | Initial | Full |  | Complete | Normal | 2016-06-01 | 2016-06-30 | 2016-06-16 | Jim Stors
VAL000539 | Milli-Q Gradient A10 Water Filtration System | United States | Milford Refurb | PVal | Initial | Full |  | Complete | Normal | 2015-12-21 | 2016-03-31 | 2016-06-06 | Tetiana Morse
VAL000540 | Milli-Q Academic Water Filtration System | United States | Milford NPI | PVal | Initial | Full |  | Complete | Normal | 2015-12-21 | 2016-02-29 | 2016-06-06 | Tetiana Morse | PVAF-WAT124-2015
TE83057-3 | RI Detector Download-Configure Test Station | United States | Milford Clean Room | TEQ | Initial | Full |  | Complete | Normal | 2016-04-27 | 2016-06-30 | 2016-06-02 | Tyler Modelski | TE83057-3-TEQA
VAL000568 | Sensitech ColdStream Site Temp Monitoring System | United States | GDC | PVal | Initial | Full |  | Complete | Normal | 2015-02-02 | 2015-05-29 | 2016-05-31 | Tetiana Morse | VAL000568-PVAF-2016
VAL000527 | So-Low DHW20-20MDP Freezer - SN: 0708172 | United States | GDC | PVal | Initial | Full |  | Complete | Normal | 2014-08-10 | 2016-05-20 | 2016-05-20 | Tetiana Morse
VAL000565 | So-Low DHW20-17SMDP Freezer - SN: 1011396 | United States | GDC | PVal | Initial | Full |  | Complete | Normal | 2015-04-01 | 2014-04-30 | 2016-05-20 | Tetiana Morse | VAL000565-PVAF-2016
VAL000566 | Bally 3678-3-P Walk-In Cooler - SN: DX1007965-01 | United States | GDC | PVal | Initial | Full |  | Complete | Normal | 2015-01-01 | 2015-04-30 | 2016-05-20 | Tetiana Morse | VAL000566-2016
VAL000567 | So-Low DH30-49SDSS Freezer - SN: 11211862 | United States | GDC | PVal | Initial | Full |  | Complete | Normal | 2015-01-01 | 2015-04-30 | 2016-05-20 | Tetiana Morse | VAL000567-PVAF-2016
TE82758-1 | 2414 Final Test System | United States | Milford Clean Room | TEQ | Initial | Full |  | Complete | Normal | 2016-04-01 | 2016-04-29 | 2016-04-15 | Tyler Modelski
TE82798-2 | ELSD-2424 Final Pre-Test Station | United States | Milford Clean Room | TEQ | Initial | Full |  | Complete | Normal | 2015-10-09 | 2015-12-31 | 2016-04-01 | Tetiana Morse
VAL001103 | 2414 Response Test Empower Work Station | United States | Milford Clean Room | TEQ | Initial | Full | New Product Intro | Complete | Normal | 2016-03-01 | 2016-04-29 | 2016-04-01 | Tyler Modelski
VAL000486 | Residual Gas Analyzer TB685C | United States | Milford Machine Shop | PVal | Initial | Full | New / Duplicate | Complete | Normal | 2015-12-01 | 2016-02-29 | 2016-03-09 | Tetiana Morse | PVAF-TB685C-2015
VAL000577 | Botron Elite ESD Tester - Model B88025 | United States | Milford Refurb | PVal | Initial | Full |  | Complete | Normal | 2015-07-30 | 2016-01-29 | 2016-02-16 | Tetiana Morse | PVAF-ESD93267-2015
TE82943 | ACQUITY SDS Final Test System BSM | United States | Design | PVal | Initial | Full |  | Complete | Normal | 2011-09-01 | 2012-03-30 | 2016-02-12 | Tetiana Morse
VAL000506 | Milli-Q Advantage A-10 Water Filtration System | United States | Milford White Room | PVal | Initial | Full |  | Complete | Normal | 2015-12-18 | 2016-03-31 | 2016-02-03 | Tetiana Morse | PVAF-WAT122-2015
VAL000573 | Semi Automated Mixer Assembly (SAMA) | United States | Milford Clean Room | PVal | Initial | Full |  | Complete | Normal | 2015-04-01 | 2015-09-30 | 2016-01-20 | Tanya Morse | PVAF-WAT053-2015
VAL000514 | Botron Elite Model B88000 ESD Tester | United States | Milford Clean Room | PVal | Initial | Full |  | Complete | Normal | 2015-04-01 | 2015-12-31 | 2015-12-18 | Tetiana Morse
VAL000521 | So-Low DH30-49DSS Freezer - SN: 11513548 | United States | GDC | PVal | Initial | Full |  | Complete | Normal | 2015-11-13 | 2015-12-31 | 2015-11-20 | Tetiana Morse | PVAF-11513548-2015
VAL000574 | Flow Cell Tube Cutting Machine | United States | Milford Tubing Assembly | PVal | Initial | Full |  | Complete | Normal | 2015-04-01 | 2015-09-30 | 2015-11-16 | Tetiana Morse
TE83064-04 | CPSM Final Test System | United States | Milford NPI | LEQ | Initial | Full |  | Complete | Normal | 2015-01-01 | 2015-04-30 | 2015-11-15 | Tetiana Morse
TE82798 | ELSD-2424 Final Pre-Test Station | United States | Design | TEV | Initial | Partial |  | Complete | Normal | 2016-07-01 | 2015-10-30 | 2015-10-15 | Tyler Modelski
VAL000575 | Baker Horizontal Lar Flow Hood - E6-6320 | United States | Milford Kitting | PVal | Initial | Full |  | Complete | Normal | 2015-07-20 | 2016-09-30 | 2015-09-09 | Tetiana Morse | VAF-WAT121-2015
VAL000576 | Cleatech Laminar Flow Hood | United States | Milford Machine Shop | PVal | Initial | Full |  | Complete | Normal | 2015-01-26 | 2015-05-29 | 2015-07-08 | Tetiana Morse | VAF-WAT054-2015
VAL000533 | So-Low DHW20-20MDP Freezer - SN: 0708173 | United States | GDC | PVal | Initial | Full |  | Complete | Normal | 2016-05-20 | 2014-05-20 | 2015-05-20 | Tetiana Morse | VAL000533-PVAF-2016
TE84002 | Trap Valve Manager Final Test System | United States | Design | TEV | Initial | Full | New Product Intro | Complete | Normal | 2015-03-02 | 2015-05-29 | 2015-05-15 | Tetiana Morse
TE82943-05 | ACQUITY SDS Final Test System | United States | Milford Refurb | LEQ | Initial | Full |  | Complete | Normal | 2014-11-03 | 2015-02-27 | 2015-05-12 | Tetiana Morse
TE82943-23 | ACQUITY SDS Final Test System | United States | Milford NPI | LEQ | Initial | Full |  | Complete | Normal | 2014-12-01 | 2015-03-31 | 2015-05-12 | Tetiana Morse
TE82903-06 | ACQUITY SDS Final Test System | United States | Milford Clean Room | LEQ | Initial | Full |  | Complete | Normal | 2014-12-01 | 2015-02-27 | 2015-05-06 | Tetiana Morse
TE82943-02 | ACQUITY SDS Final Test System | United States | Milford Clean Room | LEQ | Initial | Full |  | Complete | Normal | 2014-11-03 | 2015-02-27 | 2015-05-06 | Tetiana Morse
TE82943-03 | ACQUITY SDS Final Test System | United States | Milford NPI | LEQ | Initial | Full |  | Complete | Normal | 2014-11-03 | 2015-02-27 | 2015-05-06 | Tetiana Morse
TE82943-04 | ACQUITY SDS Final Test System | United States | Milford Clean Room | LEQ | Initial | Full |  | Complete | Normal | 2014-11-03 | 2015-02-27 | 2015-05-06 | Tetiana Morse
TE82943-07 | ACQUITY SDS Final Test System | United States | Milford Refurb | LEQ | Initial | Full |  | Complete | Normal | 2014-11-03 | 2015-02-27 | 2015-05-06 | Tetiana Morse
TE82943-08 | ACQUITY SDS Final Test System | United States | Milford Clean Room | LEQ | Initial | Full |  | Complete | Normal | 2014-11-03 | 2015-02-27 | 2015-05-06 | Tyler Modelski
TE82943-09 | ACQUITY SDS Final Test System | United States | Milford NPI | LEQ | Initial | Full |  | Complete | Normal | 2014-11-03 | 2015-02-27 | 2015-05-06 | Tetiana Morse
TE82806-2 | 717 Final Test System | United States | Milford Refurb | LEQ | Initial | Full |  | Complete | Normal | 2014-10-01 | 2014-12-31 | 2015-04-01 | Tetiana Morse
TE83064-03 | CPSM Final Test System | United States | Milford NPI | LEQ | Initial | Full |  | Complete | Normal | 2015-01-01 | 2015-03-31 | 2015-02-11 | Tetiana Morse
TE83059-1 | ACQUITY RI Noise and Drift Test System | United States | Milford Clean Room | LEQ | Initial | Full |  | Complete | Normal | 2015-01-01 | 2015-03-31 | 2015-02-06
TE83060-2 | ACQUITY RI Detector Response Test System | United States | Milford Clean Room | LEQ | Initial | Full |  | Complete | Normal | 2015-01-01 | 2015-03-31 | 2015-02-06 | Tetiana Morse
VAL000569 | Fisher Scientific Isotemp Fridge Model 13-986-227R | United States | Milford Quality Lab | PVal | Initial | Full |  | Complete | Normal | 2015-11-24 | 2015-12-31 | 2014-12-22 | Tetiana Morse
VAL000984 | Fisher Scientific Isotemp Fridge Model 148-QA2 | United States | Milford Quality Lab | PVal | Initial | Full |  | Complete | Normal | 2014-11-03 | 2014-12-31 | 2014-12-22 | Tetiana Morse
TE82534-2 | 515 Pump Final Test System | United States | Milford Refurb | LEQ | Initial | Full |  | Complete | Normal | 2014-10-03 | 2015-01-30 | 2014-11-18 | Tetiana Morse
TE82854-Refrb | ACQUITY Sample Manager Final Test | United States | Milford Refurb | LEQ | Initial | Full |  | Complete | Normal | 2014-10-01 | 2014-11-28 | 2014-11-07 | Tetiana Morse
TE83064-Refrb | CPSM Final Test System | United States | Milford Refurb | LEQ | Initial | Full |  | Complete | Normal | 2014-11-07 | 2014-11-28 | 2014-11-07 | Tetiana Morse
TE82865-Refrb | Sample Organizer/ CPSO Final Test System | United States | Milford Refurb | LEQ | Initial | Full |  | Complete | Normal | 2014-10-01 | 2014-11-28 | 2014-11-03 | Tetiana Morse
TE82943 | ACQUITY SDS Final Test System | United States | Design | PVal | Initial | Full |  | Complete | Normal | 2011-07-01 | 2012-07-31 | 2013-01-04 | Tetiana Morse
TE82854 | ACQUITY Classic Sample Manager Final Test System | United States | Design | PVal | Initial | Full |  | Complete | Normal | 2015-04-01 | 2010-10-29 | 2012-10-08 | Tetiana Morse
TE82865 | Sample Organizer/ CPSO Final Test System | United States | Design | PVal | Initial | Full |  | Complete | Normal | 2010-01-01 | 2011-09-08 | 2012-09-27 | Tetiana Morse
TE82705 | 1525µ Binary HPLC Pump Final Test System | United States | Design | PVal | Initial | Full |  | Complete | Normal | 2010-07-01 | 2011-12-30 | 2010-11-11 | Tetiana Morse
TE82943-02 | ACQUITY SDS Final Test System | United States | Milford White Room | IQ | Requalification | Partial | New Product Intro | Pending | Urgent | 2018-03-28 |  |  | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-04 | ACQUITY SDS Final Test System | United States | Milford White Room | IQ | Requalification | Partial | New Product Intro | Pending | Urgent | 2018-03-28 |  |  | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-05 | ACQUITY SDS Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | New Product Intro | Pending | Urgent | 2018-03-28 |  |  | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-06 | ACQUITY SDS Final Test System | United States | Milford White Room | IQ | Requalification | Partial | New Product Intro | Pending | Urgent | 2018-03-28 |  |  | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-07 | ACQUITY SDS Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | New Product Intro | Pending | Urgent | 2018-03-28 |  |  | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-08 | ACQUITY SDS Final Test System | United States | Milford White Room | IQ | Requalification | Partial | New Product Intro | Pending | Urgent | 2018-03-28 |  |  | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-25 | ACQUITY SDS Final Test System | United States | Milford RDEL | IQ | Initial | Full | New / Duplicate | Pending | Normal |  | 2018-06-29 |  | Tetiana Morse | Submission Form
TE82956 | ACQUITY High Temperature Column Heater Tester | United States | Design | EDV | Initial | Full | VMP Catch Up | Pending | Normal |  | 2018-03-30 |  | Jim Stors | Need submission form
TE82984 | ACQUITY UPLC Colulmn Manager Test System | United States | Design | EDV | Initial | Full | VMP Catch up | Pending | Normal | 2017-12-15 | 2018-06-29 |  | Tetiana Morse
TE83013 | ACQUITY H-Class CH-A Test System | United States | Design | EDV | Initial | Full | VMP Catch Up | Pending | Normal | 2018-03-19 | 2018-04-13 |  | Jim Stors | Need Submission form
TE83013-3 | ACQUITY H-Class CH-A Test System | United States | Milford Refurb | IQ | Initial | Full | VMP Catch up | Pending | Normal | 2018-01-01 | 2018-03-30 |  | Jim Stors
TE83026 | ACQUITY Column Manager Test-I and H class | United States | Design | EDV | Initial | Full | VMP Catch up | Pending | Normal | 2018-05-01 | 2018-06-29 |  | Jim Stors
TE83060-2 | ACQUITY RI Detector Response Test System | United States | Milford Clean Room | IQ | Requalification | Partial |  | Pending | Normal
TE83064-03 | CPSM Final Test System | United States | Milford NPI | IQ | Requalification | Partial | New Product Intro | Pending | Normal | 2018-04-02 |  |  | Emma Pierce | TE83064-02APR2018-VAF
TE83064-04 | CPSM Final Test System | United States | Milford NPI | IQ | Requalification | Partial | New Product Intro | Pending | Normal | 2018-04-02 |  |  | Emma Pierce | TE83064-02APR2018-VAF
TE83064-06 | CPSM Final Test System | United States | Milford White Room | IQ | Requalification | Partial | New Product Intro | Pending | Normal | 2018-04-02 |  |  | Emma Pierce | TE83064-02APR2018-VAF
TE83064-07 | CPSM Final Test System | United States | Milford White Room | IQ | Requalification | Partial | New Product Intro | Pending | Normal | 2018-04-02 |  |  | Emma Pierce | TE83064-02APR2018-VAF
TE83064-09 | CPSM Final Test System | United States | Milford White Room | IQ | Requalification | Partial | New Product Intro | Pending | Normal | 2018-04-02 |  |  | Emma Pierce | TE83064-02APR2018-VAF
TE83064-16 | CPSM Final Test System | United States | Venture GES | IQ | Requalification | Partial | New Product Intro | Pending | Normal | 2018-04-02 |  |  | Emma Pierce | TE83064-02APR2018-VAF
TE83064-17 | CPSM Final Test System | United States | Venture GES | IQ | Requalification | Partial | New Product Intro | Pending | Normal | 2018-04-02 |  |  | Emma Pierce | TE83064-02APR2018-VAF
TE83064-18 | CPSM Final Test System | United States | Milford White Room | IQ | Requalification | Partial | New Product Intro | Pending | Normal | 2018-04-02 |  |  | Emma Pierce | TE83064-02APR2018-VAF
TE83064-RDEL | CPSM Final Test System | United States | Milford RDEL | IQ | Initial | Full | New / Duplicate | Pending | Normal |  | 2018-06-29 |  | Tetiana Morse | Submission Form
TE83064-REFRB | CPSM Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | New Product Intro | Pending | Normal | 2018-04-02 |  |  | Emma Pierce | TE83064-02APR2018-VAF
TE83064-REFRB2 | CPSM Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | New Product Intro | Pending | Normal | 2018-04-02 |  |  | Emma Pierce | TE83064-02APR2018-VAF
TE83082-1 | WFMA Delay Coil, Tube, and Needle Characterization | United States | Milford NPI | IQ | Initial | Full | New Product Intro | Pending | Normal | 2017-12-15 | 2018-06-29 |  | Emma Pierce
TE84040-1 | MSV Leak Test System | United States | Milford White Room | IQ | Initial | Full | New Product Intro | Pending | Normal |  | 2018-06-29 |  | Tyler Modelski | Submission Form
TE84040-1 | MSV Leak Test System | United States | Milford White Room | TMV | Initial | Full | New Product Intro | Pending | Normal |  | 2018-06-29 |  | Tyler Modelski | Submission Form
TE84040-1 | MSV Leak Test System | United States | Milford White Room | EDV | Initial | Full | New Product Intro | Pending | Normal |  | 2018-06-22 |  | Tyler Modelski | Submission Form
VAL001011 | Elma Automated Cleaning System | United States | Milford Critical Clean | IQ | Initial | Full | Critical Clean | Pending | Normal | 2017-10-05 | 2018-08-31 |  | Jim Stors
VAL001137 | Manual Passivation Line | United States | Milford Critical Clean | IQ | Initial | Full | Critical Clean | Pending | Normal | 2017-11-01 | 2018-10-01 |  | Jim Stors
VAL001139 | Pero R0 - Conventional | United States | Milford Critical Clean | IQ | Initial | Full | Critical Clean | Pending | Normal | 2017-11-01 | 2018-05-31 |  | Jim Stors
VAL001141 | Pero R0 - Valve Cell | United States | Milford Critical Clean | IQ | Initial | Full | Critical Clean | Pending | Normal | 2017-11-01 | 2018-05-31 |  | Jim Stors
VAL001142 | Zeiss Duramax CMM for NC | United States | Milford Machine Shop | IQ | Initial | Full | New / Duplicate | Pending | Normal | 2018-01-10 | 2018-06-01 |  | Emma Pierce
VAL001143 | Zeiss Duramax CMM for Turning - SN:190544 | United States | Milford Machine Shop | TMV | Initial | Full | New / Duplicate | Pending | Normal | 2018-02-09 | 2018-03-31 |  | Emma Pierce
VAL001144 | Zeiss Surfcom NEX 100SD-13-N | United States | Milford Machine Shop | IQ | Initial | Full | New / Duplicate | Pending | Normal | 2018-01-10 | 2018-06-01 |  | Tetiana Morse
VAL001145 | Keyence Vision System | United States | Milford Machine Shop | IQ | Initial | Full | New / Duplicate | Pending | Normal | 2018-01-10 | 2018-06-01 |  | Tetiana Morse
VAL001216 | Liquid Particle Counter-SLS-2000 syringe sampler with the Liquilaz E20P liquid particle counter | United States | Milford Quality Lab | IQ | Initial | Full | New / Duplicate | Pending | Normal |  | 2018-09-28 |  | Lexi Crowell | Submission Form
VAL001216 | Liquid Particle Counter-SLS-2000 syringe sampler with the Liquilaz E20P liquid particle counter | United States | Milford Quality Lab | TMV | Initial | Full | New / Duplicate | Pending | Normal |  | 2018-09-28 |  | Lexi Crowell | Submission Form
TE81490 | Temp X-Ducer tester | United States | Milford White Room | IQ | Initial | Full | Physical Move | Active | Normal | 2018-01-18 | 2018-03-30 |  | Jim Stors | TE0081490-17JAN2018-VAF
TE81491 | Steel Column Heater, M600 assembly tester | United States | Milford White Room | IQ | Initial | Full | Physical Move | Active | Normal | 2018-01-18 | 2018-03-30 |  | Jim Stors | TE0081491-17JAN2018-VAF
TE82878-1 | ACQUITY Fluidics Tray Tester | United States | Milford White Room | IQ | Initial | Full | Physical Move | Active | Urgent | 2018-04-05 | 2018-04-20 |  | Jim Stors | VAL001218-26MAR18-VAF
TE82878-2 | ACQUITY Fluidics Tray Tester | United States | Milford White Room | IQ | Initial | Full | Physical Move | Active | Urgent | 2018-04-16 | 2018-04-27 |  | Jim Stors | VAL001218-26MAR18-VAF
TE82891-1 | Auto Tune Syringe Pump Tester | United States | Milford White Room | IQ | Initial | Full | Physical Move | Active | Urgent | 2018-04-16 | 2018-04-27 |  | Jim Stors | VAL001218-26MAR18-VAF
TE82891-2-1 | Metering MSV Tester | United States | Milford White Room | IQ | Initial | Full | Physical Move | Active | Urgent | 2018-04-16 | 2018-04-27 |  | Jim Stors | VAL001218-26MAR18-VAF
TE82943-05 | ACQUITY SDS Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | Firmware | Active | Normal | 2018-02-21 | 2018-04-30 |  | Jim Stors | TE82943-19JAN2018-VAF
TE82943-07 | ACQUITY SDS Final Test System | United States | Milford Refurb | IQ | Requalification | Partial | Firmware | Active | Normal | 2018-02-21 | 2018-04-30 |  | Jim Stors | TE82943-19JAN2018-VAF
TE82949-1 | Barb Fitting Inspection Fixture | United States | Milford White Room | IQ | Initial | Full | Physical Move | Active | Urgent | 2018-04-16 | 2018-04-27 |  | Jim Stors | VAL001218-26MAR18-VAF
TE82995-1 | ACQUITY CPSM RTZ Assembly Test System | United States | Milford Clean Room | IQ | Initial | Full | Physical Move | Active | Urgent | 2018-04-16 | 2018-04-27 |  | Jim Stors | VAL001218-26MAR18-VAF
TE83006-1 | CPSM Metering Syringe Tester | United States | Milford White Room | IQ | Initial | Full | Physical Move | Active | Urgent | 2018-04-16 | 2018-04-27 |  | Jim Stors | VAL001218-26MAR18-VAF
TE83056-1 | Dual Syringe Home Sensor Set | United States | Milford White Room | IQ | Initial | Full | Physical Move | Active | Urgent | 2018-04-16 | 2018-04-27 |  | Jim Stors | VAL001218-26MAR18-VAF
TE83057-2 | RI Detector Download-Configure Test Station | United States | Milford Refurb | IQ | Initial | Partial | Firmware | Active | Normal | 2017-12-15 | 2018-03-02 |  | Emma Pierce | TE83057-01DEC2017-VAF
TE83082 | WFMA Delay Coil, Tube, and Needle Characterization | United States | Design | EDV | Initial | Full | New Product Intro | Active | Normal | 2017-12-15 | 2018-06-22 |  | Emma Pierce
TE84014 | 2690 Heater/Cooler PCB GTS Test Fixture | United States | Design | EDV | Initial | Full | TE Improvement | Active | Normal | 2017-09-01 | 2018-04-27 |  | Tyler Modelski | Submission Form
TE84028 | 2475 Personality PCB Functional Test Fixture | United States | Design | EDV | Initial | Full | New / Duplicate | Active | Normal | 2018-01-11 | 2018-03-05 |  | Emma Pierce | Need Submission Form
TE84031 | 2690 Alliance CPU Test Fixture | United States | Design | EDV | Initial | Full | TE Improvement | Active | Normal | 2017-08-01 | 2018-03-30 |  | Emma Pierce | Submission Form
VAL000935 | Pero N2/007-EX7897 Solvent Cleaner | United States | Milford Critical Clean | OQ | Initial | Full | Critical Clean | Active | Normal | 2017-08-17 | 2019-03-16 |  | Jim Stors | VAL000935-PVAF
VAL001121 | Autobagger - Auto Batching System | United States | Milford Kitting | IQ | Initial | Full | New / Duplicate | Active | Normal | 2018-01-15 | 2018-03-30 |  | Jim Stors
VAL001122 | MAFAC Elba Tray cleaner | United States | Milford Critical Clean | IQ | Initial | Full | Critical Clean | Active | Normal | 2017-11-01 | 2018-05-18 |  | Jim Stors
VAL001131 | Zeiss Contura G2 (SN:20115505811) | United States | Milford Incoming | IQ | Initial | Full | Physical Move | Active | Normal | 2018-01-19 | 2018-03-30 |  | Emma Pierce | VAL001131-22DEC2017-VAF
VAL001133 | Zeiss DuraMax CMM (SN: 142406) | United States | Milford Machine Shop | IQ | Initial | Full | Physical Move | Active | Normal | 2018-01-19 | 2018-03-30 |  | Emma Pierce | VAL001133-08JAN2018-VAF
VAL001138 | Pero R0 - Columns | United States | Milford Critical Clean | IQ | Initial | Full | Critical Clean | Active | Normal | 2017-11-01 | 2018-05-11 |  | Jim Stors
VAL001140 | Pero R0 - Turning | United States | Milford Critical Clean | IQ | Initial | Full | Critical Clean | Active | Normal | 2017-11-01 | 2018-05-11 |  | Jim Stors
VAL001143 | Zeiss Duramax CMM for Turning - SN:190544 | United States | Milford Machine Shop | IQ | Initial | Full | New / Duplicate | Active | Normal | 2018-02-09 | 2018-03-31 |  | Emma Pierce
TE82943-13 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2018-03-28 | 2018-04-25 | 2018-05-02 | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-20 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2018-03-28 | 2018-04-25 | 2018-05-02 | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-21 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2018-03-28 | 2018-04-25 | 2018-05-02 | Emma Pierce | TE82943-28MAR2018-VAF
TE83064-14 | CPSM Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2018-04-02 | 2018-05-20 | 2018-04-30 | Emma Pierce | TE83064-02APR2018-VAF
TE83064-15 | CPSM Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2018-04-02 | 2018-05-20 | 2018-04-30 | Emma Pierce | TE83064-02APR2018-VAF
TE82943-14 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2018-03-28 | 2018-04-25 | 2018-04-30 | Emma Pierce | TE82943-28MAR2018-VAF
TE83064-12 | CPSM Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2018-04-02 | 2018-04-25 | 04/25/2018 | Emma Pierce | TE83064-02APR2018-VAF
TE83064-13 | CPSM Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2018-04-02 | 2018-04-25 | 04/25/2018 | Emma Pierce | TE83064-02APR2018-VAF
TE82943-01 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2018-03-28 | 2018-04-20 | 04/23/2018 | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-19 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2018-03-28 | 2018-04-20 | 04/23/2018 | Emma Pierce | TE82943-28MAR2018-VAF
TE83064-10 | CPSM Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2018-04-02 | 2018-04-20 | 2018-04-19 | Emma Pierce | TE83064-02APR2018-VAF
TE83064-11 | CPSM Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2018-04-02 | 2018-04-20 | 2018-04-19 | Emma Pierce | TE83064-02APR2018-VAF
TE82943-11 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2018-03-28 | 2018-04-20 | 2018-04-19 | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-12 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2018-03-28 | 2018-04-20 | 2018-04-19 | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-21 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-22 | 2018-01-31 | 2018-02-02 | Tetiana Morse | TE82943-19JAN2018-VAF
TE82943-22 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-22 | 2018-01-31 | 2018-02-02 | Tetiana Morse | TE82943-19JAN2018-VAF
TE82943-24 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-22 | 2018-01-24 | 2018-02-02 | Tetiana Morse | TE82943-19JAN2018-VAF
TE82943-19 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-22 | 2018-01-31 | 2018-01-30 | Tetiana Morse | TE82943-19JAN2018-VAF
TE82943-20 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-22 | 2018-01-31 | 2018-01-30 | Tetiana Morse | TE82943-19JAN2018-VAF
TE82964-1 | 2489 ACQUITY TUV Pre-Test Download Station | International | Flextronics | IQ | Initial | Partial | Firmware | Complete | Urgent | 2018-01-23 | 2018-01-31 | 2018-01-29 | Jim Stors | TE82964-1-22JAN18-VAF
VAL001004 | 2475 Flurourescence Detector Firmware / SN Download Station | International | Venture GES | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-25 | 2018-01-31 | 2018-01-29 | Emma Pierce | 2475FLRDWEX-22JAN2018-VAF
TE82943-01 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2018-01-22 | 2018-01-31 | 2018-01-26 | Tetiana Morse | TE82943-19JAN2018-VAF
TE82943-24 | ACQUITY SDS Final Test System BSM | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-12-14 | 2018-01-31 | 2018-01-19 | Siew Yee Yeap | TE82903-01DEC17-VAF
TE83057-4 | RI Detector Download-Configure Test Station | International | Flextronics | IQ | Requalification | Partial | Firmware | Complete | Normal | 2018-01-01 | 2018-01-31 | 2018-01-10 | Emma Pierce | TE83057-01DEC2017-VAF
TE82943-14 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Full | TE Improvement | Complete | Normal | 2017-12-01 | 2017-12-29 | 2017-12-19 | Siew Yee Yeap
TE82943-18 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Full | TE Improvement | Complete | Normal | 2017-11-16 | 2017-12-29 | 2017-12-14 | Siew Yee Yeap
TE82943-17 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Full | TE Improvement | Complete | Normal | 2017-11-16 | 2017-12-29 | 2017-12-13 | Siew Yee Yeap
TE82943-22 | ACQUITY SDS Final Test System BSM | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2017-11-07 | 2017-12-29 | 2017-12-08 | Siew Yee Yeap | TE82943-01DEC17-VAF
TE82943-15 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Full | TE Improvement | Complete | Normal | 2017-12-01 | 2017-12-29 | 2017-12-07 | Siew Yee Yeap
TE82943-16 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Full | TE Improvement | Complete | Normal | 2017-12-01 | 2017-12-29 | 2017-12-07 | Siew Yee Yeap
VAL001004 | 2475 Flurourescence Detector Firmware / SN Download Station | International | Venture GES | IQ | Requalification | Partial | Firmware | Complete | Urgent | 2017-11-22 | 2017-12-29 | 2017-12-07 | Emma Pierce | 2475FLRDWEX-20NOV2017-VAF
TE82943-13 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Full | TE Improvement | Complete | Normal | 2015-11-16 | 2017-12-29 | 2017-12-06 | Siew Yee Yeap
TE82943-19 | ACQUITY SDS Final Test System BSM | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-11-29 | 2017-12-29 | 2017-12-05 | Siew Yee Yeap | TE82903-01DEC17-VAF
TE82943-20 | ACQUITY SDS Final Test System BSM | International | Venture GES | IQ | Requalification | Full | New Product Intro | Complete | Normal | 2017-12-05 | 2017-12-29 | 2017-12-05 | Siew Yee Yeap | TE82903-01DEC17-VAF
TE82943-21 | ACQUITY SDS Final Test System BSM | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-12-01 | 2017-12-29 | 2017-12-05 | Siew Yee Yeap | TE82903-01DEC17-VAF
TE82903-10 | TUV Detector Final Test System | International | Flextronics | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2017-11-30 | 2017-12-29 | 2017-12-04 | Jim Stors | TE82903-08NOV2017-VAF
TE82774-3 | Alliance Column Heater/Cooler Test Station | International | Venture GES | IQ | Initial | Full | New Product Intro | Complete | Normal | 2017-11-28 | 2017-12-29 | 2017-11-30 | Siew Yee | TE82774-09NOV2017-VAF
TE82943-01 | ACQUITY SDS Final Test System BSM | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-11-27 | 2017-12-29 | 2017-11-30 | Siew Yee Yeap | TE82903-01DEC17-VAF
TE82943-12 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Full | TE Improvement | Complete | Normal | 2017-11-16 | 2017-12-29 | 2017-11-30 | Siew Yee Yeap | TE82943-26SEP2017-VAF
TE82774-2 | Alliance Column Heater/Cooler Test Station | International | Venture GES | IQ | Initial | Full | New Product Intro | Complete | Normal | 2017-11-24 | 2017-12-29 | 2017-11-28 | Tetiana Morse | TE82774-09NOV2017-VAF
TE82903-09 | TUV Detector Final Test System | International | Flextronics | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2017-10-27 | 2017-12-29 | 2017-11-28 | Jim Stors | TE82903-08NOV2017-VAF
TE82903-08 | TUV Detector Final Test System | International | Flextronics | IQ | Requalification | Partial | New Product Intro | Complete | Urgent | 2017-11-17 | 2017-12-29 | 2017-11-22 | Jim Stors | TE82903-08NOV2017-VAF
TE82943-11 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Full | TE Improvement | Complete | Normal | 2017-11-16 | 2017-12-29 | 2017-11-22 | Siew Yee Yeap | TE82943-26Sep2017-VAF
TE83057-4 | RI Detector Download-Configure Test Station | International | Flextronics | IQ | Initial | Partial | New Product Intro | Complete | Normal | 2017-10-17 | 2017-11-30 | 2017-11-15 | Emma Pierce | TE83057-4-22SEP17-VAF
TE82882-08 | 2998 PDA Final Test System | International | Flextronics | IQ | Initial | Partial | New Product Intro | Complete | Urgent | 2017-11-14 | 2017-10-31 | 2017-11-14 | Emma Pierce | TE82882-14NOV17-VAF
TE82969-1 | ACQUITY Arc Bio 2998 PDA Detector | International | Flextronics | IQ | Initial | Partial | New Product Intro | Complete | Urgent | 2017-10-17 | 2017-11-30 | 2017-11-14 | Emma Pierce | TE82969-28SEP17-VAF
VAL001096 | StarLight 150 PDA Alignment System | International | Flextronics | IQ | Initial | Full | New Product Intro | Complete | Urgent | 2017-10-09 | 2017-11-30 | 2017-11-14 | Emma Pierce
TE82882-09 | 2998 PDA Final Test System | International | Flextronics | IQ | Initial | Partial | New Product Intro | Complete | Urgent | 2017-10-27 | 2017-11-30 | 2017-11-01 | Emma Pierce | TE82882-14NOV17-VAF
TE83021 | HTCH GTS Test Fixture | International | Venture GES | IQ | Initial | Partial | TE Improvement | Complete | Urgent | 2017-10-26 | 2017-11-30 | 2017-10-31 | Emma Pierce | TE83021-26OCT2017-VAF
TE83021 | HTCH GTS Test Fixture | International | Venture GES | EDV | Initial | Partial | TE Improvement | Complete | Urgent | 2017-10-27 | 2017-11-30 | 2017-10-31 | Emma Pierce | TE83021-26OCT2017-VAF
TE82817-2 | PCM ll Final Test System | International | Venture GES | IQ | Initial | Partial | Physical Move | Complete | Normal | 2017-10-06 | 2017-10-31 | 2017-10-10 | Siew Yee Yeap | Multiple_WPPL_TE-02OCT17-VA
TE82818-2 | TCM ll Final Test System | International | Venture GES | IQ | Requalification | Partial | Physical Move | Complete | Normal | 2017-10-06 | 2017-10-31 | 2017-10-10 | Siew Yee Yeap | Multiple_WPPL_TE-02OCT17-VAF
TE82824 | PCBA Board Test Fixture | International | Venture GES | IQ | Initial | Partial | Physical Move | Complete | Normal | 2017-10-06 | 2017-10-31 | 2017-10-10 | Siew Yee Yeap | Multiple_WPPL_TE-02OCT17-VAF
TE82984-1 | ACQUITY UPLC Colulmn Manager Test System | International | Venture GES | IQ | Initial | Partial | Physical Move | Complete | Urgent | 2017-10-06 | 2017-10-31 | 2017-10-10 | Siew Yee Yeap | Multiple_WPPL_TE-02OCT17-VAF
TE82987-1 | Column Manager Functional Test System | International | Venture GES | IQ | Initial | Partial | Physical Move | Complete | Urgent | 2017-10-06 | 2017-10-31 | 2017-10-10 | Siew Yee Yeap | Multiple_WPPL_TE-02OCT17-VAF
TE83013-2 | ACQUITY H-Class CH-A Test System | International | Venture GES | IQ | Initial | Full | Physical Move | Complete | Urgent | 2017-10-10 | 2017-10-31 | 2017-10-10 | Siew Yee Yeap | TE83013-2-02OCT17-VAF
TE83026-1 | ACQUITY Column Manager Test System | International | Venture GES | IQ | Requalification | Partial | Physical Move | Complete | Normal | 2017-10-06 | 2017-10-31 | 2017-10-10 | Siew Yee Yeap | Multiple_WPPL_TE-02OCT17-VAF
TE83026-2 | ACQUITY Column Manager Test System | International | Venture GES | IQ | Requalification | Partial | Physical Move | Complete | Normal | 2017-10-06 | 2017-10-31 | 2017-10-10 | Siew Yee Yeap | Multiple_WPPL_TE-02OCT17-VAF
TE83031-1 | 2475 FLR Optics Bench Alignment System | International | Venture GES | IQ | Initial | Partial | Physical Move | Complete | Normal | 2017-10-06 | 2017-10-31 | 2017-10-10 | Siew Yee Yeap | Multiple_WPPL_TE-02OCT17-VAF
TE83032-1 | ACQUITY FLR Optics Bench Alignment System | International | Venture GES | IQ | Initial | Partial | Physical Move | Complete | Normal | 2017-10-06 | 2017-10-31 | 2017-10-10 | Siew Yee Yeap | Multiple_WPPL_TE-02OCT17-VAF
TE83064-10 | CPSM Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-09-01 | 2017-09-29 | 2017-09-26 | Siew Yee Yeap | TE83064-02AUG2017-VAF
TE83064-11 | CPSM Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-09-01 | 2017-09-29 | 2017-09-26 | Siew Yee Yeap | TE83064-02AUG2017-VAF
TE83064-12 | CPSM Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-09-01 | 2017-09-29 | 2017-09-26 | Siew Yee Yeap | TE83064-02AUG2017-VAF
TE83064-13 | CPSM Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-09-01 | 2017-09-29 | 2017-09-26 | Siew Yee Yeap | TE83064-02AUG2017-VAF
TE83064-14 | CPSM Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-09-01 | 2017-09-29 | 2017-09-26 | Siew Yee Yeap | TE83064-02AUG2017-VAF
TE83064-15 | CPSM Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-09-01 | 2017-09-29 | 2017-09-26 | Siew Yee Yeap | TE83064-02AUG2017-VAF
TE83064-16 | CPSM Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-09-01 | 2017-09-29 | 2017-09-26 | Siew Yee Yeap | TE83064-02AUG2017-VAF
TE83064-17 | CPSM Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Complete | Normal | 2017-09-01 | 2017-09-29 | 2017-09-26 | Siew Yee Yeap | TE83064-02AUG2017-VAF
VAL001004 | 2475 Flurourescence Detector Firmware / SN Download Station | International | Venture GES | IQ | Initial | Partial | Firmware | Complete | Normal | 2017-08-02 | 2017-08-31 | 2017-08-10 | Emma Pierce
TE82943-19 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | Firmware | Complete | Normal | 2017-07-25 | 2017-08-31 | 2017-08-09 | Emma Pierce | TE82903-13-JUL-2017-VAF
TE82943-21 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | Firmware | Complete | Normal | 2017-07-27 | 2017-08-31 | 2017-08-09 | Emma Pierce | TE82903-13-JUL-2017-VAF
TE82943-22 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | Firmware | Complete | Normal | 2017-07-27 | 2017-08-31 | 2017-08-09 | Emma Pierce | TE82903-13-JUL-2017-VAF
TE82943-24 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | Firmware | Complete | Normal | 2017-07-27 | 2017-08-31 | 2017-08-09 | Emma Pierce | TE82903-13-JUL-2017-VAF
TE82943-01 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | Firmware | Complete | Normal | 2017-07-27 | 2017-08-31 | 2017-08-08 | Emma Pierce | TE82943-13-JUL-2017-VAF
TE82943-20 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | Firmware | Complete | Normal | 2017-07-27 | 2017-08-31 | 2017-08-08 | Emma Pierce | TE82903-13-JUL-2017-VAF
TE82964-1 | 2489 ACQUITY TUV Pre-Test Download Station | International | Flextronics | IQ | Initial | Partial | Firmware | Complete | Normal | 2017-08-04 | 2017-08-31 | 2017-08-07 | Emma Pierce
TE83026-1 | ACQUITY Column Manager Test System | International | Venture GES | IQ | Initial | Partial | Firmware | Complete | Normal | 2017-08-04 | 2017-08-31 | 2017-08-07 | Emma Pierce | TE83026-13-JUL-2017-VAF
TE83026-2 | ACQUITY Column Manager Test System | International | Venture GES | IQ | Initial | Partial | Firmware | Complete | Normal | 2017-08-04 | 2017-08-31 | 2017-08-07 | Emma Pierce | TE83026-13-JUL-2017-VAF
TE82903-09 | TUV Detector Final Test System | International | Flextronics | TEQ | Initial | Full |  | Complete | Normal | 2017-05-25 | 2017-06-30 | 2017-05-30 | Siew Yee | TE82903-TEQA
TE82903-10 | TUV Detector Final Test System | International | Flextronics | TEQ | Initial | Full |  | Complete | Normal | 2017-05-19 | 2017-06-30 | 2017-05-23 | Siew Yee | TE82903-TEQA
TE82903-08 | TUV Detector Final Test System | International | Flextronics | TEQ | Initial | Full |  | Complete | Normal | 2016-07-22 | 2017-05-31 | 2017-05-16 | Siew Yee | TE82903-TEQA
TE82903-06 | TUV Detector Final Test System | International | Flextronics | TEQ | Initial | Full |  | Complete | Normal | 2016-07-22 | 2017-05-31 | 2017-05-09 | Siew Yee | TE82903-TEQA
TE83064-10 | CPSM Final Test System | International | Venture GES | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-11 | CPSM Final Test System | International | Venture GES | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-12 | CPSM Final Test System | International | Venture GES | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-13 | CPSM Final Test System | International | Venture GES | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-14 | CPSM Final Test System | International | Venture GES | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-15 | CPSM Final Test System | International | Venture GES | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-16 | CPSM Final Test System | International | Venture GES | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE83064-17 | CPSM Final Test System | International | Venture GES | TEQA | Requalification | Partial | TE Improvement | Complete | Normal | 2017-04-17 | 2017-05-31 | 2017-05-09 | Tyler Modelski | TE83064-12Apr2017-TEQA
TE82995-3 | ACQUITY CPSM RTZ Assembly Test System | International | Venture GES | TEQ | Initial | Full |  | Complete | Urgent | 2017-01-01 | 2017-02-28 | 2017-01-25 | Wesley Wong | TE82995-12DEC2016-TEQA
TE82995-2 | ACQUITY CPSM RTZ Assembly Test System | International | Venture GES | TEQ | Initial | Full |  | Complete | Urgent | 2017-01-02 | 2017-01-31 | 2017-01-24 | Siew Yee Yeap | TE82995-12DEC2016-TEQA
TE83064-16 | CPSM Final Test System | International | Venture GES | TEQ | Initial | Full |  | Complete | Normal | 2016-08-15 | 2017-01-31 | 2016-12-28 | Wesley Wong
TE83064-14 | CPSM Final Test System | International | Venture GES | TEQ | Initial | Full |  | Complete | Normal | 2016-08-15 | 2016-12-30 | 2016-12-13 | Wesley Wong
TE83064-17 | CPSM Final Test System | International | Venture GES | TEQ | Initial | Full |  | Complete | Normal | 2016-11-01 | 2016-12-30 | 2016-12-13 | Tyler Modelski
TE83064-15 | CPSM Final Test System | International | Venture GES | TEQ | Initial | Full |  | Complete | Normal | 2016-08-15 | 2016-09-30 | 2016-12-01 | Wesley Wong
TE83064-12 | CPSM Final Test System | International | Venture GES | TEQ | Initial | Full |  | Complete | Normal | 2016-08-15 | 2016-11-30 | 2016-11-22 | Wesley Wong
TE83064-13 | CPSM Final Test System | International | Venture GES | TEQ | Initial | Full |  | Complete | Normal | 2016-08-15 | 2016-11-30 | 2016-11-22 | Wesley Wong
TE83064-10 | CPSM Final Test System | International | Venture GES | TEQ | Initial | Full |  | Complete | Normal | 2016-11-09 | 2016-11-30 | 2016-11-14 | Tyler Modelski
TE83064-11 | CPSM Final Test System | International | Venture GES | TEQ | Initial | Full |  | Complete | Normal | 2016-08-01 | 2016-09-30 | 2016-11-14 | Tyler Modelski
TE82943-24 | ACQUITY SDS Final Test System | International | Venture GES | TEQ | Initial | Full |  | Complete | Normal | 2015-10-01 | 2016-07-29 | 2016-09-30 | Edward Jackson
TE82503-4 | Injector/Seal Pack Tester | International | Flextronics | IQ | Initial | Full | New Product Intro | Complete | Urgent | 2018-02-20 | 2018-03-16 |  | Emma Pierce | TE82503-26FEB2018-VAF
TE82503-5 | Injector/Seal Pack Tester | International | Flextronics | IQ | Initial | Full | New Product Intro | Complete | Urgent | 2018-02-20 | 2018-03-16 |  | Emma Pierce | TE82503-26FEB2018-VAF
TE82705-2 | 1500 Series Pump Final Tester | International | Flextronics | IQ | Initial | Full | VMP Catch up | Pending | Normal | 2017-12-15 | 2018-03-30 |  | Emma Pierce
TE82865-2 | Sample Organizer/ CPSO Final Test System | International | CEI | IQ | Initial | Full | VMP Catch up | Pending | Normal | 2017-10-01 | 2018-03-30 |  | Emma Pierce
TE82865-5 | Sample Organizer/ CPSO Final Test System | International | CEI | IQ | Initial | Full | VMP Catch up | Pending | Normal | 2017-10-01 | 2018-03-30 |  | Emma Pierce
TE82865-6 | Sample Organizer/ CPSO Final Test System | International | CEI | IQ | Initial | Full | VMP Catch up | Pending | Normal | 2017-10-01 | 2018-03-30 |  | Emma Pierce
TE82882-08 | 2998 PDA Final Test System | International | Flextronics | IQ | Requalification | Partial | TE Improvement | Pending | Normal | 2018-02-19 | 2018-04-20 |  | Jim Stors | TE82882-27DEC17-VAF
TE82882-09 | 2998 PDA Final Test System | International | Flextronics | IQ | Requalification | Partial | TE Improvement | Pending | Normal | 2018-02-19 | 2018-04-20 |  | Jim Stors | TE82882-27DEC17-VAF
TE82882-10 | 2998 PDA Final Test System | International | Flextronics | IQ | Requalification | Partial | TE Improvement | Pending | Normal | 2018-02-19 | 2018-04-20 |  | Jim Stors | TE82882-27DEC17-VAF
TE82882-11 | 2998 PDA Final Test System | International | Flextronics | IQ | Requalification | Partial | TE Improvement | Pending | Normal | 2018-02-19 | 2018-04-20 |  | Jim Stors | TE82882-27DEC17-VAF
TE82882-13 | 2998 PDA Final Test System | International | Flextronics | IQ | Requalification | Partial | TE Improvement | Pending | Normal | 2018-02-19 | 2018-04-20 |  | Jim Stors | TE82882-27DEC17-VAF
TE82882-14 | 2998 PDA Final Test System | International | Flextronics | IQ | Requalification | Partial | TE Improvement | Pending | Normal | 2018-02-19 | 2018-04-20 |  | Jim Stors | TE82882-27DEC17-VAF
TE82943-15 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Partial | New Product Intro | Pending | Urgent | 2018-03-28 |  |  | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-16 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Partial | New Product Intro | Pending | Urgent | 2018-03-28 |  |  | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-17 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Partial | New Product Intro | Pending | Urgent | 2018-03-28 |  |  | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-18 | ACQUITY SDS Final Test System | International | Flextronics | IQ | Requalification | Partial | New Product Intro | Pending | Urgent | 2018-03-28 |  |  | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-22 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Pending | Urgent | 2018-03-28 |  |  | Emma Pierce | TE82943-28MAR2018-VAF
TE82943-24 | ACQUITY SDS Final Test System | International | Venture GES | IQ | Requalification | Partial | New Product Intro | Pending | Urgent | 2018-03-28 |  |  | Emma Pierce | TE82943-28MAR2018-VAF
TE82956-2 | ACQUITY High Temperature Column Heater Tester | International | Venture GES | IQ | Initial | Full | VMP Catch up | Pending | Normal | 2017-12-15 | 2018-03-30 |  | Emma Pierce
TE83013-1 | ACQUITY H-Class CH-A Test System | International | Venture GES | IQ | Initial | Full | VMP Catch up | Pending | Normal | 2017-10-03 | 2018-03-30 |  | Jim Stors
TE82882 | 2998 PDA Final Test System | International | Design | EDV | Initial | Full | TE Improvement | Active | Normal | 2018-02-19 | 2018-04-20 |  | Jim Stors | TE82882-08FEB18-VAF
TE82969-1 | ACQUITY Arc Bio 2998 PDA Detector | International | Flextronics | IQ | Requalification | Partial | TE Improvement | Active | Normal | 2018-01-10 | 2018-03-30 |  | Jim Stors | TE82969-03JAN2018-VAF