## Slide 1: 5 Mar 2021
Lean pre-training briefing

## Slide 2
CI project leader:
Champion:
Problem Statement : The CPSM Testers in Venture
What: Macdonald’s takes an average of 8 minutes to complete customers orders.
Why: The entire process and the work station are not optimised hence it led to a high cycle time of 8 minutes.
Impact: Customers feedbacked that Macdonald’s fast food restaurant serve “slow food”. Customer confidence towards the fast food chain have dropped. Business revenue took a hit.
Critical Success Factors/Assumptions :
Assumption: Achieve goal by optimising the process.
Assumptions made to achieve the goal statement
CSF: Remove non-value added activity in the process and
optimise the placement of ingredients and tools at the work
station
Critical factors that determines the success or failure of the
project.
Goal Statement :
To improve the cycle time of the order completion to under 4 minutes within 2 months upon project commencement Adopt SMART objective S- Specific M- Measurable A- Attainable R- Realistic
T- Time-based
Project Scope : To improve the process cycle time from receiving customer’s order to completion of customer’s order. Determine the project scope means setting the boundaries for the project leader to work on.
Process: Receive customer order, verify customer order, send order to kitchen, meal preparation, meal packaging, order verification, serve order to customer.
Dictate the existing process allows the project leader to grasp the understanding of current situation.
Business Benefit and Metrics
Primary Metric: Timing for order completion Identify the metric that dictates the key success criteria for the project.
Benefit: Lowered cycle time by 50%
Type of benefit: hard/soft savings Hard savings refers to tangible cash savings
Soft savings refers to intangibles savings
Project Est. Duration: 2 months
Project Resources: Macdonald’s staff. Indicate stakeholders (department/specific individual and etc)
Project Title: Lean Improvement for CPSM Testers
Project Charter