## Sheet1
Tester ID | Tester Description | Location | Hardware Installation Status | Validation Status | Target Completion Date
TE82988-12 | GTS Tester for QDA PCB | Venture | Done | VAF drafted, Gathering the documents for IQ | 2019-05-31
| RF Box tester | Venture | ECO Implementation is on going |  | 2019-05-31
TE82774-4 | Column Heater Cooler Test Station | Venture | Waiting for tester location allocation |  | 2019-06-28
TE827760 | FLR Detector Final Test Station | Venture | Waiting for tester bench set up |  | 2019-07-26
TE84018-01 | Alliance Heater Cooler Test Station | Flex | Done | Preparing the IQR report for approval | 2019-05-31