## Sheet1
Sort | level | Task Name | Duration | Start | Finish | Predecessors | Resource Names
1 | 1 | 186017001/186017007 to Flex | 267 days | Fri 3/27/20 | Mon 4/5/21
2 | 2 | Transfer Program Execution | 267 days | Fri 3/27/20 | Mon 4/5/21
3 | 3 | Materials | 123 days | Fri 3/27/20 | Tue 9/15/20
4 | 4 | Material Procurement | 95 days | Fri 3/27/20 | Thu 8/6/20
5 | 5 | Issue Transfer Commitment PO | 5 days | Fri 3/27/20 | Thu 4/2/20 |  | Waters SG
6 | 5 | Procure Material | 90 days | Fri 4/3/20 | Thu 8/6/20 | 5 | Flex
7 | 5 | FAIR Process | 90 days | Fri 4/3/20 | Thu 8/6/20 | 5 | Wan Jing Loh
8 | 5 | Material Procurement Complete | 0 days | Thu 8/6/20 | Thu 8/6/20 | 7,6
9 | 4 | 205 Kits (Matl Sold To CMO) | 20 days | Thu 4/2/20 | Wed 4/29/20
10 | 5 | Add To Flex Price Table (Existing Kits) | 10 days | Thu 4/2/20 | Wed 4/15/20
11 | 6 | 205001477 | 10 days | Thu 4/2/20 | Wed 4/15/20 |  | Kris Bujold
12 | 6 | 205001921 | 10 days | Thu 4/2/20 | Wed 4/15/20 |  | Kris Bujold
13 | 6 | 205001478 | 10 days | Thu 4/2/20 | Wed 4/15/20 |  | Kris Bujold
14 | 6 | 205001904 | 10 days | Thu 4/2/20 | Wed 4/15/20 |  | Kris Bujold
15 | 6 | 205001888 | 10 days | Thu 4/2/20 | Wed 4/15/20 |  | Kris Bujold
16 | 6 | Price table updates complete | 0 days | Wed 4/15/20 | Wed 4/15/20 | 11,12,13,14,15
17 | 5 | New Kit Creation | 20 days | Thu 4/2/20 | Wed 4/29/20 |  | Mfg Eng
18 | 6 | Create/Release - 430004479 | 10 days | Thu 4/2/20 | Wed 4/15/20 |  | Gayle Gaudreau
19 | 6 | Create/Release - 430002406 | 10 days | Thu 4/2/20 | Wed 4/15/20 |  | Gayle Gaudreau
20 | 6 | Create/Release - 430002012 | 10 days | Thu 4/2/20 | Wed 4/15/20 |  | Gayle Gaudreau
21 | 6 | Create/Release - 405023323 | 10 days | Thu 4/2/20 | Wed 4/15/20 |  | Gayle Gaudreau
22 | 6 | Add to Flex Price Table | 10 days | Thu 4/16/20 | Wed 4/29/20
23 | 7 | 430004479 | 10 days | Thu 4/16/20 | Wed 4/29/20 | 18 | Kris Bujold
24 | 7 | 430002406 | 10 days | Thu 4/16/20 | Wed 4/29/20 | 19 | Kris Bujold
25 | 7 | 430002012 | 10 days | Thu 4/16/20 | Wed 4/29/20 | 20 | Kris Bujold
26 | 7 | 405023323 | 10 days | Thu 4/16/20 | Wed 4/29/20 | 21 | Kris Bujold
27 | 7 | New Kits Complete | 0 days | Wed 4/29/20 | Wed 4/29/20 | 23,24,25,26
28 | 4 | SAP Cross Over | 119 days | Thu 4/2/20 | Tue 9/15/20
29 | 5 | Create SAP Cross over Plan | 20 days | Thu 4/2/20 | Wed 4/29/20 |  | Materials Teams
30 | 5 | Delay for project timing | 90 days | Thu 4/30/20 | Wed 9/2/20 | 29
31 | 5 | Execute SAP Cut In | 5 days | Thu 9/3/20 | Wed 9/9/20 | 30 | Comm Mgmt/Planning
32 | 5 | Issue Production Purchase Orders | 3 days | Thu 9/10/20 | Mon 9/14/20 | 31 | Waters SG
33 | 5 | Cancel Initial PO | 1 day | Tue 9/15/20 | Tue 9/15/20 | 32 | Waters SG
34 | 5 | SAP Cross Over Complete | 0 days | Tue 9/15/20 | Tue 9/15/20 | 31,32,33
35 | 4 | Materials Activity Complete | 0 days | Tue 9/15/20 | Tue 9/15/20 | 8,34
36
37 | 3 | Technical | 163 days | Fri 3/27/20 | Tue 11/10/20
38 | 4 | Process Review | 25 days | Fri 3/27/20 | Thu 4/30/20
39 | 5 | Prove Out Documentation | 10 days | Fri 3/27/20 | Thu 4/9/20 |  | Andrew Day
40 | 5 | Final Documentation Edits | 5 days | Fri 4/10/20 | Thu 4/16/20 | 39 | Andrew Day
41 | 5 | Release Documentation To ECO Control | 10 days | Fri 4/17/20 | Thu 4/30/20 | 40 | Andrew Day
42 | 5 | Process Development Complete | 0 days | Thu 4/30/20 | Thu 4/30/20 | 41
43 | 4 | Test Equipment Duplication | 163 days | Fri 3/27/20 | Tue 11/10/20
44 | 5 | Determine Test Equipment Needed | 15 days | Fri 3/27/20 | Thu 4/16/20 |  | Rick Davis
45 | 5 | Compose CEA | 2 days | Fri 4/17/20 | Mon 4/20/20 | 44 | Rick Davis
46 | 5 | Process CEA | 5 days | Tue 4/21/20 | Mon 4/27/20 | 45 | Rick Davis
47 | 5 | Waters Capital Expense Delay Q2 2020 | 50 days | Tue 4/28/20 | Mon 7/6/20 | 46
48 | 5 | Procure and Build Test Equipment | 48 days | Tue 7/7/20 | Thu 9/10/20 | 47 | Rick Davis
49 | 5 | Develop Packaging Solution | 10 days | Fri 9/11/20 | Thu 9/24/20 | 48 | Rick Davis
50 | 5 | Ship Tooling To CM | 7 days | Mon 10/26/20 | Tue 11/3/20 | 49102 | Rick Davis
51 | 5 | Install at CM | 5 days | Wed 11/4/20 | Tue 11/10/20 | 50 | Rick Davis
52 | 5 | Test Equipment Complete | 0 days | Tue 11/10/20 | Tue 11/10/20 | 51
53 | 4 | Production Tool Duplication (Waters Supplied) | 163 days | Fri 3/27/20 | Tue 11/10/20
54 | 5 | Determine Production Tools Needed | 5 days | Fri 3/27/20 | Thu 4/2/20 |  | Andrew Day
55 | 5 | Compose CEA | 2 days | Fri 4/3/20 | Mon 4/6/20 | 54 | Andrew Day
56 | 5 | Process CEA | 5 days | Tue 4/7/20 | Mon 4/13/20 | 55 | Andrew Day
57 | 5 | Waters Capital Expense Delay Q2 2020 | 60 days | Tue 4/14/20 | Mon 7/6/20 | 56
58 | 5 | Procure and Build Production Tools | 59 days | Tue 7/7/20 | Fri 9/25/20 | 57 | Andrew Day
59 | 5 | Prove Out Production Tools | 15 days | Mon 9/28/20 | Fri 10/16/20 | 58 | Andrew Day
60 | 5 | Develop Packaging Solution | 10 days | Mon 10/19/20 | Fri 10/30/20 | 59 | Andrew Day
61 | 5 | Ship Tooling To Supplier | 7 days | Mon 11/2/20 | Tue 11/10/20 | 60102 | Andrew Day
62 | 5 | Waters Supplied Tooling Complete | 0 days | Tue 11/10/20 | Tue 11/10/20 | 61 | Andrew Day
63 | 4 | Production Tools (Contract Mfgr Supplied) | 46 days | Fri 3/27/20 | Fri 5/29/20
64 | 5 | Determine Production Tools Needed | 10 days | Fri 3/27/20 | Thu 4/9/20 |  | Andrew Day
65 | 5 | Provide Data To Contract Mfgr | 1 day | Fri 3/27/20 | Fri 3/27/20 |  | Andrew Day
66 | 5 | Procure Tools Needed | 45 days | Mon 3/30/20 | Fri 5/29/20 | 65 | Flex
67 | 5 | Contract Mfg Tool Procurement Complete | 0 days | Fri 5/29/20 | Fri 5/29/20 | 66
68 | 4 | Miscellaneous Project Activty | 30 days | Fri 5/1/20 | Thu 6/11/20
69 | 5 | Label Printing Authorization | 5 days | Fri 5/1/20 | Thu 5/7/20 | 100 | Andrew Day
70 | 5 | Test Equipment Communications Dedicated Line (As Needed) | 30 days | Fri 5/1/20 | Thu 6/11/20 | 100 | Rick Davis
71 | 5 | Miscellaneous Project Activity Complete | 0 days | Thu 6/11/20 | Thu 6/11/20 | 69,70
72 | 4 | Minor Facility Improvements at Contract Mfgr (As Needed) | 80 days | Fri 3/27/20 | Thu 7/16/20
73 | 5 | Determine Facility Requirements | 10 days | Fri 3/27/20 | Thu 4/9/20 |  | Michael Doyle
74 | 5 | Review With Contract Mfgr | 5 days | Fri 4/10/20 | Thu 4/16/20 | 73 | Michael Doyle
75 | 5 | Procure Required Equipment/Materials | 45 days | Fri 4/17/20 | Thu 6/18/20 | 74 | Flex
76 | 5 | Install Equipment/Materials (Training) | 10 days | Fri 6/19/20 | Thu 7/2/20 | 75 | Flex
77 | 5 | Review with Waters | 5 days | Fri 7/3/20 | Thu 7/9/20 | 76 | Flex
78 | 5 | Approve Facility Updates | 5 days | Fri 7/10/20 | Thu 7/16/20 | 77 | Michael Doyle
79 | 5 | Minor Facility Improvements Complete | 0 days | Thu 7/16/20 | Thu 7/16/20 | 78
80 | 4 | Major Capital Equipment Purchases (Contract Mfgr Supplied As Needed) | 95 days | Fri 3/27/20 | Thu 8/6/20
81 | 5 | Define Equipment Needed | 10 days | Fri 3/27/20 | Thu 4/9/20 |  | Contract Mfgr
82 | 5 | Review With Waters | 5 days | Fri 4/10/20 | Thu 4/16/20 | 81 | Contract Mfgr
83 | 5 | Procure Equipment | 60 days | Fri 4/17/20 | Thu 7/9/20 | 82 | Contract Mfgr
84 | 5 | Install Equipment | 10 days | Fri 7/10/20 | Thu 7/23/20 | 83 | Contract Mfgr
85 | 5 | Training | 10 days | Fri 7/24/20 | Thu 8/6/20 | 84 | Contract Mfgr
86 | 5 | Major Capital Equipment Purchase Complete | 0 days | Thu 8/6/20 | Thu 8/6/20 | 85 | Contract Mfgr
87
88 | 4 | Training and Related Activity | 183 days | Fri 3/27/20 | Tue 12/8/20
89 | 5 | Training | 161 days | Fri 3/27/20 | Fri 11/6/20
90 | 6 | Develop Training Plan | 15 days | Fri 3/27/20 | Thu 4/16/20 |  | Michael Doyle
91 | 6 | Seek Trainee's from Contract Mfgr | 1 day | Fri 3/27/20 | Fri 3/27/20 |  | Michael Doyle
92 | 6 | Define Trainee's | 5 days | Mon 3/30/20 | Fri 4/3/20 | 91 | Flex
93 | 6 | Review Trainee List and apply to plan | 2 days | Mon 4/6/20 | Tue 4/7/20 | 92 | Michael Doyle
94 | 6 | Approve Trainee's | 1 day | Wed 4/8/20 | Wed 4/8/20 | 93 | Michael Doyle
95 | 6 | Determine Training Dates and Location | 3 days | Thu 4/9/20 | Mon 4/13/20 | 94 | Michael Doyle
96 | 6 | Seek Site Access Approval for Trainiees | 3 days | Tue 4/14/20 | Thu 4/16/20 | 94,95 | Kris Bujold
97 | 6 | Issue Visa Invitation Letters If Required | 2 days | Fri 4/17/20 | Mon 4/20/20 | 96 | Kris Bujold
98 | 6 | Passport Approvals If Required | 10 days | Tue 4/21/20 | Mon 5/4/20 | 97 | Flex
99 | 6 | Prepare Training Documentation | 5 days | Fri 4/17/20 | Thu 4/23/20 | 90 | Michael Doyle
100 | 6 | Prepare Facility For Training | 10 days | Fri 4/17/20 | Thu 4/30/20 | 90 | Michael Doyle
101 | 6 | Training Activity - On Site | 15 days | Mon 9/7/20 | Fri 9/25/20 | 102FS-35 days | Team
102 | 6 | Traing On Site With New TE/Prod Fixt. | 20 days | Mon 9/28/20 | Fri 10/23/20 | 48,58 | Team
103 | 6 | ECO's for Documentation Clean Up | 10 days | Mon 10/26/20 | Fri 11/6/20 | 102 | Andrew Day
104 | 6 | Flex Team travel home | 5 days | Mon 10/26/20 | Fri 10/30/20 | 102 | Flex
105 | 6 | Training Activity Complete | 0 days | Fri 11/6/20 | Fri 11/6/20 | 103
106 | 5 | Labor Validation Build | 183 days | Fri 3/27/20 | Tue 12/8/20
107 | 6 | Determine Build Requirements | 5 days | Fri 3/27/20 | Thu 4/2/20 |  | Michael Doyle
108 | 6 | Kit Material At Waters (Qty=???) | 20 days | Mon 9/7/20 | Fri 10/2/20 | 101FS-15 days | Michael Doyle
109 | 6 | Ship To Contract Mfgr | 5 days | Mon 10/5/20 | Fri 10/9/20 | 108 | Michael Doyle
110 | 6 | Kit/Review at Flex | 10 days | Mon 10/12/20 | Fri 10/23/20 | 109 | Flex
111 | 6 | Build at Contract Mfgr | 10 days | Mon 11/9/20 | Fri 11/20/20 | 103 | Flex
112 | 6 | Ship To Waters For Review | 7 days | Mon 11/23/20 | Tue 12/1/20 | 111 | Flex
113 | 6 | Review At Waters / Issue Report | 5 days | Wed 12/2/20 | Tue 12/8/20 | 112 | Michael Doyle
114 | 6 | Validation Build Complete | 0 days | Tue 12/8/20 | Tue 12/8/20 | 113
115
116 | 5 | Production Builds | 267 days | Fri 3/27/20 | Mon 4/5/21
117 | 6 | Pre-Production Build / Mfg Qual Readiness | 207 days | Fri 3/27/20 | Mon 1/11/21
118 | 7 | Establish Build Plan | 20 days | Wed 9/16/20 | Tue 10/13/20 | 34 | Comm Mgmt,Waters SG
119 | 7 | Provide Purchase Orders | 5 days | Wed 10/14/20 | Tue 10/20/20 | 118 | Waters SG
120 | 7 | Compose Mfg Qual Readiness Plan | 15 days | Fri 3/27/20 | Thu 4/16/20 |  | Kris Bujold, Allison Hacker
121 | 7 | Review for program readiness | 5 days | Wed 12/9/20 | Tue 12/15/20 | 42,52,62,105,114,67,79,86,71,120 | Team
122 | 7 | Kit Material At Contract Mfgr | 5 days | Wed 12/16/20 | Tue 12/22/20 | 6121 | Flex
123 | 7 | EOQ / Holiday Delay | 13 days | Wed 12/16/20 | Fri 1/1/21 | 121
124 | 7 | Mfg Qual Readiness Build | 5 days | Mon 1/4/21 | Fri 1/8/21 | 123 | Team
125 | 7 | Sustaining Production Starts | 1 day | Mon 1/11/21 | Mon 1/11/21 | 124 | Flex
126 | 7 | Qual Readiness Complete | 0 days | Mon 1/11/21 | Mon 1/11/21 | 125
127 | 6 | Qual Readiness Documentation | 30 days | Mon 1/11/21 | Fri 2/19/21
128 | 7 | Provide Data to Milford for report | 5 days | Mon 1/11/21 | Fri 1/15/21 | 124 | Desmond
129 | 7 | Mfg Qual Readiness Report | 30 days | Mon 1/11/21 | Fri 2/19/21 | 124 | Allison Hacker
130 | 7 | Mfg Qual Readiness Complete | 0 days | Fri 2/19/21 | Fri 2/19/21 | 129
131 | 6 | Dual Builds Flex/Milford | 60 days | Mon 1/11/21 | Fri 4/2/21
132 | 7 | Dual Builds Milford | 60 days | Mon 1/11/21 | Fri 4/2/21 | 124 | Milford Ops
133 | 7 | Dual Builds Flex | 60 days | Mon 1/11/21 | Fri 4/2/21 | 124 | Flex
134 | 7 | Dual Builds Complete | 0 days | Fri 4/2/21 | Fri 4/2/21 | 132133
135 | 6 | Full Production - Flex | 1 day | Mon 4/5/21 | Mon 4/5/21
136 | 7 | Full Production - Flex | 1 day | Mon 4/5/21 | Mon 4/5/21 | 134 | Flex
137 | 7 | Full Procustion Complete | 0 days | Mon 4/5/21 | Mon 4/5/21 | 136
138
139 | 1 | Related Program Activity | 306 days | Fri 3/27/20 | Fri 5/28/21
140 | 2 | Spares Activity | 275 days | Fri 3/27/20 | Thu 4/15/21
141 | 3 | Define Spares To Be Transferred | 10 days | Fri 3/27/20 | Thu 4/9/20 |  | Tech Proj Mgr
142 | 3 | Prepare/Send RFQ Packages | 10 days | Fri 3/27/20 | Thu 4/9/20 |  | Waters SG
143 | 3 | Quote Assemblies | 30 days | Fri 4/10/20 | Thu 5/21/20 | 142 | Contract Mfgr
144 | 3 | Review Quotes / Resolve Issues | 10 days | Fri 5/22/20 | Thu 6/4/20 | 143 | Waters SG
145 | 3 | Award Quote To Contract Mfgr / Change SAP Demands | 3 days | Tue 1/12/21 | Thu 1/14/21 | 125 | Waters SG
146 | 3 | Procure Material | 60 days | Fri 1/15/21 | Thu 4/8/21 | 145 | Contract Mfgr
147 | 3 | Build Spares | 5 days | Fri 4/9/21 | Thu 4/15/21 | 146 | Contract Mfgr
148 | 3 | Initial Spares Actvity Complete | 0 days | Thu 4/15/21 | Thu 4/15/21 | 147 | Comm Mgmt
149 | 2 | ETL Compliance Certification At Contract Mfgr | 100 days | Mon 1/11/21 | Fri 5/28/21
150 | 3 | Internal Activity | 60 days | Mon 1/11/21 | Fri 4/2/21
151 | 4 | Add CM to report | 60 days | Mon 1/11/21 | Fri 4/2/21 | 124 | Compliance
152 | 3 | External Activity | 40 days | Mon 4/5/21 | Fri 5/28/21
153 | 4 | Set Up Facility Audit | 20 days | Mon 4/5/21 | Fri 4/30/21 | 151 | Compliance
154 | 4 | Perform Facility Audit | 5 days | Mon 5/3/21 | Fri 5/7/21 | 153 | Audit
155 | 4 | Complete Audit Forms | 5 days | Mon 5/10/21 | Fri 5/14/21 | 154 | Audit
156 | 4 | Audit Reports | 10 days | Mon 5/17/21 | Fri 5/28/21 | 155 | Audit
157 | 4 | ETL Activity Complete | 0 days | Fri 5/28/21 | Fri 5/28/21 | 151156 | Compliance
158 | 2 | Dock To Stock | 272 days | Fri 3/27/20 | Mon 4/12/21
159 | 3 | Compose Plan | 30 days | Fri 3/27/20 | Thu 5/7/20 |  | Waters SG Quality
160 | 3 | Dock To Stock Review Period | 60 days | Mon 1/11/21 | Fri 4/2/21 | 124 | Flex,Waters Quality
161 | 3 | Dock To Stock Data Review | 5 days | Mon 4/5/21 | Fri 4/9/21 | 160 | Waters SG Quality
162 | 3 | Dock To Stock Decision | 1 day | Mon 4/12/21 | Mon 4/12/21 | 161 | Waters SG Quality
163 | 3 | Dock To Stock Complete | 0 days | Mon 4/12/21 | Mon 4/12/21 | 162