## Packaging Timeline
Item | Required Prior | Responsible | Description | Length | Notes
1 |  | ME | Review expense requirements with Manufacturing Engineering Management | 1 Week | (parts for package testing and packaging process)
2 |  | PE | Obtain CC parts for QA evaluation (new parts) | 2 months | Parts have a 6-8 week lead time from manufacturer. + CC process time.
3 | 2 | QA | Cleanliness testing of Clamshell | 1 Month | Milestone: Approval of Clamshell inside CC bag
4 | 3 | ME/Machine Shop | Obtain Parts for Rand and Whitney: Record coating condition prior to testing | 2 Weeks
5 | 3 | R&W | Design and test packaging for Stators/rotors. Including Drop test and Vibration testing. | 2 Months
6 | 3 | R&W | Initial Meeting
7 | 6 | R&W | Design Review
8 | 4,7 | R&W | Provide parts for testing
9 | 8 | R&W | Drop/Vibration testing |  | Milestone: Drop/Vibration test report
10 | 9 | Purchasing | Order clamshells to be used for packaging, create CC part number. | 2 months | (Clamshell Parts have a 6-8 week lead time, can be ordered prior potential to be used elsewhere)
11 | 9 | Machine Shop | Add Clamshell to packaging for 405020260, inside CC bag. | 2 Weeks
12 | 9 | todd mongeau | Create and Release Packaging | 1 Week
13 | 11,12 | ME | Create and Release kits in ECR. | 2 Weeks

## Capacity Calculations
| Year 17 | Year 19 Predicted | Year 19 Adjusted | Time Per assembly | Notes
Qty OLD | 4870 | 3934 | 0 | 0.324 | (does not include test, spares are tested at MSV stage) | NOTE: Year 17 Quantity is of all stators used in US31.
QTY NEW | 0 | 1218 | 5152 | 0.183 | (build and test) | Year 19 Predicted is current values in SAP for 2019 planning predictions.
Total Time | 1577.88 | 1497.51 | 942.816 |  |  | Year 19 Adjusted is the total quantity of Year 19 predicted, but only for the new part number.