## Sheet1
Enter Company Name in cell B2. | Company Name | Waters Pacific Pte Ltd
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Project Lead: HuaZhen | Project Start: |  | 2021-07-09
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 2 |  |  | 2021-07-12 | [6 empty] | 2021-07-19 | [6 empty] | 2021-07-26 | [6 empty] | 2021-08-02 | [6 empty] | 2021-08-09 | [6 empty] | 2021-08-16 | [6 empty] | 2021-08-23 | [6 empty] | 2021-08-30
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-07-12 to 2021-09-05
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2021-07-12 to 2021-09-05
CPSM upgrade | TE83064-14 upgrade | HZ |  | 2021-07-12 | 2021-07-16 | 5 | bar: 2021-07-19 to 2021-07-23
| TE83064-16 upgrade | HZ |  | 2021-07-12 | 2021-07-16 | 5 | bar: 2021-07-19 to 2021-07-23
| TE83064-13 upgrade | HZ |  | 2021-08-10 | 2021-08-20 | 9 | bar: 2021-08-17 to 2021-08-20; 2021-08-23 to 2021-08-27
| TE83064-10 upgrade | HZ |  | 2021-08-23 | 2021-09-02 | 9 | bar: 2021-08-30 to 2021-09-03