## TE82943 Tester setup Schedule
Installation Plan |  |  | Work Day
Tester | Action Item | Status | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-05 | 2021-08-06
TE82943-XX | Installation of new test PC and test box | Planned | bar: 2021-07-19 to 2021-07-20
Actual
| Tester Configuration | Planned | bar: 2021-07-21 to 2021-07-22
Actual
| Weighing scale calibration | Planned | bar: 2021-07-22
Actual
| Test Software Update | Planned | bar: 2021-07-22 to 2021-07-23
Actual
| Functional Verification and Validation | Planned | bar: 2021-07-28 to 2021-08-06
Actual
Installation Plan |  |  | 2021-07-19: Work Day
Tester | Action Item | Status | 2021-07-22 | 2021-07-23 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-05 | 2021-08-06 | 2021-08-09 | 2021-08-10 | 2021-08-11
TE82943-XX | Installation of new test PC and test box | Planned | bar: 2021-07-22 to 2021-07-23
Actual
| Tester Configuration | Planned | bar: 2021-07-28 to 2021-07-29
Actual
| Weighing scale calibration | Planned | bar: 2021-07-22
Actual
| Test Software Update | Planned | bar: 2021-07-29 to 2021-07-30
Actual
| Functional Verification and Validation | Planned | bar: 2021-07-31 to 2021-08-11
Actual
Legend: | Planned Action Item
Completed Action Item
Timeline consideration
- 2 working days for hardware setup such as tester PC, test box, monitor and cable harnesses, etc..
- 2 working days for tester configuration to get ready for functionality.
- 2 working days for test software upgrade.
- 7 working days for functional verification and tester validation.
Terms and Condition
-PM due date is still valide at the point of transfer and no PM is required
- TUV lamp hour is less than 2000hr

## Activity tracking
TE0084050-18
Date | Action Item | Remark