## Slide 1
Q1 2020
Alliance & PCBA
Q2 2020
FTN & PCBA
Alliance Final testers upgrade x 8
ICT fixture replacement (Altera IC) x 1*
Alliance Pump Tray upgrade x 3
PCBA Front end tester migration*
GTS Gen 2 & PCBA functional testers development training*
ICT fixture replacement (Altera IC) x 1*
Q4 2019
PCBA
RECAL Test system consolidation*
ICT fixture replacement (Altera IC) x 2*
Alliance system for PCBA troubleshooting
Tester Renewal Workplan
Q3 2020
Q4 2020
Label view & servers
ICT fixture replacement (Altera IC EOL project) x 1*
GTS Gen 2 (2nd system)*
Cloud based label printers upgrade*
FTN & PCBA
FTN Final Testers x 8
GTS Gen 2 (1st system)*
ICT fixture replacement (Altera IC) x 1*
Q1 2021
QSM/BSM & PCBA
BSM/QSM final tester upgrade x 16
RECAL transition to GTS Platform (# old models)*
Functional testers refurbish/upgrade
Initiative Value Proposition: Extend current testers lifecycle through pro-active renewal/upgrade of test equipment to minimize tester downtime and risk to production. Improvements will also provide better analytics capabilities.
Team Members: Jaaffar, Matt B, Mark Jussaume, Paul Deschenes (Milford); Edwin, HuaZhen, New HC* (Singapore)
Criteria | Measures
Training on PCBA functional test knowledge | Migrate front end testers for old models to GTS platform by Q2 2020
Development of Gen 2 GTS system | Ability to configure and commission a new GTS Gen 2 by Q3 2020
Cloud based label printing | Local administrator for cloud based label printing support by Q4 2020
Measurable Success
Notes: PCP and objective to get external skills set
Q1
Alliance New test bays
- include upgraded PC windows 10
- sigmasure access for tracking
Upgrade/replace EOL components like valves, solenoids and circuits
Q2
Q3
BSM/QSM final tester – switch from weight balance to flow meter