## Timeline
Waters CPSM upgrade for Arc FTN Transfer Timeline |  | Date: 15-Dec-2020
CPSM upgrade | Task description | Responsibility | Status | 2020-11-01 |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  | 2021-04-01 |  |  |  |  | 2021-05-01 |  |  |  | 2021-06-01 |  |  |  | 2021-07-01 |  |  |  |  | 2021-08-01 |  |  |  | 2021-09-01
|  |  |  | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24
1. Discussion and CEA approval
| CPSM upgrade BOM local source review & Discussion | All | 2 | 2020-11-01 6: 2; 2020-11-01 13: 2
| CEA Approval | Hua Zhen/Edwin | 2 | 2020-11-01 20: 2; 2020-11-01 27: 2
2. BOM Readiness
1. PC
| - PO for PC | Hua Zhen | 2 | 2020-12-01 4: 2
| -Advance payment required | Hua Zhen/Finance | 2 | 2020-12-01 11: 2
| -Shipping to Singapore | Hua Zhen | 3 | 2020-12-01 11: 3; 2020-12-01 18: 3; 2020-12-01 25: 1; 2021-01-01 1: 1
| -Upload PC image to Flex Server | Rick | 1 | bar: 2020-12-01 25 to 2021-01-01 1
| -Setup PC and copy PC image to new PC | Hua Zhen | 1 | bar: 2021-01-01 1 to 2021-01-01 8
| -Load license for empower on new PC | Bill Bates | 1 | bar: 2021-01-01 8
2.TouchScreen Monitor
| -PO for touchscreen Monitor | Hua Zhen | 2 | 2020-12-01 4: 2
| -Estimated shipping date | Hua Zhen | 3 | 2020-12-01 11: 3; 2020-12-01 18: 3; 2020-12-01 25: 1; 2021-01-01 1: 1; 2021-01-01 8: 1
3. 3D Printing Parts
| -3D print vendor capability validation | Hong Min/Edwin | 1 | bar: 2020-12-01 11 to 2020-12-01 18
| -PO for 3D Printing Parts | Hua Zhen | 1 | bar: 2020-12-01 18 to 2020-12-01 25
| -3d Print parts qualification | Hong Min | 1 | bar: 2021-01-01 1 to 2021-01-01 8
| -2 sets of fabricated parts by JEG | Guan Yee/Hua Zhen | 2 | 2020-12-01 11: 2; 2020-12-01 18: 2
4. Interface Box
| - Build 2x Interface Boxes to WPPL | Rick | 1 | bar: 2021-01-01 1
| - Ship 2x Interface Boxes to WPPL | Rick | 1 | bar: 2021-01-01 8
3. Venture Tester verify
| -Functionality check and familization | Hua Zhen | 1 | bar: 2020-12-01 25
4. Venture Tester decommissioning and shipping to WPPL
| -Inform Venture/ME 2x testers decommissioning for upgrade | Edwin/HuaZhen | bar: 2021-01-01 1
| -Pack and ship to WPPL | Venture/HuaZhen | 1 | bar: 2021-01-01 8
5. 2x CPSM testers upgrade in WPPL
| - Unpack, upgrade and functional verification | Hua Zhen/Rick | 1 | bar: 2021-01-01 15 to 2021-01-01 22
| - Old TE# deactivate and activate new TE# | Rick | 1 | bar: 2021-01-01 15 to 2021-01-01 22
| - New test program introduction | Rick | 1 | bar: 2021-01-01 15 to 2021-01-01 29
| - Pack and ship 2x upgraded testers to Flex | Hua Zhen | 1 | bar: 2021-01-01 29
6. Ship and set up 2x Testers in Flex
| -Tester equipment setup at Flex | Flex/Hua Zhen | 1 | bar: 2021-02-01 5
7. Validation 2x Testers in Flex
Complete | -Tester Validation (IQ) at Flex | Ernest/Emma | 1 | bar: 2021-02-01 19
Critical Date:
1. Decommissioning 2x Testers in Venture on Week 8 Jan 2021
2. All BOM parts should be ready on Week 15 Jan 2021
3. Complete this project on Week 15 Feb 2021
Note on B8: HuaZhen Luo: All parts should be ready on week 15 Jan 21
Note on C12: HuaZhen Luo: Est Shipping date: 16 Dec 20
Note on C18: HuaZhen Luo:
Note on B29: HuaZhen Luo: decommissioning on week 8 Jan 2021
Note on B39: HuaZhen Luo: Complete this project on Week 15 Feb 2021

## BOM WPPL20024
CEA# WPPL20024
Items | Quantity | Description | Manufacturer | Part Number | Unit Price | Total | Local office/Distributor | Unit Price(SGD) | Unit Price (USD) | Remark | Local purchase? | PO #/invoice # | Qty | Date of PO issuing | Est Shipping date | Target Delivery date | Invoice closure Date
1 | 1 | 1U, Rack Mount, Long life, Industrial PC | SuperLogics | SL-1U-LLQ370M-LA Configuration ID#3867780 | 1365 | 1365 | NA | NA | 1365 | Purchase online and load image; Bill Bates to load empower license once set up. | Yes | WPPL-OP-094 | 8 | 2020-12-02 | 2020-12-16
2 | 1 | ViewSonic TD1711, touchscreen Display | CDW | 5201210 | 299 | 299 | https://www.bhphotovideo.com/bnh |  | 299 | Purchase TD1711 online; The same model TD1711 will be order for this project. | Yes | Order # 1069668097 | 8 | 2020-12-02 | 2020-01-04
3 | 1 | Cable Interface Box (3 panels, 2 w/ Paint) | Model Shop |  | 447 | 447 |  |  | 0 | Can Milford upgrade and ship it to Singapore by 04 Jan 2021? | Milford | TBD
4 | 1 | USB-6501 | National Instruments | 779205-01 | 114 | 114 |  | 170 | 125.9259
5 | 1 | USB 4 port serial converter | StarTech | ICUSB2324I | 115 | 115 | Ingram Micro Singapore | 160 | 118.5185
6 | 2 | Cable, USB A-B, .3 meters | LCOM | CAUABHFX-03M | 14.19 | 28.38 | L-Com website | NA | 14.75
7 | 2 | USB Adapter B-A, shielded | LCOM | ECF504-BAS | 8.61 | 17.22 | L-Com website |  | 8.61
8 | 1 | 2U 16in Universal Vented Rack Mount Cantilever Shelf | StarTech | CABSHELFV | 47.99 | 47.99 | Ingram Micro Singapore | 72 | 53.3333 | ACE Peripherals | NA
9 | 1 | CPSM Cross Bar, 3Dprinted ABS-ESD7, Solid Infill, .010 Slice Height | R&D Technology | 999047233_swp | 75 | 75 | Zelta3D | 163 | 120.7407 | This part is required to have 3D printing. Alternate local 3D printing supplier quotation is under review; | Yes | WPPL-OP-093 | 2 | 2020-12-02 | 2020-12-16 | 2020-12-16
10 | 1 | CPSM Main Panel, 3Dprinted ABS-ESD7, Solid Infill, .010 Slice Height | R&D Technology | 999047232_swp | 125 | 125 | Zelta3D | 490 | 362.963 |  |  | WPPL-OP-094 | 2 | 2020-12-02 | 2020-12-16 | 2020-12-16
11 | 1 | CPSM Fluidic Docking Block, ABS-ESD7, Solid Infill, .010 Slice Height | R&D Technology | 999047123_swp | 75 | 75 | Zelta3D | 50 | 37.037 |  |  | WPPL-OP-095 | 2 | 2020-12-02 | 2020-12-16 | 2020-12-16
12 | 1 | CPSM Fluidic Docking Cap, ABS-ESD7, Solid Infill, .010 Slice Height | R&D Technology | 999047136_swp | 125 | 125 | Zelta3D | 15 | 11.1111 |  |  | WPPL-OP-096 | 2 | 2020-12-02 | 2020-12-16 | 2020-12-16
13 | 1 | CPSM L Bracket, Aluminium 0.190" thick | Model Shop | 999047221 | 225 | 225 | JEG ENGINEERING SUPPLIES | 450 | 333.3333 | Fabricate 2 sets by JEG tentatively | Yes | WPPL-OP-093 | 2 | 2020-12-02 | 2020-12-16 | 2020-12-16
14 | 0 | Paint ($300 lot charge) 2 of 3 panels only |  |  | 300 | 0 |  |  | 0 | Can model shop support? | Milford
3058.59
|  | Exchange rate | 1.35