## CPSM tester upgrade for Arc FTN
Waters CPSM upgrade for Arc FTN Transfer Timeline |  | Date: 15-Dec-2020
CPSM upgrade | Task description | Responsibility | Status | 2020-11-01 |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  | 2021-04-01 |  |  |  |  | 2021-05-01 |  |  |  | 2021-06-01 |  |  |  | 2021-07-01 |  |  |  |  | 2021-08-01 |  |  |  | 2021-09-01
|  |  |  | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24
1. Discussion and CEA approval
| CPSM upgrade BOM local source review & Dicussion | All | 2 | 2020-11-01 6: 2; 2020-11-01 13: 2
| CEA Approval | Hua Zhen/Edwin | 2 | 2020-11-01 20: 2; 2020-11-01 27: 2
2. BOM Readiness
1. PC
| - PO for PC | Hua Zhen | 2 | 2020-12-01 4: 2
| -Advance payment required | Hua Zhen/Finance | 2 | 2020-12-01 11: 2
| -Shipping to Singapore | Hua Zhen | 3 | 2020-12-01 11: 3; 2020-12-01 18: 3; 2020-12-01 25: 1; 2021-01-01 1: 1
| -Upload PC image to Flex Server | Rick | 1 | bar: 2020-12-01 25 to 2021-01-01 1
| -Setup PC and copy PC image to new PC | Hua Zhen | 1 | bar: 2021-01-01 1 to 2021-01-01 8
| -Load license for empower on new PC | Bill Bates/HuaZhen | 1 | bar: 2021-01-01 8
2.TouchScreen Monitor
| -PO for touchscreen Monitor | Hua Zhen | 2 | 2020-12-01 4: 2
| -Estimated shipping date |  | 3 | 2020-12-01 11: 3; 2020-12-01 18: 3; 2020-12-01 25: 1; 2021-01-01 1: 1; 2021-01-01 8: 1
3. 3D Printing Parts
| -3D print vendor capbility validation | Hong Min/Edwin | 1 | bar: 2020-12-01 11 to 2020-12-01 18
| -PO for 3D Printing Parts | Hua Zhen | 1 | bar: 2020-12-01 18 to 2020-12-01 25
| -3d Print parts qaulificaiton | Hong Min | 1 | bar: 2021-01-01 1 to 2021-01-01 8
4. Interface Box
| - Build and ship 2x Interface Boxes to WPPL | Rick | 1 | bar: 2021-01-01 1 to 2021-01-01 8
3. Venture Tester verify
| -Functionality check and familization | Hua Zhen | 1 | bar: 2021-01-01 1
4. Venture Tester Decomminissoing and shipping to WPPL
| -Inform Venture/ME 2x testers decommissioning for upgrade | Edwin/HuaZhen | bar: 2021-01-01 1
| -Pack and ship to WPPL | Venture/HuaZhen | 1 | bar: 2021-01-01 8
5. 2x CPSM testers upgrade in WPPL
| -Unpack, upgrade and funcional verification | Hua Zhen/Rick | 1 | bar: 2021-01-01 15 to 2021-01-01 22
| - old TE# deactive and active new TE# | Rick | 1 | bar: 2021-01-01 22
| - New test proprogram instroduction | Rick | 1 | bar: 2021-01-01 22 to 2021-01-01 29
| - Pack and ship 2x upgraded testers to Flex | Hua Zhen | 1 | bar: 2021-01-01 29
6. Ship and set up 2x Testers in Flex
| -Test equipment setup at Flex | Flex/Hua Zhen | 1 | bar: 2021-02-01 5
7. Validation 2x Testers in Flex
Complete | -Tester Validation (IQ) at Flex | Ernest/Emma | 1 | bar: 2021-02-01 12
Critical Date:
1. Decommissioning 2x Testers in Venture onWeek 8Jan 2021
2. All BOM parts should be ready on Week 15 Jan 2021
3. Complete this project on Week 15 Feb 2021
Note on B8: HuaZhen Luo: All parts should be ready on week 15 Jan 21
Note on C12: HuaZhen Luo: Est Shipping date: 16 Dec 20
Note on C18: HuaZhen Luo:
Note on B28: HuaZhen Luo: Decommisioning on week 8 Jan 2021
Note on B38: HuaZhen Luo: Complete this project on Week 15 Feb 2021

## Sheet1 (hidden)
Legend for Gantt Chart
1 | Plan
2 | closed
3 | in progress
4 | extend time

## BSM (hidden)
Acquity Binary Solvent Manager Transfer Program Overview
9/14/2009 Rev A
# of wks |  | Responsibility | Aug'09 |  |  |  |  | Sep'09 |  |  |  | Oct'09 |  |  |  | Nov'09 |  |  |  |  | Dec'09 |  |  |  | Jan'10 |  |  |  | Feb'10 |  |  |  | Mar'10 |  |  |  |  | Apr'10
|  |  | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
TG0 - Request for Proposal
| RFQ Received | Waters GSC Mgt
| Flextronics Proposal Submission (7 August 2009) | Flex GAM | bar: Aug'09 3 to Aug'09 10
| Letter of Intent - all investment activities to be linked to LoI. | Waters GSC Mgt | bar: Aug'09 17
TG1 - Program Kick Off
| Teams formed | Waters/Flex | bar: Aug'09 17 to Aug'09 24
| Furnish comphrehensive updated mfg package | Waters PM | bar: Aug'09 24
| ECO Review / Doc validation | Flex Mfg Engr | bar: Aug'09 17 to Sep'09 21
| CIS for parts that have changed (ECOs) | Flex PM | bar: Sep'09 28 to Oct'09 5
| First pass Localization Roadmap | Flex SCM | bar: Sep'09 21 to Oct'09 19
| ID equipment and training requirements | Waters Mfg Engr | bar: Sep'09 21 to Oct'09 19
| Shipment of "Golden Units / Samples" to Flex | Waters PM | bar: Sep'09 21 to Sep'09 28
| Kickoff mtg at customer site | Waters/Flex | bar: Sep'09 21
TG2A - Commercial Release
| POs - Production, Mfg & Supply Chain NREs | Waters PM | bar: Sep'09 28 to Oct'09 5
| Production Forecast / Ramp Plan | Waters/Flex Mfg | bar: Oct'09 5 to Oct'09 19
| Model Localization Step Pricing | Flex GAM | bar: Oct'09 19 to Nov'09 9
TG2B - Category A/B Localization
| NRE POs to Suppliers | Flex Materials | bar: Oct'09 5 to Oct'09 19
| Risk POs to Suppliers | Flex Materials | bar: Oct'09 12 to Oct'09 19
| Samples & FA Submission | Flex SQE | bar: Nov'09 2 to Jan'10 25
| CTB - Secure Production Material | Flex Materials | bar: Jan'10 11 to Feb'10 1
TG2C - Category C Localization
| NRE POs to Suppliers | Flex Materials | bar: Oct'09 5 to Nov'09 9
| Risk POs to Suppliers | Flex Materials | bar: Oct'09 12 to Nov'09 16
| Samples & FA Submission | Flex SQE | bar: Dec'09 14 to Mar'10 29
| PI / PO Management | Flex Materials | bar: Feb'10 1 to Apr'10 26
Other Procurement
| Set up procurement from exisiting (US) supply chain | Flex Materials | bar: Sep'09 28 to Oct'09 26
| Shutdown forecasting to existing supply chain | Waters Materials | Apr'10 12: Final - June
| Identification of Excess Material and Phase In Plan | Waters Materials | bar: Feb'10 15 to Mar'10 1; Apr'10 26
| Excess material Phase In Plan | Flex Materials | bar: Mar'10 15 to Apr'10 26
TG3 - Qualification Build / Approval
| "Critical Clean" Supplier Implementation (estimate) | Waters Mfg Engr | bar: Nov'09 2 to Mar'10 29
| Tube Assembly Cleaning Requirements | Waters Mfg Engr | bar: Sep'09 7 to Sep'09 21
| Tube cleaning equipment on order (NRE PO) | Waters Mfg Engr | bar: Sep'09 21 to Jan'10 4
| Installation of Upgrade Cleaning Equipment in Sng | Flex Mfg Engr | bar: Jan'10 11 to Jan'10 25
| Headcount hiring and cross training | Flex Ops Mgmt | bar: Nov'09 30 to Dec'09 28
| Test & mfg Equip Duplication/Validation | Waters Mfg Engr | bar: Sep'09 7 to Jan'10 18
| Training at Milford (5 weeks) | Waters Mfg | bar: Jan'10 4 to Feb'10 1
| Shipment of consigned material for qual build | Waters Mfg Engr | bar: Jan'10 11
| Shipment of consigned mfg & test equipment | Waters Mfg Engr | bar: Jan'10 25
| Equipment setup at Flex / Material Inspection | Flex Mfg Engr | bar: Feb'10 1 to Feb'10 8
| BSM Mfg Qualification Build (5 pcs Customer material) | Flex Mfg | bar: Feb'10 8
| Ship Units to Milford for Verification | Waters Quality | bar: Feb'10 8
Verification at Milford
Customer Support (on site)Gp1 | bar: Feb'10 1 to Feb'10 8
TG4 - Production Launch / Ramp
| BSM Localization Sample Build (2 pcs) | Flex Mfg | bar: Feb'10 8
| Pre-Production Risk Build | Flex Mfg
| On Site DTS Validation | Waters Quality | bar: Feb'10 22 to Mar'10 1
| Customer Support (on site)Gp2 | Waters Mfg Engr | bar: Feb'10 22 to Mar'10 8
[32 empty] | 25 | 25 | 30 | 35 | 40 | 45
12 | BSM Production Ramp | Flex Mfg | bar: Feb'10 22 to Apr'10 26
TG5 - Fully localized production (per proposal) |  | Steve/ Satya/ Waters
Not finalised - ABCD/ Critical clean/ Final list pending
Note on T5: Giles Rae: Thanksgiving Holiday in USA
Note on X5: Giles Rae: Christmas Holiday
Note on AF5: Giles Rae: Chinese New Year 14 Feb

## Manufacturing readiness (hidden)
Waters - Detector 2489 Manufacturing Infrastructure Readiness
Subject: NPI
| Date: 26-Mar'07 |  | NPI
Item |  | Action |  | Mar | Apr |  |  |  | Apr
|  | By | Status | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | Remarks
1 | NPI PO from customer
2 | NRE PO from customer
3 | Customer's Documentation
| a) BOM / assy | Waters
P/N : 630-3260 (P21 MLB) Rev 05
"EEE" : JVS
Last RFA# rec'd : 146346
| b) Process Flow/ Quality Plan | Waters
| c) Operation Lay out/ Cycle Time/ Labour | Waters
4 | Process Toolings
| a) Tooling /fixtures List | Waters
| b)Tooling /fixtures Transfer ETA | Waters
| c)Training Material, e.g. DVD Video, Training Document. | Waters
| d)Critical Process/ Specification, e.g. Clean Room Requirement | Waters
| e)Indirect Material Requirment/list/ specification | Waters
| g)Drawing/ Specification/ Procedure | Waters
5 | ST Tube Process Toolings
| a) Tooling /fixtures/Template List | Waters
| b)Tooling /fixtures/Template Transfer ETA | Waters
| c)Drawing/ Specification/ Procedure | Waters
6 | Internal Documents
| a) SYSTEM BOM | ME
| b) ECNs | ME
| c) Up-date related Document into Document Control/System | ME
| d) Up-date related Document into EDS. | Document Control
7 | Test Engineering
| a) Test fixtures & Tester Transfer ETA | Waters
| b) Tester Software / Programming Transfer ETA | Waters
| c) Test procedure/ Documentation | Waters
| d) Troubleshooting guide | Waters
| e) Spare Part for Troubleshooting | Waters
| f) Calibration & PM Program/Schedule | Waters
| h) Tester Set up | Joel
8 | Chemical Engineering
| a) Chemical list & Estm. Usage | Waters
| b) Chemical Specification/AVL (if different then Alliance) | Waters
9 | Quality Engineering
| a) Quality Plan | KL
| b) DMR/DHR | KL
| c)Audit Plan | KL
| d)Quality Check list | KL
| e)Incoming Inspection Plan/ checklist | JS
| f) SOLTRACK | Delli
| g)OQPQ /ORT procedure/Equipment | Delli
| h)Training | Delli
10 | Production
| a) Receive Waters Process/Station/Tester Lay out & Labour | Waters
| a) Production 3P Lay out | LP/Chng
| b) Station Set up/ buy off | LP/Chng/KL
| c) Training | ME
| d) FA Build | Production/ME/QA
11 | Qual run
12 | NPI shipment to Waters
i) Special Inst. for Shipment