## FTN Tester upgrade Schedule
Installation Plan |  |  | Work Day
Tester | Action Item | Status | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10
TE-15 | Installation of new test PC and test box | Planned | bar: 2021-05-31 to 2021-06-01
Actual | bar: 2021-05-31 to 2021-06-01
| Tester Configuration | Planned | bar: 2021-06-02 to 2021-06-03
Actual | bar: 2021-06-02 to 2021-06-03
| Functional Verification and Validation | Planned | bar: 2021-06-04 to 2021-06-10
Actual | bar: 2021-06-04 to 2021-06-10
Installation Plan |  |  | 2021-05-31: Work Day
Tester | Action Item | Status | 2021-06-10 | 2021-06-11 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18
TE-17 | Installation of new test PC and test box | Planned | bar: 2021-06-10
Actual | bar: 2021-06-10
| Tester Configuration | Planned | bar: 2021-06-11
Actual | bar: 2021-06-11
| Functional Verification and Validation | Planned | bar: 2021-06-11 to 2021-06-18
Actual | bar: 2021-06-11 to 2021-06-18
Tester upgrade activity will be paused till 05 July to support Q2 shipment by Venture Singapore.
Installation Plan |  |  | 2021-06-10: Work Day
Tester | Action Item | Status | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15
TE-14 | Installation of new test PC and test box | Planned | bar: 2021-07-05 to 2021-07-06
Actual
| Tester Configuration | Planned | bar: 2021-07-07 to 2021-07-08
Actual
| Functional Verification and Validation | Planned | bar: 2021-07-09 to 2021-07-15
Actual
Installation Plan |  |  | 2021-07-05: Work Day
Tester | Action Item | Status | 2021-07-16 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-26 | 2021-07-27 | 2021-07-28
TE-16 | Installation of new test PC and test box | Planned | bar: 2021-07-16 to 2021-07-19
Actual
| Tester Configuration | Planned | bar: 2021-07-20 to 2021-07-21
Actual
| Functional Verification and Validation | Planned | bar: 2021-07-22 to 2021-07-28
Actual
7 working days for tester PM - TE10 and 13
Installation Plan |  |  | 2021-07-16: Work Day
Tester | Action Item | Status | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20
TE-13 | Installation of new test PC and test box | Planned | bar: 2021-08-10 to 2021-08-11
Actual
| Tester Configuration | Planned | bar: 2021-08-12 to 2021-08-13
Actual
| Functional Verification and Validation | Planned | bar: 2021-08-16 to 2021-08-20
Actual
Installation Plan |  |  | 2021-08-10: Work Day
Tester | Action Item | Status | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02
TE-10 | Installation of new test PC and test box | Planned | bar: 2021-08-23 to 2021-08-24
Actual
| Tester Configuration | Planned | bar: 2021-08-25 to 2021-08-26
Actual
| Functional Verification and Validation | Planned | bar: 2021-08-27 to 2021-09-02
Actual
Installation Plan |  |  | 2021-08-23: Work Day
Tester | Action Item | Status | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23
TE-12 | Installation of new test PC and test box | Planned | bar: 2021-09-13 to 2021-09-14
Actual
| Tester Configuration | Planned | bar: 2021-09-15 to 2021-09-16
Actual
| Functional Verification and Validation | Planned | bar: 2021-09-17 to 2021-09-23
Actual
Installation Plan |  |  | 2021-09-13: Work Day
Tester | Action Item | Status | 2021-09-24 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-04 | 2021-10-05 | 2021-10-06
TE-11 | Installation of new test PC and test box | Planned | bar: 2021-09-24 to 2021-09-27
Actual
| Tester Configuration | Planned | bar: 2021-09-28 to 2021-09-29
Actual
| Functional Verification and Validation | Planned | bar: 2021-09-30 to 2021-10-06
Actual
Legend: | Planned Action Item
Completed Action Item
Timeline consideration
- 2 working days for hardware replacements such as tester PC, test box, monitor and cable harnesses, etc..
- 2 working days for tester configuration to get ready for functionality.
- 7 working days for functional verification and tester validation.