## Sheet1
CPSM Final Test Upgrade
Procure Parts
| PC's | 2 PC's imaged for Refurb - ready to go
Monitors
Shelves
DIO Card
Shadow Board (Printed)
Docking Station (Printed)
Shadow Board Bracket (Model Shop)
| USB-Serial Converter | bought 2 on project expense received Tues. 11/18
Standard Cables (LCOM)
Custom Cables (build)
Box Panels (out for paint)
Modify Cable Interface Box |  | 1x ready | Requires swapping out the old Box, removing the bottom panel and sending to the Model Shop
Build Custom Cables |  | 1x ready |  |  |  |  | Can be built ahead of time
Mount Shelf
Mount Monitor on Arm |  | Purchase as required |  | Refurb | NPI | Manufacturing | Requires Bench has a place to mount it | Production Automation Corp. (PAC) Arm and keyboard add-on | keyboard | #8633
arm
Mount Shadow Board |  |  |  | Refurb | NPI | Manufacturing | Requires bench has a place to mount it
Mount Docking Station |  | Manually mounts to Solvent Tray or any other convienient location
Mount PC in Shelf |  | Mounts under bench. Requires L-brackets from Model Shop
Swap Cable Interface Boxes
Route Cables to PC
Route Cables to System