## Sheet1
Pump Tray Test Capacity Enhancement (OESR 193124-TRF MJUE-BJYJL4) |  |  | WW 0320 13-17 Jan'20 | WW 0420 20-24 Jan'20 | WW 0520 27-31Jan'20 | WW 0620 03-07 Feb'20 | WW 0720 10-14 Feb'20 | WW 0820 17-21 Feb'20 | WW 0920 24-28 Feb'20 | WW 10'20 02-06 Mar'20 | WW 11'20 09-13 Mar '20 | WW 12'20 16-20 Mar'20 | WW 13'20 23-27 Mar'20 | WW 13'20 30 Mar-03 Apr '20 | WW 13'20 06-10 Apr '20 | WW 13'20 13-17 Apr '20 | WW 13'20 20-24 Apr '20 | WW 13'20 27 Apr-01 May '20 | REMARKS
TE 82526 (new) | Plan | Tester E.T.A. to Flex and verified complete
| Actual |  | 16 Jan 2020 Do Not Open
| Plan | Build Creform |  | Creform Table Setup
Actual
| Plan | Mount and Install the Pump Tray Tester
Actual
| Plan | Validation
Actual
TE 82526 Upgrade | Plan | Tester E.T.A. to Flex and verified complete
| Actual |  | 16 Jan 2020 Do Not Open
| Plan | Mount and Install the Pump Tray Tester upgrade
Actual
| Plan | Validation
Actual
TE 82526-1 Upgrade | Plan | Tester E.T.A. to Flex and verified complete
| Actual |  | 16 Jan 2020 Do Not Open
| Plan | Mount and Install the Pump Tray Tester upgrade
Actual
| Plan | Validation
Actual
TE 82526-4 Upgrade | Plan | Tester E.T.A. to Flex and verified complete
| Actual |  | 16 Jan 2020 Do Not Open
| Plan | Mount and Install the Pump Tray Tester upgrade
Actual
| Plan | Validation
Actual