## Timeline
Updated on:
2018-04-02 | FY17Q4 |  |  |  | FY18Q1 | [8 empty] | FY18Q2 | [8 empty] | FY18Q3 |  |  | FY18Q4 |  |  | Activities | Resource
| Oct | Nov |  | Dec | Jan |  |  | Feb |  |  | Mar |  |  | Apr |  |  |  | May |  |  | Jun |  | Jul | Aug | Sep | Oct | Nov | Dec
[29 empty] | Tester IQ activities - TVE MR audits - ME & QA DTS buy off (Jan 2018) - QA | PE: Yin Ying ME: Yee Hwa (Flex), Su Fern (Venture) TVE: Siew Yee QA: Eugene (Flex), Wan Jing (Venture)
Arc Bio [COMPLETED] |  |  |  | MR |  |  | DTS / Mass Production
[29 empty] | ECO activities (materials planning) - PE RFQ for new parts - PE FA / IPC buy off - QA Tester IQ activities - ME / TE Implementation - PE, ME & QA ** assumption: mainly impacting Flex | PE: Bethany ME: Yee Hwa (Flex) TE: Hua Zhen QA: Eugene (Flex)
Pul |  |  | Preparation (RFQ, ECO) | [5 empty] | SS Stent Degasser cut in (both instrument and spare)
|  |  | 100 sets seal pack (new) (RFQ & materials preparation) |  |  |  |  | Build of 100 eval sets (completed) |  |  |  | ECO & IQ activity |  | New seal pack cut in |  |  | 1. Degasser Vent Fitting, 2. Detector LCD Gasket |  |  |  | Check Valve (cut in TBA)
[29 empty] | Tester IQ activities - ME / TE New part - RFQ & purchasing - PE FA / IPC buy off - QA MR audits - ME/TE & QA DTS buy off (May 2018) - QA | PE: Bethany ME: Yee Hwa (Flex), Desmond (Venture) TE: Hua Zhen QA: Eugene (Flex), Wan Jing (Venture)
BiFrost / ACQUITY Plus | [13 empty] | Materials | BOM pkge | Consignment Build |  |  | MR | Mass production
Milford NPI eval
Tester IQ
[29 empty] | ISO preparation - ALL Materials - PE & SDE Manufacturing line - ME Training - ME & QA Build at Venture - SDE, ME, PAE & QA | PE / SDE: Yin Ying (materials), Yu Xue (Pdt Eng) ME: Su Fern (main), Yee Hwa (PCBA) PAE: Siddharth & Mandy QA: Wan Jing
QDA |  |  | PCBA build / First Article |  |  | PCBA and Sub Assy build |  |  | CNY | Sub Assy Verification |  |  | 25 units instrument build |  |  |  |  | Internal Audit |  |  | ISO Audit | Mass production
Training @ Wexford
[29 empty] | New / ECO parts readiness - PE & SDE Beta II build - ME & QA Pre-production (MR) audits - ME & QA | PE / SDE: Yin Ying, Yu Xue ME: Su Fern PAE: Siddharth QA: Wan Jing
Beacon | Beta II build | [6 empty] | ** HTL Assy last 8u for Beta II - ECO released & completed | [5 empty] | Exhibition units build
[11 empty] | Pre-Production material positioning |  |  |  |  | Pre-Production build (20 units)
TODAY
Note on AE22: sgyyso: 5 off by 27th April, 5 off 4th May, 5 off 11th May & 5 off 1st June.

## BiFrost IQ Plan
H-Class QSM | 186015018 | >> | 186015080
I-Class BSM | 186015000 | >> | 186015082
H-Class FTN | 186015017 | >> | 186015085
I-Class FTN | 186015046 | >> | 186015088

## QDA Team Visit
Wilmslow & Wexford visits to Singapore March / April 2018
Department | Who | Flies Out | In Work | Departs | Reason | Primary Site
Wilmslow PAE | Eddie Credland | Monday 26th Feb | Wed 28th Feb | Sat 10th March | Sub-assembly verification | WPPL
Wilmslow QA | Ashley Jeffrey | Friday 9th March | Monday 12th March | Thurs 22nd March | WPPL SOPs | WPPL
Wilmslow PAE | Will Hudd | Sunday 11th March | Tues 13th March | Sat 17th march | Qda source enclosure test rig | GES Venture
Wilmslow PAE | Simon Hanley | Friday 16th March | Monday 19th March | Wed 28th March | Instrument test & DHR | GES Venture
Wexford Production Build | Barry Nolan | Friday 16th March | Monday 19th March | Wed 28th March | Instrument Build | GES Venture
Wilmslow QA | Tom Roderick | Friday 16th March | Monday 19th March | Monday 2nd April | Venture SOPs | GES Venture
Wilmslow PAE | Paul Slater | Friday 23rd March | Monday 26th March | Thurs 05th April | Instrument test | GES Venture
Wexford Production Test | Tom Reddy | Friday 23rd March | Monday 26th March | Thurs 05th April | Instrument test | GES Venture
Wilmslow Management | Ray Cribbin | Saturday 24th March | Monday 26th March | Thursday 29th March | Project Management | GES Venture
Wexford QA | Andrew Crowe | Friday 30th March | Monday 2nd April | Saturday 7th April | WPPL ISO pre-audit | WPPL

## Project Team
| QDA (Venture) | Beacon (Venture) | Arc Bio (Flex) | Arc Bio (Venture) | PDA (Flex) | Pul (Flex) | BiFrost (Flex) | BiFrost (Venture)
Build Schedule
NPI / Beta Build | [6 empty] | Mid April | Mid April
Pre-Production / MR Build |  | 2018-04-01 |  |  |  |  | May 7th to May 18th | May 7th to May 18th
Production / DTS Build | [6 empty] | May 21st | May 21st
WPPL Team
Project Lead | Yin Ying / Edwin | Yin Ying / Yu Xue | Yin Ying | Yin Ying | Yin Ying / Bethany | Bethany / Yin Ying | Bethany / Yin Ying | Bethany / Yin Ying
Quality | Wan Jing / Eugene | Wan Jing / Eugene | Eugene / Jen | Wan Jing / Eugene | Eugene / Shaynee (PCBA) | Eugene / Jen | Eugene / Jen | Wan Jing / Eugene
Manufacturing | Su Fern & Yee Hwa / Desmond | Su Fern / Desmond | Yee Hwa / Desmond | Su Fern / Desmond | Desmond / Edwin | Yee Hwa / Desmond | Yee Hwa / Desmond | Desmond / Su Fern
Test & Validation | Sid & Mandy | Sid | Edwin | Edwin | Siew Yee / Edwin | Hua Zhen / Edwin | Hua Zhen / Edwin | Hua Zhen / Edwin
Materials & ECO | Bethany & Jie Hui / Yin Ying | Bethany & Jie Hui / Yin Ying | Bethany / Yin Ying | Bethany / Yin Ying | Bethany / Yin Ying | Bethany & Jie Hui / Yin Ying | Bethany & Jie Hui / Yin Ying | Bethany & Jie Hui / Yin Ying
Supply & Distribution | Kevin / Zack | Kevin / Zack | Zack / Kevin | Zack / Kevin | Zack / Kevin | Kevin / Zack | Kevin / Zack | Kevin / Zack
Finance | Alan | Alan | Alan | Alan | Alan | Alan | Alan | Alan
Sponsor | Ee Ling | Ee Ling | Ee Ling | Ee Ling | Ee Ling | Ee Ling | Ee Ling | Ee Ling
Transfer Site | Wilmslow | Wilmslow | Milford | Milford | Milford | Milford | Milford | Milford
Project Lead | Ray Cribbin | Ray Cribbin | Kris Bujold / Gayle Gaudreau | Kris Bujold / Gayle Gaudreau | Kris Bujold / Scott Stevenson | Gayle Gaudreau / Kris Bujold | Robert Cherenfant / Kris Bujold | Robert Cherenfant / Kris Bujold
Quality | Ashley Jeffery / Andrew Dean | Ashley Jeffery / Andrew Dean | Denise Soter | Denise Soter | Denise Soter | Denise Soter | Denise Soter | Denise Soter
Milford ME / Wilmslow PE | Colin Marshall, Ian Wilson, John Iveson, Coby Golden | John Iveson | Andrew Day | Randy Chin |  | TBA | Andrew Day | Andrew Day
Milford TE / Wilmslow PAE | Paul Merson | Paul Merson | Eric Turner (PDA) Mark Jussaume (TUV) | Ed Jackson | Eric Turner | Mike Cotter / Mark Jussaume | TBA | Mike Cotter
Production |  |  | Eric Turner (PDA) Mark Jussaume (TUV) | Ed Jackson | Eric Turner |  | Keith Lavellee | Keith Lavellee
Sponsor | Steve Curbishley | Steve Curbishley