## OESR Apr
Log Number | Group | ASP TSP No | Date | TE Tool No | Originator | STATUS | Problem Summary | Summary | Assignee 1 | Assignee 2 | Minutes on Feb 27, 2019 | Minutes on March 30, 2020 and Apr 30, 2020 | WPPL update on 04 May 2020 | 25 Jun 2020 review udpate | October 1 2020 update | October 28 2020 Update | November 23, 2020 Update | December Update, 2020 Update | APR Update
161186 | TE | N/A | 2016-10-26 | N/A | Desmond Ann | OPEN | "CEA 16009" is to build the Universal Coarse and Fine Align Station for PDA optics benches. | Open since 2017, June 03, 2019: CEA# WPPL19002 for 2 control box. Pending Milford to Fabricate box. ASK ERIC FOR COMPLETION DATE. March 30, 2020: Matt will dig in tomorrow, and understand what is needed, and we will see if we can get someone on it. APR 30, 2020: To advise a date - Huazhen | Bill Bates | Matt Brule | Chau to confirm with Eric if Matt and his group are working on it. | View updates from Matt | Checked with Flex, can put this acitivity KIV till 30 Jun | Matt/Stephen will continue after shutdown; add TE No/Tool. HZ check with Flex and send it | Matt: Q4 2020 estimate completion date | Working on ordering parts with China Testers. Reasign…. |  |  | To be built at same time as China systems Working on drawings
171694 | TE | NA | 2017-04-27 | N/A | Yeap Siew Yee | Open | Files pending in the 'sendbuffer' folders yet to be sent out. 1) TE83013 (HTCH tester) 2) TE83013-2 (HTCH tester) 3) TE83026-1 (CM tester) 4) TE83026-2 (CM tester) | Open Since 2017, 27-FEB-2019 Hope to get time to get this going in 2019 May 2019: Still at same status, second on project priority list March 30, 2020: HTCH updates looking like 2nd quarter completion APRIL 30, 2020: End Jun to complete the TE83026 upgrade. | Matt Brule |  | On-going | View updates from Matt |  | Target to complet it by Q3 2020 | Primier products added; TE0083013 will be shipping to Venture; target to complete upgrade by Q4 2020; | Will Clean out today or tomorrow | Pending, keeping open to track updates to TE83013 and TE83026 | Pending, keeping open to track updates to TE83013 and TE83026 | Pending, keeping open to track updates to TE83013 and TE83026
193460 | TE | N/A | 2019-07-29 | TE82475 | Luo HuaZhen | OPEN | Based on tester utilization calculation, this pressure decay tester in Flex has been used up 91.56% of total tester capacity. So we plan to buy another TE82475 tester by raising CEA. Please kindly advise the total price and estimated complete date to build this tester. Thank you Tester utilization data, FYI Tester Utilization based on Q1 & Q2’20 numbers: Prime is 79.3% Prime + Spares is 91.56% Q3 & Q4’19 numbers: Prime is 78.2% Prime + Spares is 91.5% | 26 Feb 2020: Redesign under way March 30, 2020: New tester in design proof stage now APRIL 30, 2020: In progress | Mark Jussaume |  | HuaZhen will meet Edwin to review and provide CEA to Milford when approved. | View updates from Matt |  | In progess, target to finish by end of this year. | In progess, target to finish by end of this year. | In progess, target to finish by end of this year. | Purchasing off-the-shelf solution, looking into cal / PM and CEA before writing req. | Purchasing off-the-shelf solution, looking into cal / PM and CEA before writing req. | Testers in-house in Milford, config to begin as soon as time allows.
203852 | TE | N/A | 2020-01-10 | TE83044 | Luo HuaZhen | OPEN | Flex Malaysia request to have a spare CPU with firmware for the following tester fixtures. Most of these CPU are obsoleted. Please kindly advise a spare solution. Can you please send us a spare if you have same part number? Or please advise if can use 520 CPU2K board with correct firmware version from you? Tester/Fixture# CPU Card # PCBA # 1) TE 83044 210000273 Rev G 210000345 2) TE 83002 pls refer to page 2 attachment 210000414 3) TE82718 487 CPU 081060 279002660 4) TE82961-2 PCB 210000182 210000565 5) TE82940 PCB 210000333 210000355 & 210000404 | March 30, 2020: Collecting all necessary PCBs and firmware APRIL 30, 2020: Get information on GTS with individual CPU under teststand. Install the fixture with CPU - Huazhen | Paul Deschenes | Tony Fontes | Waiting for updates from Paul | View updates from Matt. (Tony was no longer with Waters) | Install actual fixture and update Matt the date of each fixture. - HZ | Matt will load firmware and ship it out after shutdown | In pregross Matt to collect and email firmware, such that boards can be programmed in SG | In progress Matt to collect and email firmware, such that boards can be programmed in SG | In progress Matt to collect and email firmware, such that boards can be programmed in SGFirmware Part numbers in OESR for 3, need to look at remaining two Matt to email programming instruction and look up remaining PCBs | In progress Matt to collect and email firmware, such that boards can be programmed in SGFirmware Part numbers in OESR for 3, need to look at remaining two Matt to email programming instruction and look up remaining PCBs | Matt Owes instruction to HuaZhen, involve Weimen
204253 | TE | 735005108 | 27—Aug—20 | N/A | Luo HuaZhen | Open | We have complete 1st Premier TUV test in Flex as per TSP 735005108. During the run, the following items were redlined by production. Please kindly review and update if necessary. Thanks 1. On page 3, specified file name should be stated in TSP to give a clear instruction for operator to select. 2. On page 3, shunt with part number should be stated in TSP for operator to select. 3. On page 5. Leak Detect Test result should be added into Test Record. The redlined TSP is attached on page 2 |  | Mark Jussaume | [5 empty] | May be done, need to check in SAP | May be done, need to check in SAP. Now ? | Reassigned to Mark Jussaume, will be completed as part of the impending ARC Premier updates. | Reassigned to Mark Jussaume, will be completed as part of the impending ARC Premier updates. | Reassigned to Mark Jussaume, will be completed as part of the impending ARC Premier updates. Mark did not completre Matt to pick up
204371 | ME |  |  |  |  | Open | Flex report their shunt 289002227 for ASP 279003847 step 8.16 is worn out. Request to have a replacement for this shunt. Also request additional shunt 289002226 to meet production needs. Please kindly advise the build cost for shunt 289002227 and 289002226. So, we can raise a capex request by this week. Thanks |  | Alex Beaudoin | Matt Franklin | [8 empty] | Matt Franklin actively trying to aquire shunts
204443 | TE |  |  |  |  | Open | ICT Fixture TE83053 in CEI Batam failed test at U1 programming Since switching to new approved IC IS25LP032D from ISSI. Fixture is working fine with old IC FL032PIF from Micro Spansion, but this old IC FL032PIF is EOL and CEI has zero stock of this old IC. 54 pcs of this PCB were affected by this failure. CEI cannot pass test at U1 with new IC IS25LP032D from ISSI. Local ICT fixture vendor Patracarbon has accessed the ICT tester remotely and recommend working with ISSI vendor to update ICT programming code. Please kindly provide support CEI Batam to fix this issue. | ICT programming issue | Paul Deschenes | Luo Hua Zhen | [6 empty] | Active Working programming issue with fixture vendor | Active Working programming issue with fixture vendor | Active Working programming issue with fixture vendor, In process with US ICT supplier.
204486 | TE |  |  |  |  | Open | Sigmasure Data issue |  | Matt Brule | [9 empty] | Matt picking up from Mark
204492 | TE |  |  |  |  | Open | 2 CPSM testers |  | Bill Bates | [9 empty] | Work underway
214708 | TE |  |  |  |  | Open | During PM for testers PC in Venture, they found there're files under sigmaquene and sendbuffer folders for testers PC in the attached list. Please kindly be informed and clear it if necessary. |  | Matt Brule | [9 empty] | Sigmasure records to copy, will get to soon.
214621 | TE |  |  |  |  | Open | New SIT tester |  | Bill Bates | [9 empty] | Get update from Bill
214708 | TE |  |  |  |  | Open | Please be informed that tested data at below two testers in Feb cannot be pushed out to SigmaSure during PC PM. Data can be seen in SigmaQueue folder of their respective testers. 1)TE83026-1 (IP:10.249.40.27) 2)TE83064-11 (IP:10.249.40.31) Please kindly help to check and clear these files under SigmaQueue buffer. |  | Matt Brule | [9 empty] | Will get to soon
214746 | TE |  |  |  |  | Open | Sigmasure errors |  | Matt Brule | [9 empty] | Will get to soon
Categories

## Pending Items
No. | Who | When | Why | What we waiting for | Where
1 | Matt Franklin/Alex Beaudoin | 2020-10-15 | Sourcing fibre bins (Done); Building shunts now | Shunts for Flex PDA/eLambda production | Flex
2 | Matt Franklin | 2020-10-16 | Working on live readout during alignment | Improved new LED alignment tool for Venture optical bench alignment. | Venture
3 | Matt Brule(Mark J) | 2019-07-29 | Testers in-house in Milford, config to begin as soon as time allows. | New Leak Decay Tester TE82475 for Flex | Flex
4 | Matt Brule(Mark J) | 2020-10-15 | TSP 735005108 update for Acquity Premier needed to be updated | Updated TSP | Flex
5 | Matt Brule | 2021-03-05 | SigmaSure test data stop posting on TE83026-1 | SigmaSure can post test data | Venture
6 | Christopher | 2021-02-17 | Purchasing components for test box build | CPSM test box components | Venture
7 | Eric Turner | 2021-03-30 | Further Troubeshooting is required | Fix for App Crash on TE82882-13 | Flex
8 | Matt Brule | 40.Apr.21 | ASO software upgrade to 5.34 | Software to be upgrade | CEI
9 | Paul Deschenes | 2021-11-06 | Working programming issue with fixture vendor, In process with US ICT supplier. | Test software updated for ICT fixture TE83053 | CEI
10 | Christopher Oski | 2021-04-23 | Purchasing components for test box build | Components for CPSM test box build | Venture
11 | Stephen | 2016-10-26 | To be built at same time as China systems Working on drawings | build the Universal Coarse and Fine Align Station for PDA optics benches | Flex
12 | Matt Brule | 2021-01-10 | Prepare Spare for fixtures in Flex Senai | spare CPU firmware download instruction | Flex