## WPPL
Open
| To do list | Where | Working with | By When | Status | Discussion w Edwin (12th Oct)
1 | Production Meeting (Status update) | WPPL | Team | Mon | Weekly
2 | Update OESR | WPPL | Team | Mon/Tue | Weekly
3 | Online Learning in WPPL | WPPL | online | whenever available | In Progress
5 | Weekly Meeting slide update | WPPL | Team | Fri | Weekly
6 | Oct Training request form | WPPL | Mr. Wong | 15st Oct | In Progress, The training schedule was changed. Alliance is basic requirement for Acquity LC if need a certificate; | Provide Training detailed plan by 19th;
7 | One on One with Edwin | WPPL | Edwin | Fri | Weekly
8 | Review redline TSP update for Venture (already received) | Venture | Desmond | Thu | In Progress, To check status according to OESR# from the list | Huazhen to review based on OESRs and advise if it a prority to revise by 19th
| a. TSP 735000698 Rev L |  |  |  | OESR#171540; Corrected Rev M. Case Closed
| b. TSP 735000629 Rev E |  |  |  | OESR#171552; request to change password for tester; Non-technical change, OFI
| c. TSP 735002011 Rev C |  |  |  | OESR#171551; request to change password for tester; Non-technical change, OFI
| d. TSP 735002056 Rev B |  |  |  | OESR#17547; Partiailly addressed by Rev D, such as typo. The rest is OFI status.
| e. TSP 735002236 Rev F |  |  |  | OESR#171608; request to change password for tester; Non-technical change, OFI
9 | Understand calibration procedure TSP 50593 | WPPL | Self | 15th Oct 2018 | In Progress
10 | Check Alliance Template 1.9 | Flex | Mike/Edwin | 15th Oct 2018 | In Progress, replied Mike and wait for his update 17 Oct, Mike will work a chemical kit with ERA for currently TSP
12 | Performance update | WPPL | self | Fri | Weekly
13 | GTS new VMF drafting | WPPL | Tetiana | 15th Oct 2018 | In Progress, sent new VMF form and wait for update from Tanya/Ray
14 | Check with Milford about Compressed Dry Air |  | Mike Cotter |  | In Progress, the spec for filters. Sent an email to Mark/Mike on 18 Oct
15 | Review Calibration/PM master list with CMs |  | CMs | 31th Oct 2018 | In progress, Pending Flex to update the latest Master List
16 | Understand the reason of Alliance FPY, and Carrier testing | Flex | Joel | 24th Oct 2018 | In progress, Asked Joel to pull out data and looking into failure modes.
17 | CEI request TSP access on Waters Portal | CEI | Wang | 23rd Oct 2018 | Asked Wang to list all affected TSP and persons.
Closed | [5 empty] | Discussion w Edwin (12th Oct)
| To do list | Where | Working with | By When | Status
11 | Detector linearity Test IQ. Following up with James for approving | Flex | James | Mon | Done
9 | Understand calibration procedure. P/N 730002232 | WPPL | Self | 15th Oct 2018 | Done

## Venture
Open
| Venture | Owner | By When | Status | Discussion w Edwin (12th Oct)
1 | QSM flow rate (Chan trimmed R1&R2 on TE24, Collect the data & monitoring) Deliveries: Update the latest test data, especially flow rate failure on TE24 & TE1 | Chan | 18th Oct | Done for Sep on 11Oct. Keep montoring as failure rate trend down while sourcing the tubing TSP200350
2 | Pump tester tubing change frequency determing by usage ( Chan is working on this) Deliveries: Update the change freq based on the study | Chan | 18th Oct | In progress, started data collecting on 11Oct. Need more data to determine usage
6 | PC/Tester backup/image ( Using PC list to check) Deliveries: Start the PC backup and updating the PC list with backup progress | Hong Cheng/Jason | 18th Oct | Done the backup on PCB, and partially on instruments side, still in pogress, ETA Wk44.
9 | GTS qualification (- OESR) Deliveries: update WPPL regarding GTS repair progress | Jason | 18th Oct | In progress, New GTS already working with the new deployed Test Software by Sadiq and even tested 3 known good boards. Please kindly advise and check if when we are going to start the IQOQ qualification for the tester. Milford GTS UI is not function correctly. Need to follow up by rasing an OESR. Received OESR from Jason. | US GTS UI failed after upgrade by Wilmslow. - to advise who we need to follow up this problem.
11 | Needle seal force and misalignement of wash cup on FTN Deliveries: understand the relation between misalignement of wash cup and needle seal force | Lwin | 25th Oct | In progress, study the alighment between needle wash cup and needle, collecting needle seal force reading with correct alignment of wash cup.
12 | BSM/QSM Tester station PM Deliveries: complete PM by early next week | Chan | 18th Oct | In progress, 2x stations complete by 11 Oct, the rest 4 stations are ongoing.
13 | BSM/QSM FPY, high failure rate on Priming with IPA and test alarm in Sept Deliveries: Understand the failure sympton of failure and find a solution to prevent this rising of failures | Chan | 18th Oct | In progress
14 | Detector FPY report, suggested to include test stations and changing components data Deliveries: FPY report inluding the above mentioned data | Mimi | 18th Oct | In progress
15 | Column Heater FPY report update Deliveries: Adding a target line on the chart | Chan | 18th Oct | In progress
16 | No. of testers in Dashboard and Asset Munaul should be the same Deliveries: Verify and update if necessary | Hong Cheng | 18th Oct | In progress
17 | FTN tester repair parts review Deliveries: avoid to replace whole assembly of vent valve by replacing valve head instead if needed, list the failure components of tetsers | Lwin | 25th Oct | In progress, Adding latest parts
18 | Review aging OESR Deliveries: Get back the status of OESR | KL | 23th Oct | In progress
7 | FTN tester PM review Deliveries: Provide advice about feasibility of set up TUV tester and justification.Please send the reasons if it's not feasible. | Lwin | 25th Oct | Done. KIV, Engineer/operator need be trained on TUV product first and have concerns on usage.
19 | Review the Calibration/PM master list is up todate. Delieveries: 1 up todate Master list | HC | 31th Oct | In progress, Received list. Need to determine priority
Closed
| Venture | Owner | By When | Status | Discussion w Edwin (12th Oct)
3 | Check Pump Acuactor Procedure before the Matt release new one Deliveries: confirm and advise if Venture Pump Actuator is affected or not and reply the email | Chan/Hong Cheng | 28th Sep | Done
4 | Hipot Test Training record & daily check record. Need to update Matt ASAP. ( Chroma Hipot cable damage, need repair & risk accessment) Deliveries: send WPPL Training Record & Daily Check | Hong Cheng | 4th Oct | Done
5 | Tester dashboard updae. Deliveries: Send out tester dashboard by today | Hong Cheng | 28th Sep | Done
8 | Asking Jason to repair the rebooting issue PC by using the new PC backup, need to follow up with him Deliveries: Can PC be repair? If not, why? How can WPPL assist on this repair? | Jason | 4th Oct | Done, Should Scrap? 1.) Disk of the rebooting PC(old PC ) was transferred to the new PC. Always keep rebooting still happened. 2.) Disk of the new PC was cloned and redeployed with another disk. Used the new redeployed disk to the new PC and able to boot up. However, when the new redeployed disk was used in the old PC the PC still not able to boot up. 3.) Suspected that both disk of the old pc and the mother board have something wrong. 4.) Please advise if we we’ll return to you the PC.
10 | FTN pump seal ware rate. Deliveries: Send WPPL replacement parts list and est. cost | Lwin | 18th Oct | Done. Change in half yearly
19 | Cal/PM in Q4 review per build plan Deliveries: Get back the Cal/PM in Q4 | Hong Cheng | 16th Oct | Done, Next review in Q1 2019

## Flex
Open
| Flex | Owner | By When | Status | Discussion w Edwin (12th Oct)
1 | Tester PC backup/Image (using PC list to check, should buy 1-2 HDD in WPPL?) Deliveries: Start the backup and PC list is being in place to keep track | Joel | 17th Oct | In Progress, Flex has issue with inhouse policy to buy/keep Portal harddisk.
3 | Consigned equipment health check (1500 Pump) follow up Deliveries: Sourcing local supplier for the critical parts | Joel | 17th Oct | In Progress
6 | Hipot Test Training Record & daily check record. Need to repair 2x load boxes ASAP and update matt ASAP Deliveries: Send WPPL Training records & "Daily Check" record. Get 2x Load Box repaired/Calibrated. | Joel | 17th Oct | In Progress
7 | Consigned Equipement health check review (Alliance) Deliveries: Update the critical parts information | Joel | 17th Oct | In Progress
9 | Carryover SPC, Flex demo the SPC next week, need to advise the parameters under monitoring Deliveries: Flex SPC demo with right parameters to be monitoring. | Joel | 17th Oct | In Progress,demo of SPC is done.
11 | Check the old Server if it's still power on Deliveries: Justify if should turn it off | Joel | 17th Oct | In Progress
12 | Review aging OESR Deliveries: Get back the status of OESR | Joel | 23th Oct | In progress
13 | Cal/PM in Q4 review per build plan Deliveries: Get back the Cal/PM in Q4 | Joel | 17th Oct | In Porgress
14 | Check the spec of filter Deliveries: see if can source the filter for replacement as it's overused. | Joel | 18th Oct | In Progress
19 | Review the Calibration/PM master list is up todate. Delieveries: 1 up todated Master list | Joel | 31th Oct | In progress
20 | Check the Alliance FPY, what are failures caused failing 86% target | Joel | 24th Oct | In Progress
21 | Update the carrier alignment test data in past a year, what's the failure rate? What are failure modes? | Joel | 24th Oct | In Progress
Closed |  |  |  |  | Discussion w Edwin (12th Oct)
| Flex | Owner | By When | Status
2 | TSP update, need to get confirmation from Flex and reply Matt today Deliveries: Confirm the items from Matt | Joel | 28th Sep | Done
4 | Pumptray repair ( Mark is verifying the PCB before shipping) Deliveries: Keep WPPL update if a fix is found | Joel | 3rd Oct | Done
5 | Flex should inform WPPL for venture TUV PM Deliveries: Keep WPPL informed before PM start | Joel | 3rd Oct | Done
8 | Alliance Final Tester 5 intermittently hangs. Joel suspect PC issue, it's under monitoring Deliveries: Determine if repair is required or if it can be repair | Joel | 3rd Oct | Done
10 | Tester dashboard updae. Deliveries: Send WPPL Test Dashboard | Joel | 28th Sep | Done

## CEI
Open
| CEI | Owner | By When | Status | Discussion w Edwin (12th Oct)
1 | GX7310 power supply repair (Wait for CA action) Deliveris: Get support agreement from Waters UK or advise if CEI bears repair | CA | 16th Oct | In Progress, Written to Raymond Cribbin on 24 Sep 18. No reply yet
5 | Hipot Test Training Record & Daily Check record ( need to update Matt) Deliveries: Send WPPL training record and Hipot 'daily check' record | Wang | 16th Oct | Done of records update on 5th Oct. HV cable repalcement is in progress.
6 | Tester PC backup/Image ( shoud communicate with CA/Wang) Deliveries: Start to backup PC and using PC list as a tracker for progress | Wang/CA | 16th Oct | In Progress, PCBA test computer : 1. GTS (1 for Milford, 1 for Micromass) 2. Racal 3. WAT tester (2 units) 4. RF-Gen tester Test program may be regularly update by Micromass through the server computer. Batam had been regularly making backup for all the test computers. The next backup be on Oct 18.
7 | Review the Calibration/PM master list is up todate. Create one if no existing list Delieveries: 1 up todate Master list | Wang/CA | 31th Oct | In progress
Closed
| CEI | Owner | By When | Status | Discussion w Edwin (12th Oct)
2 | Update recent repaired testers. Deliveries: update WPPL the tester status after replacing parts | CA | 2nd Oct | Done, TE-82999-1 GTS fixture for 210000367. Working fine after replacing 210000412 pcba in fixture and repair to gasket.
4 | Tester Dashboard upate (new template) Deliveries: Send WPPL tester dashboard with new template | Wang | 28th Sep | Done
3 | New Degasser board request ( CA should raise new OESR) Deliveries: Raise a new OESR and collect PCB for standby | CA | 16th Oct | In Progress - Received OESR on 16Oct. The part will be arranged for collection